| Name of organization: Mukinge Youth Development Foundation(MYDF) Address: Mukinge Hills Mission Community, Box, 120092, Kasempa, Zambia Organization’s Email: youth.mukinget@gmail.com |
| --- |
| Project title: Strengthening Community Engagement for Prevention of HIV/AIDS among Vulnerable Population Groups of Youths |
| Name of the project area: 19 Wards in Kasempa District. |
| Names of Sub counties to be covered | Number of parishes to be covered per ward mentioned | Number of target villages |
| Muselepete/Kamusongolwa | 10 | 1500 |
| Mukinge | 6 | 300 |
| Kabutwitwi | 5 | 500 |
| Kivuku | 7 | 540 |
| Kamumba | 4 | 150 |
| Shibende | 5 | 300 |
| Nteete | 3 | 59 |
| Mukunashi | 4 | 400 |
| Kabusenga | 2 | 25 |
| Lubofu | 8 | 250 |
| Kelongwa | 10 | 540 |
| Mpungu | 9 | 1500 |
| Misambelombe | 6 | 350 |
| Nyoka | 25 | 2500 |
| Lunga | 15 | 500 |
| Nselauke | 18 | 1600 |
| Kaimbwe | 7 | 560 |
| Mukema | 5 | 350 |
| Kaminzekenzeke | 8 | 950 |
| Project time frame: Start date: January 2014 End date: December 2016 | Total amount requested: ZMK: 8,175,484.00 Amount in U.S. Dollars $ 1,635,096.8 |
| Targeted direct project beneficiaries by Age (stipulate number and denominator for each group) |
|  | Female | Male | Total |  |
| Age category | Target | Denominator | Target | Denominator | Target | Denominator |
| 10-14 | 8,905 | 9,540 | 7,830 | 8,440 | 16,735 | 17,980 |
| 15-24 | 9,538 | 10,772 | 8,399 | 10,532 | 17,937 | 21,304 |
| 25+ years | 9,715 | 10,462 | 9,670 | 10,496 | 19,385 | 20,958 |
| Total 1 | 28,158 | 30,774 | 25,899 | 29,468 | 54,057 | 60,242 |
| Target population by Category e.g. In school youths, CSWs, etc (only indicate numbers and denominators for each targeted population) |
| Category of Target population | Female | Male | Total |
|  | Target | Denominator | Target | Denominator | Target | Denominator |
| 1. Youths in school | 4,500 | 4,500 | 5,000 | 5,000 | 9,500 | 9,500 |
| 2. CSWs | 150 | 150 | - | - | 150 | 150 |
| 3. Couples including pregnant women | 6,536 | 7,984 | 6,536 | 7,984 | 13,073 | 15,968 |
| 4. Youth out of school | 2,908 | 3,068 | 3,846 | 4,995 | 6,754 | 8,063 |
| PLHIV | 3,380 | 4,624 | 2,285 | 3,512 | 5,665 | 8,136 |
| Other population | 14,248 | 14,998 | 14,082 | 14,802 | 28,330 | 29,800 |
| Total 2 | 31,722 | 35,324 | 31,741 | 36,293 | 63,322 | 71,467 |
| Note: Total 1 is expected to be the same as Total 2 Service providers to be trained –peer educators Category Number Volunteer Peer educators 150 Village Health Teams 50 Community resource corps/volunteers 250 TOTAL 450 Intervention Areas Targets by Intervention Areas Male Female Total Target Behavior change communication (BCC) 32,158 28,899 61,057 HIV Counseling & Testing (HCT) 17200 14800 32,000 Prevention of mother to child transmission of HIV (PMTCT) 2639 2639 Safe Male Circumcision Sensitization 16, 000 16, 000 Structural HIV prevention 39,158 38,899 78,057 Condoms distribution 1,560,000 840,000 2,400,000 |
| Key Contact person Name: Yungana Gerald Position: Executive Director Email:gerald.yungana@yahoo.com/ gyungana8@gmail.com Telephone:+260969530761 |  |

- ORGANIZATIONAL BACKGROUND AND QUALIFICATIONS

Founded in 2012 by a group of youth of Kasempa District, who decided to build a new rural society in Zambia, a society in which each of us has a chance to grow, achieve, create dignity not for ourselves but also for the future generation, and contribute to the improvement of youths, children, young women and men in health, education, environment, governance and sector innovations.

Officially registered in 2013 under the Zambian Societies Act Cap 119, 2013 Certificate Number ORS 102/39/188 on November 8th 2013, with domain “MUKINGE YOUTH DEVELOPMENT FOUNDATION- ZAMBIA” (MYDF) and after being convinced that through human rights advocacy, Corruption campaigns, HIV/AIDs sensitization and prevention and improved education innovation we shall contribute fully to the benefit of our communities.

MYDF is a charitable, nonpartisan, non-religious and non-profit organization.

MYDF is convinced that the educated people  alone cannot solve the burden of rural poor young women, young men, orphans and vulnerable children alone, but it is united effort of all people  to come up and promote meaningful cultural norms and fight away poverty, end hunger, improve health and live a good life.

MYDF is dedicated to give time and resources in all forms and efforts to facilitate development initiatives by providing assistance and working together with people to discuss and develop ideas which will meet the true needs of the community.

- Grounded in a rights-based approach, MYDF will work with professionals to mobilise communities to be health rights advocates, promoting equity and social justice for all, with a particular focus on marginalized and vulnerable populations of youths.  The organisation is guided by values of Youth driven, Faith based, Abstinence, Responsibility, team work, equality, voluntarism, confidentiality and service above self.

The project will be implemented in 19 wards in Kasempa district. Out of 19 sub counties 31 parishes will be selected and from those parishes 145 villages are targeted. This arrangement is critical because of the vastness of Kasempa district with its poor infrastructure, high rate of HIV/AIDS, early marriages, limited care for expectant mothers among other related health issues.

2.0 	PROJECT DESCRIPTION

2.1 	Problem Statement

Kasempa District is located in the North-western Province of Zambia. Kasempa is the second largest geographical District in Zambia (21, 000 sq   km). It is a rural area with an estimated population of 78, 423 people.

Kasempa is 190 km away from the Provincial Headquarters, Solwezi. Solwezi is about 800 km from the Capital City, Lusaka. Kasempa is the second largest geographical District in Zambia (21, 000 sq km). It is a rural area with an estimated population of 78,423 people.

In Kasempa District, just in reflection of national trends, HIV prevalence rates have stagnated and the number of new infections is increasing. Majority of the population (60% under 18 years, 51% female) live in rural and hard to reach areas and less than 5% have a secure income. A predominance of high risk populations and poor access to basic services, particularly for marginalized groups, presents challenges for HIV prevention in Kasempa and necessitates a combination prevention strategy

HIV/AIDS awareness campaigns in Kasempa district are being hindered by lack of funds, causing an increase in the rate of HIV infections. Kasempa district is likely to record high rate of HIV infection if no measures are put in place due to mushrooming mines which have emerged and due to lack of awareness.

The geographical and service coverage of the HIV/AIDS response by government and nongovernmental organisations in Kasempa district remains limited. The current HIV/AIDS interventions are not evenly distributed across the district, resulting in some sub-counties being left out by services. Most programs do not sufficiently reach rural areas because they cover only a few sub-counties within the district, and there is often a higher concentration of interventions around urban centers than in the rural area. Furthermore it has been noted that some of the main drivers and risk factors of the epidemic such as intact foreskin and discordance among monogamous sexual relationships are not adequately addressed.

Complex behavioral and structural drivers underpin the epidemic and a lack of comprehensive sexual reproductive health information for youths is contributing to both risky behavior (e.g. drug/substance abuse and unprotected sex with multiple partners) and low demand for and access to HIV prevention, care and treatment services. Presently, less than 50% of the population can refute all HIV and AIDS myths and misconceptions and only 69% recognize being faithful as a major prevention strategy. The knowledge that individuals do have about generalized epidemic is not being translated into practice.

Harmful socio-cultural norms such as gender inequality, early and polygamous marriages, and prostitution further exacerbate the epidemic in Kasempa. Combined with stigma and discrimination faced by people living with HIV (PLHIV) and disabled youth contributes to the HIV epidemic and hinders effective response. Lack of community-led responses to address culturally ingrained beliefs jeopardizes positive behavior change. Compounding this is a lack of appropriate services, particularly for marginalized groups. Only 15% of Kasempa’s health centers implement outreach to most at risk populations and only 1% has functional Post-Test Clubs.

The HIV prevention programming in the District has been poorly aligned to the above behavioral and structural drivers, new infections continue to rise. The individuals and particularly those from high risk groups have been negatively affected. This is straining limited resources and preventing the achievement of District and National development objectives.

2.2	Solution to the Problem

In order to address the HIV epidemic in Kasempa District, it is critical to target the structural and behavioral drivers with a focus on the identified most at risk populations. Prevention efforts need to provide these individuals with information, support and services as well as address the problems that heighten their risk, including lack of opportunity, gender inequality, and poverty.

This proposed project therefore will build on MYDF’s successful community engagement model of social and behavioral change communication, focusing on individuals from high risk populations (In school youths, commercial sex workers, Traders, youth living with HIV, and transport workers). Peer education and training as an awareness-raising strategy for sexual and reproductive health (including HIV) will be complemented by capacity building for service providers and government, including supporting increased collaboration on community-led HIV prevention efforts.

2.3	Geographical Coverage

MYDF proposes to implement this project in 19 sub counties in Kasempa district. Out of 19 sub counties 60 parishes will be selected on from those parishes 180 villages are targeted

This project will engage youths, community, and government and service providers in these communities over the three years to achieve maximum and sustained results from behavior and social change communication. Also planned are Sub-County and District-wide activities, and outreach to key most at risk populations. These activities will extend programme reach beyond the focal Parishes, ensuring the sharing of learning and good practices in targeting at risk populations.

| Sub County | Denominator (by sub county) | Target (by sub county) |
| --- | --- | --- |
|  | Male | Female | Total | Male | Female | Total |
| Mukunashi Sub-County | 11,900 | 13,100 | 25,000 | 10,675 | 10,841 | 21,516 |
| Lunga Sub-County | 7,000 | 7,200 | 14,200 | 5,224 | 5,317 | 10,541 |
| TOTAL | 18,900 | 20,300 | 39,200 | 15,899 | 16,158 | 32,057 |

2.4	Target Population

This 3 year project will directly reach 60,242 Individual community members who reside in Kasempa District with behaviour and socio-structural HIV prevention interventions, including:

To ensure a comprehensive combination HIV prevention strategy, the programme will also engage 450 service providers (i.e. Volunteer Peer Educators, CORPS  and Village Health Teams) in order to increase supply of appropriate services in support of reducing new HIV infections.

- OBJECTIVES

3.1 Project Goal: Contributing to the reduction of new HIV infections in Kasempa district by 40% by 2015.

3.2 Project Purpose: Increasing coverage, demand and utilization of comprehensive and community-led HIV prevention services.

3.3 Project Objectives:

- To empower over 32,057 individuals and communities to effectively demand for quality HIV/AIDS services and to demand for inclusive delivery of these services in Kasempa district by August 2016.

- To increase adoption of safer sexual behaviors and practices among 18,057 target populations and community members in Kasempa district by August 2016.

- To create a sustainable enabling environment that mitigates the underlying socio-cultural, gender based and other structural drivers of the HIV epidemic in Kasempa district by August 2016.

- To achieve a well coordinated HIV prevention response in Kasempa district by August 2016.

- To strengthen the monitoring and evaluation systems of the project by the end of August 2016.

- AREAS OF FOCUS AND APPROACHES TO BE USED

MYDF selected the 19 target wards through a participatory and consultative process. This process ensured: greater involvement of PLHIV (GIPA) and more meaningful involvement of PLHIV (MIPA); as well as minimising duplication of efforts; and greater engagement of key stakeholders.

In order to achieve the project goal, purpose and objectives, the proposed programme will use targeted behavioral and social change communication strategies delivered through MYDF’S integrated and cost-effective approach. These are evidence based innovative approaches to addressing drivers of the HIV/AIDS epidemic while improving the quality and efficiency of service delivery.

Regular engagement with all stakeholders will guide programme development and implementation, including the sharing of monitoring and evaluation data. Key programmes strategies are summarised in the table and outlined in further detail below.

| Programme strategies and approaches to be used |
| --- |
| Objective | Strategies to target behavioural and structural drivers |
| 1 | Youth-led peer education model that engages community volunteers, including those from targeted most at risk populations Targeted behaviour change communication with a focus on at risk populations |
| 2 | Youth-led peer education model that engages community volunteers, including those from targeted most at risk populations Activities delivered in collaboration with others and to support service providers to increase delivery and access of HIV prevention services. |
| 3 | Community-led model for social change communication Integrated livelihoods and life skills to promote HIV prevention protective factors |
| 4 | Capacity-building of service providers Sharing and learning amongst those involved in combination HIV prevention from grass-roots through to District level (extending beyond through established Western region network) |

In a bid to increase knowledge and awareness of high risk populations of safe sexual behavior and increase demand for and access to services, the project will utilize a peer education model engaging community volunteers, including  those from targeted most at risk populations. MYDF will recruit, train and support Volunteer Peer Educators (VPEs) and in order to have greater impact in the project area, 19 VPEs will be selected from each of the targeted parish. These will be individuals living and working to deliver weekly, targeted behavior change communications through awareness-raising and advocacy activities to a range of community stakeholders, with a particular focus on the identified most at risk populations in Kasempa district. These sessions will address sexual and reproductive health and life skills (including human rights, gender equity and issues of stigma and discrimination). Engaging young people from at risk populations as VPEs to support the design and delivery of these activities will ensure targeted and effective programming.

Supporting community members to be empowered, especially those from most at risk populations, with the knowledge to make informed decisions regarding their sexual and reproductive behaviour will ensure that they can live healthy, productive lives. Activities which support this objective and the overall goal focus on the ABC+ approach to HIV prevention, aligning with the National HIV Prevention Strategy and targeting those most at risk of new infections, using a community-driven approach.

It is essential to address the stigma and discrimination faced by young adults from most at risk populations thereby ensuring sustained behaviour change. For the most at risk communities to improve their sexual and reproductive behaviour and reduce HIV infection, community members, service providers and district and sub-county officials must be aware of the harmful socio-structural norms and provide support to these groups for positive behaviour change. To increase the number of community members, service providers and government actors that are aware of the socio-structural norms jeopardizing HIV prevention strategies, the programme will use targeted social change communication with a particular focus on the issues faced by most at risk populations. The VPE-led model ensures ongoing interaction between community members, supporting collective HIV prevention efforts with a focus on promotion of the ABC+ strategy, regular VCT and access to appropriate health services. Practices that have been proven to significantly reduce chances of HIV infection such as safe male circumcision will be vigorously promoted.

In order to strengthen the coordination amongst state and non-state actors delivering combination HIV prevention strategies to have more effective referral systems, MYDF will strengthen existing relationships with previously trained service providers and Civil Society Organisations (CSOs) to ensure increased access to information on HIV prevention services and support structures in targeted communities. VPEs and staff will provide referrals to and follow up on prevention, treatment and care services. In this way, the project will support linkage with providers of biomedical HIV prevention services such as PMTCT, HCT, SMC and ART. The PLHIV networks and associations as well as community stakeholders will be supported to engage with district and sub-county officials on local policy, planning and resource allocation processes on combination HIV prevention strategies. Increased collaboration will also be supported through linking to MYDF’s experience sharing network through quarterly meeting to share best practices and coordinate programming and advocacy efforts.

MYDF will support networking and/or collaboration between a range of partners over the three years in order to achieve the project objectives and goal as seen hereunder.

| Partnerships & role |
| --- |
| Partner | Role |
| Kasempa District PLHIV Network PLHIV Networks in all the targeted sub-counties/wards Community groups and networks of most at risk populations District & sub-county local government MAPP, Kuba Lusa and other NGOs, networks and coalitions operating in the area District and sub-county health centres Faith based institutions Private clinics and drug shops Cultural institutions | Support programme design and delivery to best meet the needs of most at risk populations Engaged through VPE activities in support of community-led response to HIV prevention and management of AIDS Support mobilisation of service providers and government stakeholders for capacity-building, support effective referral systems Support shared learning of good practice and advocacy efforts |

MYDF will work very closely with these identified partners, ensuring that all project activities adhere to the principles of gender equity, including incorporating sessions into the social and behaviour change communication sessions that address issues of girl’s rights and gender equity. We will also ensure that gender imbalances are addressed throughout project design, implementation and evaluation phases. These measures should ensure that our interventions address the concerns of women, girls, boys and other marginalized groups of youths.

Significant to effective programme delivery and sustainability will be alignment to district, national and international HIV and AIDS strategies. At district level, MYDF has complimented Kasempa’s District Development Plan, the Ministry of Education programme, the Ministry of Health’s National Strategic Plan for HIV/AIDS. Internationally, our efforts contribute to the attainment of MDG 6 target 7; to halt and begin to reverse the spread of HIV/AIDS by 2015.

- ACTIVITIES

Objective 1: To empower over 18,057 individuals and communities to effectively demand for quality HIV/AIDS services and to demand for inclusive delivery of these services in Kasempa district by August 2016.

This will be supporting community members, especially targeted beneficiaries to be empowered with knowledge, behaviours and practices necessary to demand for quality HIV/AIDS services and to demand for inclusive delivery of these services, so they can live healthy and productive lives.

Key activities include:

Activity 1.1.1: Project Launch at the district targeting 30 key stakeholders: MYDF will hold a project launch at the district targeting the key stakeholders in order to gain their support for effective project delivery and sustainability.

Activity 1.1.2: Conduct 180 monthly HCT Outreaches (1 outreach/month/sub-countyX3 years) for target beneficiaries (9,158 females and 8,899 males)

MYDF will work with government health facilities to target beneficiaries using daytime HCT, moonlight HCT for 100 CSWs and youth friendly service delivery approaches. CSWs will be targeted at their places of work especially in Kinembelo and other night clubs. 2 Health workers in each of these facilities will be facilitated to carry out HCT, while the testing kits will be provided freely by the District Health Office. 250 VHTs, 50 CORPs & 150 PEs will mobilise beneficiaries within their areas including out-of-school youth, In school youths, Traders, CSWs, married couples, pregnant women and other community members to undertake HCT and immediately know their results.  The outreach team shall be facilitated with meals, refreshments and facilitation fees will be provided for the health centre staff. BCC messaging, SRH, STI screening & treatment and condom distribution shall be integrated in the HCT & all other outreaches by the project. After undertaking HCT, those found positive will be referred to access HIV care, support & treatment services at accredited government health facilities and the negative ones will be encouraged to participate in fidelity clubs. All those tested will be provided risk reduction counselling to enable them lead healthy, safe & productive lives.

Activity 1.1.3: Conduct 96 quarterly PMTCT outreaches (1 outreach/quarter/sub county (08) x 3 years) for 639 pregnant women & lactating mothers

PMTCT will be promoted as a means of ensuring that all born babies are free from HIV as well as enabling PLHIV to have HIV free babies. These outreaches will be conducted by MYDF in partnership with the district HC and these will be integrated with HCT outreaches. PMTCT messages and information on EID, male involvement in PMTCT activities, community referrals for ANC, PMTCT, delivery, PNC, immunization, etc. to health facilities will also be conducted. The project VPEs and staff will also follow-up mother-baby pairs in the community and refer beneficiaries for PNC services and further follow-up at the health facilities.

Activity 1.1.4: Conduct 96 quarterly SMC outreaches (1 outreach/quarter/sub county (08) x 3 years) for 3500 males

MYDF will promote safe medical male circumcision and will work with the VHTs, PEs, CORPs, local council leaders, community leaders (religious, cultural & political) to mobilise males to benefit from this activity across the project area. MYDF will align her project activity planning with that of the District health facilities to provide quality SMC services to target beneficiaries.  SMC services & consumables will be provided by target sub county HC staff. MYDF will provide transport & facilitation fee to the government HC/hospital staff. SMC services will be provided in line with the MoH standard policies and procedures for SMC service delivery.

Objective 2: To increase adoption of safer sexual behaviors and practices among 60,242 target populations and community members in Kasempa district by August 2016.

Community members will be empowered, most especially the target populations, on how to access HCT, PMTCT, SMC, condom use and HIV prevention services so that they can live healthy and productive lives. Activities which support this objective and the overall goal focus align with the National HIV Prevention Strategy, targeting those identified as target populations, and a community-driven approach. The activities which support this objective are in line with the National HIV Prevention Strategy and overall goal focus on the ABC+ approach to HIV prevention – Abstinence, Being faithful to one uninfected partner, and correct and consistent Condom use.

Key activities under this objective include:

Activity 2.1.1: Recruit and Conduct training sessions for 38 VHTs, 19 CORPs  and 76  PEs (59 males, 40 females) in HIV combination prevention approach and effective communication skills.

MYDF staff in collaboration with DHT will recruit project VHTs and PEs. Thereafter MYDF together with DHO will conduct 1 training session to last 5 days for max. 450 participants each on HIV combination prevention approaches to a group of 450 participants including; (150 VHTs of which 19 will be PLHIV, 19 CORPs of which 8 will be PLHIV and 211 peer educators). Peer educators will include (20 in school youths, 15 youth out of school and 8 CSWs. Participants will be oriented on the current HIV/AIDS prevalence in the area, HIV epidemic (behavioural, biomedical & socio-structural) drivers in Kasempa district, HCT, SMC, PMTCT, SRH, STIs, alcohol & substance abuse, SGBV, gender and power relations in HIV&AIDS, myths & misconceptions about HIV&AIDS, condom programming, socio-structural HIV prevention, behavioral HIV prevention, community dialogues, community mobilisation, IEC/BCC, M&E tools, data collection, etc. and  roles as community resource persons for effective implementation of the project.

The trainees will be given skills in community mobilization and HIV and AIDS education to enable them mobilize and guide communities on available services, how and where to access the services including making referrals. It will also focus on communication skills, combination HIV prevention and rights to access HIV preventions services.

After the training, participants will be given materials and job aides to guide them conduct small group, peer to peer interpersonal community interactive sessions. The VHT & PEs will be provided with resource packs, training certificates and staff support visits over the course of the project as well as a monthly token to motivate them to work harder.

Activity 2.1.2:  Establish 20 condom outlets: Condom outlets will be established at designated sites in bars, hotels, lodges, video & disco halls, etc to ensure easy access of the condoms for target beneficiaries in the target sub- counties. VPEs will be responsible for managing the condom outlets to ensure proper storage of the condoms & avoid condom stock outs. Monthly reports will be written by the VPEs & submitted to MYDF project officer for this activity.

Activity 2.1.3: Procure 20 male dildos (1 per VPE): the project will procure 20 male models that will help VPEs to demonstrate condom use.

Activity 2.1.4: Procure 20 condom storage wooden boxes (1 per parish): In order to ensure safe storage of condoms, the project will put in place wooden boxes at the selected outlets. These will be conveniently located and in consideration of privacy and confidentiality.

Activity 2.1.5: Conduct condom demonstrations and distribution of 2,400,000 condoms (1,560,000 male and 840,000 female): the Project team and VPEs will deliver condom demonstrations to equip especially target populations to use condoms correctly and consistently during sexual encounters. The demonstrations and distribution will be done by the VPEs. VPEs will offer condom education and demonstrate on correct condom use with the aid of 250 male to target beneficiaries before the condoms are distributed.

Activity 2.1.6: Conduct 12 bi-annual (4 per year) drama shows for 7,000 people (3,550 females and 3,450 males)

Music, dance and drama will be used to mobilise youth and adults, especially those in harder to reach youth and adults and target populations, to introduce them to the project objectives and to disseminate targeted behavioral and social change communication messages. Messages will focus on topics such as HCT, CHCT, PMTCT, correct & consistent Condom use, SMC, EID, SGBV, stigma & discrimination, structural & behavioral HIV & AIDS drivers. Edutainment is a means of targeting large groups of people and will help to enhance interest n the activities but at the same time ensuring that those that are participating and watching also benefit from the discussions that take place during the events themselves.

Activity 2.1.7: Conduct 576 bi-monthly BCC educational sessions targeting60,242 beneficiaries (25,899 males, 28,158 females) (4 sessions/month/sub-county (08) x 3 years):

BCC sessions will be conducted for the following thematic areas including; HCT, PMTCT, SMC, SRH, condom use gender & power relations, stigma & discrimination, alcohol & substance abuse and other socio-structural and behavioural drivers of the HIV epidemic in Kasempa district. The VPEs will deliver sessions on the subjects highlighted above as well as making appropriate referrals within the target project area. This will aim at disseminating comprehensive, correct knowledge about HIV, and encouraging safer sexual behaviors and practices necessary to make informed decisions regarding their SRH and to increase understanding on SRH rights. Volunteers will use a variety of methods that include resources such as picture codes among others to disseminate information. BCC sessions will be conducted using peer-to-peer approach, small group (25-30 people) discussions/approach and interpersonal sessions.

Activity 2.1.8: Reproduce and distribute 61,057  IEC/BCC Materials: The project will reproduce the existing materials on posters and calendars with key messages on HCT, PMTCT, SMC, condom use HIV sero-discordance, ART, CHCT, EID, SGBV, Stigma & discrimination, etc for wider access to the masses. MYDF will design and advertise to youths to come up with articles to include in the IEC materials. These materials will be distributed during outreaches and they will include 3,000 posters, 9,000 charts, 2 banners, 3,000 fliers, 9,000 brochures, 3,500 calendars and 1000 T-shirt.

Objective 3: To create a sustainable enabling environment that mitigates the underlying socio-cultural, gender based and other structural drivers of the HIV epidemic in Kasempa district by August 2016.

A critical gap in combination HIV prevention strategies is the need to address underlying social cultural gender and other social drivers.  To bridge this gap, key activities to be done will include:

Activity 3.1.1: Conduct 90 community dialogue sessions (1 dialogue/every two months /sub-county x 3 years) for 60 target beneficiaries (15 elders, 20 Political, 15 cultural and 10 Religious leaders

The project will conduct 90 quarterly community dialogue sessions targeting community cultural, political and religious leaders from various parishes and villages (depending on influence) to discuss the socio- cultural, gender, other structural and behavioural drivers of the HIV epidemic in Kasempa district. Some of these include early/childhood marriages, polygamy, alcohol and drug abuse, sexual and gender based violence, forced/negotiated marriages among young girls, widow inheritance, cross generational sex, stigma and discrimination of PLHIV, etc. The dialogues will result in action plans and MYDF together with relevant stakeholders will guide implementation of agreed upon actions. Through the dialogue sessions, the community leaders are expected to make and enforce community by-laws where necessary to address structural and behavioural drivers of the HIV epidemic in their communities and areas of jurisdiction. MYDF project staff, DHT and police will facilitate these community dialogue meetings. MYDF will provide transport refund and SDA to the local government facilitators.

Activity 3.1.2: Conduct 90 (1 dialogue/ every two months /sub county(05) x 3 years) community dialogues to engage 60,242 people (25,899 males and 28,158 females) to address sexual gender based violence, childhood/ forced marriages and other socio- cultural structural drivers of HIV in Kasempa.

To address norms about masculinity related to HIV/AIDS, gender-based violence and coercion related to HIV/AIDS, legal rights and protection of women and girls impacted by HIV/AIDS, childhood/forced marriages, polygamy, widow inheritance, alcohol abuse, etc., increased male involvement in HIV prevention activities and uptake of HIV prevention services, increased access to income and productive resources of women and girls impacted by HIV/AIDS the project will engage both men and women in dialogue meetings.  The dialogues will result in action plans and MYDF together with relevant stakeholders will guide implementation of agreed upon actions by community members. The dialogue meetings will be facilitated by MYDF project staff, DHT and police in the target sub counties. MYDF will provide transport refund and SDA to the local government facilitators. About 40-45 people will be targeted per meeting.

Objective 4: To achieve a well coordinated HIV prevention response in Kasempa district by August 2016.

This will create a coordinated and supportive environment within the project area which is essential for sustained behaviour change. MYDF therefore recognizes the critical role that community-driven responses play in development.

Key activities will include:

Activity 4.1.1: Organize 6 bi-annual & participate in 12 Quarterly stakeholder DAC review meetings at the district for 30 key stakeholders:

MYDF will organise 6 bi-annual & participate in 12 quarterly stakeholder review meetings targeting key stakeholders including local government (DHO, CBO, HIV& AIDS partners) to ensure a co-ordinated HIV & AIDS response in Kasempa district and advocate for stronger combination HIV prevention strategies, programmes and budgets. Participants will be provided lunch, refreshments and transport refund.  The staff will also identify planning meetings that are held at sub-county as well as district level which they will attend to advocate with the stakeholders for improved support on HIV prevention strategies and increases financial support on activities targeting MARPS as well as youth. This is meant to influence the strategies.

Activity 4.1.2: Participate in 30 annual sub county AIDS coordination meetings (two meeting per Sub County per annum) in 3 years.

MYDF will participate in SAC meetings in each of the target 19 sub counties. SAC members and ward Local Council leaders will be facilitated with refreshments and transport refund to seek their support and ownership of project activities, review coordination of HIV & AIDS implementation and service delivery and share experiences in their respective areas. All this shall work to improve coordination and HIV service delivery in their constituencies.

MYDF will also identify planning meetings that are held at sub-county as well as district level which they will attend to advocate with the stakeholders for improved support on HIV prevention strategies and increased financial support on activities targeting key population as well as youth.

Activity 4.1.3: Develop the MYDF advocacy agenda and Participate in Annual HIV/AIDS Advocacy/ commemoration days

MYDF will participate in the HIV national advocacy/commemoration days specifically World AIDS day, international candle light day to contribute the national agenda for the year and the success of the day. The activities shall include dissemination of HIV prevention messages, distribution of IEC material and condoms, sharing of advocacy materials, health education through games and quiz.

MYDF will develop an advocacy agenda that will guide its advocacy over the three year period of this grant. The Advocacy agenda will be developed based on issues identified in the initial quarter of the project after better understanding of the challenges contributing to poor HIV and AIDS services in the district and needs of the target population. MYDF will also identify the key decision-maker(s) who have the power and influence to cause the desired change as the key target for the advocacy messages. MYDF will also identify other stakeholders and persons who have a similar interest in addressing the problem for networking and then identify joint advocacy activities and messages. This agenda will aim at contributing to improvement in HIV and AIDS services in KASEMPA district. This will be used as a guide during various HIV and AIDS advocacy events and days in the districts.

MYDF will document the key advocacy success stories which will be widely distributed to stakeholders. This will help in ensuring scalability and replication in other areas.

The project team, VHTS, CORPs & PEs and all stakeholders will be mobilised for the hosting of the candle light memorial on the eve of World AIDS Day as well as commemoration of the district organised World AIDS Day. This will further support awareness rising about HIV and to assist coordination between government and non-governmental actors in HIV prevention. The prayers will include delivering messages on HIV prevention and elimination of Mother Child HIV transmission campaign, Youth meetings sessions with youth leaders, giving testimonies by PLHIV, HCT deliverance and contributing help to the victims of HIV/AIDS.

Objective 5: To strengthen the monitoring and evaluation systems for the effective project implementation.

To ensure full implementation and greatest impact of the proposed project, the following activities will be completed:

Activity 5.1.1: Conduct 12 Quarterly Review meetings and Support Supervision visits for project Volunteers, CORPs and Peer Educators:

The project team will visit the VPE placements on a quarterly basis to meet with VPEs and community stakeholders to assess programme progress, to obtain feedback, strengthen relationships with local government and to ensure VPE welfare. This is helpful for ensuring that project VHTs & PEs implement BCC messaging and other project activities including data collection, condom education, etc. effectively and efficiently in order to achieve project goal and outcomes. It will be held for one day at the project head office and will be facilitated by the project coordinator.

Activity 5.1.2: Submit 12 Quarterly Reports: These will be delivered to the Head Office to document project progress.

Activity 5.1.3: Conduct 1 Midterm Review (Evaluation): The MTR will enable the project to make comparisons of performance of indicators against baseline values and enable an opportunity for program adjustments.

Activity 5.1.4: Conduct 6 Semesterly Board Field Visits-Monitoring visits: MYDF’s Board on a bi-annual basis will visit the project area for monitoring purposes and for quality assurance checks and ensuring value for money. These visits are essential to monitor operations of the field team in line with expected deliverables and quality standards. It is also an opportunity to build capacity of staff in key areas to ensure effective implementation and management of programme interventions.

Activity 5.1.5: Conduct 12 quarterly project review meetings for staff: MYDF will hold 12 quarterly project team meetings to review the project implementation process and trouble shoot any challenges. Quality improvement in program activities and review of the implementation plan shall be carried out in the meeting.

Activity 5.1.6: Facilitate 12 quarterly capacity building for the project staff: MYDF will facilitate her project Staff that includes Project Coordinator, M&E officer, field officer and Finance Officers attend quarterly capacity building trainings in Lusaka

Activity 5.1.7: Reproduce M&E Data collection tools:

Data will be a prerequisite at every stage of project implementation for proper monitoring and indication of project progress from the project and activity start to the end. The data collection tools will be developed both in a simplified format for the beneficiaries and other monitoring officer and standard data tools will be used by the M&E officer at program level. MYDF will reprint the standard tools to be used during data collection.

- LOGICAL FRAMEWORK MATRIX

| Hierarchy of results | Objectively Verifiable Indicators | Means of Verification | Assumptions/ Envisaged Risks |
| --- | --- | --- | --- |
| Goal: To contribute to the reduction of new HIV infections in Kasempa district by 40% by 2015. | Kasempa district HIV incidence rate Kasempa district HIV prevalence rate | AIDs Indicator Survey District Sentinel Survey |  |
| Outcome 1:60,242 individuals and communities empowered to effectively demand for quality HIV/AIDS services and to demand for inclusive delivery of these services in Kasempa district by August 2016 | % of women and men (10-59 years) that tested for HIV in the last 12 months and know their results % of HIV-positive mothers and their infants receiving a minimum package of PMTCT % of males that are circumcised % and number of people that know the nearest place where they can be tested for HIV | District LQAS reports, Annual project reports | HIV/AIDS services will be available and accessible by the targeted community |
| Output 1.1:60,242 individuals accessing HCT services | Number of individuals who received testing and counseling services for HIV and received their test results Number of individuals testing for HIV as couples | Testing forms Activity reports HCT registers | Test kits available at the health centre |
| Output 1.2: 800 expectant and lactating mothers accessing community PMTCT services through integrated HCT outreaches. | Number of pregnant women and lactating mothers reached with PMTCT messages Number of pregnant mothers referred from the communities to health facilities for ANC/PMTCT and received services Number of referrals for PNC services and infants referred for EID services Number of women who received HCT services Condoms distributed to pregnant women/lactating mothers | ANC registers Referral forms Activity reports | Expectant and lactating mothers willing to undertake PMTCT |
| Output 1.3: 4500 males circumcised through SMC outreaches. | Number of males circumcised as part of the minimum package of SMC for HIV prevention | SMC registers Activity reports Referral forms | Males will appreciate the usefulness of circumcision |
| Output 1.4: 3000 people reached through fidelity clubs activities | Number people reached by members of fidelity clubs. | List of fidelity clubs Activity reports | Community members will embrace the project |
| Activities (per objective) | Inputs |  |
| Activity 1.1.1: Launch the project at the district level 30 stakeholders | Staff, Stationery, Venue, Training manuals, Tents, Public address system, testing materials, circumcision materials, sanitization materials | Requisite resources available |
| Activity 1.1.2:Conduct 100 monthly HCT Outreaches to communities |  | Requisite resources available |
| Activity 1.1.3: Conduct 96 quarterly PMTCT outreaches |  | Requisite resources available |
| Activity1.1.4 Conduct 60 quarterly outreaches for SMC |  | Requisite resources available |
| Outcome 2: Safer sexual behaviors and practices adopted among60,242 target populations and community members in Kasempa district by August 2016. | % of females (15-49 and males 15-54) years reporting consistent condom use in the last 12 months with a non-marital sexual partner % of men and women that have disclosed their HIV results to their sexual partners in the last 12 months % of MARPS females (15-49) and males (15-54) years reporting consistent condom use with a non-marital sexual partner | LQAS survey Impact assessment Evaluation report |  |
| Outputs 2.1: 450 peer educators, corps and VHTs trained in HIV & AIDS information dissemination and mobilization skills | Number of VPEs trained and able to mobilize & disseminate HIV/AIDS information | VPE training reports Attendance lists | VPES will attend and fully participate in the organized training |
| Output 2.2: 2,400,000 condoms distributed. | Number of condom service outlets providing condoms to end users (disaggregated by female and male) Number of condoms distributed to end users | Outlet registers Condom distribution log sheets Activity reports | The district will ensure timely and adequate condom supplies. |
| Output 2.3: 10,000 people reached with messages through drama shows. | Number of drama shows conducted | Activity reports | Existing drama groups able to compose and present relevant messages |
| Output 2.4:60,242 people reached with BCC educational sessions at sub-county/town council level | Number of BCC educations sessions conducted. | BCC education reports Activity reports | Community members will be receptive and supportive of the project objectives |
| Output 2.5:60,242 of the targeted populations reached with IEC/BCC materials. | Number of IEC/BCC materials reproduced and distributed | Invoices IEC/BCC distribution log sheets | The Uganda Aids Commission will provide relevant IEC information. |
|  | Number of radio talk shows held | Partnership agreements with the radio station Recordings Activity reports photos | Radio is one of the most preferred source of information for majority of the targeted population. |
| Activities (per objective) | Inputs |  |
| Activity 2.1.1: Recruitment and training of 89 peer educators, corps and VHTs | Staff, Demonstration materials, condoms, training materials, drama groups, Facilitator/ Trainer, IEC/BCC materials, Seed capital | Requisite resources available |
| Activity 2.1.2: Establish 34 condom outlets |  | Requisite resources available |
| Activity 2.1.3: Procure 34 male dildos |  | Requisite resources available |
| Activity 2.1.4: Procure 34 condom storage wooden boxes |  | Requisite resources available |
| Activity 2.1.5: Conduct condom demonstrations and distribute 2,400,000 condoms (1560,000 male & 840,000 female) |  | Requisite resources available |
| Activity 2.1.6: Conduct 6 bi-annual drama shows for 10,000 people |  | Requisite resources available |
| Activity 2.1.7: Conduct 576 bi-monthly BCC educational sessions targeting key populations at sub-county/t/council level |  | Requisite resources available |
| Activity 2.1.8: Reproduce and Distribute 30,000 IEC/BCC Materials across the project area |  | Requisite resources available |
| Outcome 3: A sustainable enabling environment that mitigates the underlying socio-cultural, gender based and other structural drivers of the HIV epidemic in Kasempa district by August 2016. | % of women and men who experience sexual and gender based violence (SGBV) Average age of first marriage % of target population that vies SGBV as NOT acceptable % of men and women who are able to negotiate safer sex with their sexual partners % of population with accepting attitudes towards PLHIV | District LQAS report Annual report | The targeted rights and duty bearers will translate the acquired knowledge into practice. |
| Output 3.1: 60 community leaders (15 elders, 20 political, 15 cultural & 10 religious) engaged and participated in community dialogue sessions. | Number of community dialogues conducted Number of by laws enacted Number of community leaders participated & engaged in dialogue sessions Number of discouraged cultural and religious norms that perpetuate HIV epidemic | Attendance lists Activity reports | The religious and cultural and political institutions will embrace and support the project intervention |
| Output 3.2:60,242 people participate in community dialogues to address gender sexual based violence | Number of community based dialogue sessions on social-cultural, gender based and other structural drivers of the HIV epidemic Number of people attending community based dialogue sessions on social-cultural, gender based and other structural drivers of the HIV epidemic | Attendance lists Dialogue reports | The political, religious and cultural leaders will mobilize the communities to participate in the project |
| Activities (per objective) | Inputs |  |
| Activity 3.1.1: Conduct 90 community dialogue sessions (1 dialogue/ every two months per sub county x 3 years) for 60 target beneficiaries (15 elders, 20 politicians, 15 cultural and 10 religious leaders) | Staff, training manual, stationery, sports materials | Requisite resources available |
| Activity 3.1.2: Conduct 90 community dialogues (1 dialogue / every two months per sub county x 3 years) to engage60,242 people to address SGBV and socio-structural drivers of the HIV epidemic. |  | Requisite resources available |
| Outcome 4: Well-coordinated HIV prevention response in Kasempa district by August 2016. |  | Requisite resources available |
| Output 4.1: 6 bi-annual & 12 quarterly stakeholder review meetings at the District for 30 key stakeholders | Stakeholders’ challenges solved and best practices scaled | Minutes of meetings | Targeted populations willing to benefit from the project. |
| Output 4.2: CSO with an advocacy agenda in place | Advocacy agenda in place | Advocacy reports | CSO willing to develop an advocacy agenda |
| Output 4.3: 3 documented advocacy success stories in place | Number of advocacy success stories documented | Organization periodic reports Recordings from beneficiaries | Requisite resources available Organizational periodic reports available |
| Output 4.4. Participated in atleast six HIV/AIDS commemorative and advocacy day’s events organised by the district | Number of HIV/AIDS commemorative and advocacy events held and participated in. | Attendance lists Activity reports Photos | CSOs and other stakeholders willing to participate in these meeting. |

| Activities (per objective) | Inputs |  |
| --- | --- | --- |
| Activity 4.1.1: Organize 6 bi-annual & participate in 12 Quarterly stakeholder review meetings at the district | Staff, stationery, sensitization material, Referral forms, refreshments, fuel. |  |
| Activity 4.1.2: Participate in 30 annual Sub County AIDS coordination meetings | Staff, stationery, sensitization material, Referral forms, refreshments, fuel. | Requisite resources available |
| Activity 4.1.3: Develop the MYDF advocacy agenda and participate in HIV/AIDS advocacy / commemoration days’ events organised by the district. |  | Requisite resources available |
| Outcome 5: monitoring and evaluation systems for the effective project implementation. |  | Requisite resources available |
| Output 5.112 quarterly field visits & review meetings held with project volunteers , CORPs and Peer Educators | Numbers of Volunteers, CORPs and Peer Educator participate in the reviews. | Quarterly activity reports Attendance list Photos | Volunteers, CORPs and Peer Educator willingness to participate in the review meetings |
| Output 5.2 12 quarterly trips to submit reports | Number of trips done | Report submitted Donors Photos | Responsible staff submitting reports on time |
| Activities (per objective) | Inputs |  |
| Activity 5.1.1: Conduct 12 Quarterly reviews meetings and support supervision visits for project volunteer, CORPs and Peer Educator | Staff, stationery, sensitization material, activity reports, data collection tools, refreshments, fuel. | Volunteers, CORPs and Peer Educators willing to participate in the review meetings |
| Activity 5.1.2: Submit 12 Quarterly reports to Head Office |  | Responsible staff submitting reports on time |
| Activity 5.1.3: Conduct midterm Review. |  | Target beneficiaries willing to participate in the midterm review |
| Activity 5.1.4: Conduct 6 bi-annual Board Field Visits-Monitoring visits. |  | Board members willing to participate in monitoring visit. |
| Activity 5.1.5:Conduct 12 quarterly review & planning meetings for project staff |  | Targeted project staff available to attend project review & planning meetings. |
| Activity 5.1.6: Facilitate 12 quarterly capacity building for the project staff. |  | Targeted staff willing to attend the capacity building trainings. |
| Activity 5.1.7:Reproduce Monitoring and evaluation Data collection tools |  | Requisite resources available |

7.0 MONITORING AND EVALUATION NARRATIVE

- M&E Framework and Plan

| Hierarchy of Results | OVI | B | T | MOVI | F | L | F | L | R |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Goal: Contribute to the reduction of new HIV infections in Kasempa district by 40% by 2015. |
| Outcome 1:60,242 individuals and communities empowered to effectively demand for quality HIV/AIDS services and to demand for inclusive delivery of these services in Kasempa district by August 2016 | % of women and men (10-59 years) that tested for HIV in the last 12 months and know their results % of HIV-positive mothers and their infants receiving a minimum package of PMTCT % of males that are circumcised % & number of people that know the nearest place where they can be tested for HIV | TBD | 25% | Baseline and Endline Secondary Data | Annual | Project staff and M&E | Annual | M& E Officer | VPE, Staff; stationary, Secondary data |
| Output 1.1:60,242 individuals accessing HCT services | # of individuals who received Testing and Counseling services for HIV and their test results | TBD | 25,800 | HCT registers | Monthly | Project staff and M&E | Quarterly | M& E Officer | VPE, Funding for services |
| Output 1.2: 150 CSWs accessed HCT through 18 bi-monthly moonlight outreached activities. | # of CSWs accessing the HCT services | N/A | 150 | Outreach reports HCT records | Monthly | Project staff and M&E | Annual | M& E Officer | VPE, Funding for services |
| Output 1.3: 800 expectant and lactating mothers undertake PMTCT through outreaches. | # of pregnant women & lactating mothers referred from the community to health centres for ANC/PMTCT and receive services | N/A | 800 | Copy of referral forms | Monthly | Project staff and M&E | Monthly | M& E Officer | VPE, stationary, Training materials |
| Output 1.4: 4,500 males circumcised through outreaches. | # of individuals who received Safe Male Circumcision services | TBD | 4,500 | Health Centre & Clinic registers | Monthly | Project staff and M&E | Quarterly | M&E | VPE, funding for services |
| Outcome 2: Safer sexual behaviours and practices adopted among60,242 target populations and community members in Kasempa district by August 2016. | % of targeted population reporting consistent condom use with casual sexual partner | TBD | 15% | Baseline and Endline evaluation | Annual | Project staff and M&E | Annual | M&E | VPE, Project Team |
| Outputs 2.1.1: 30VHTs,16 CORPS and 43 volunteer peer educators trained in HIV & AIDS information dissemination and mobilization skills | # VPEs trained on HIV prevention peer education, including data collection | N/A | 89 | VPE training report, Participant lists | Monthly | Project staff and M&E | Quarterly | M& E Officer | Staff, stationary |
| Output 2.1.2: 2,400,000 condoms distributed. | # of condom service outlets providing condoms to the end users | N/A | 34 | Condom distribution log sheet | Monthly | Project staff and M&E | Quarterly | M&E Officer | VPE, stationary &Training |
|  | # of condoms distributed to end users | N/A | 2,400,000 | Condom distribution log sheet | Monthly | Project staff and M&E | Quarterly | M& E Officer | VPE, stationary &Training |
| Output 2.1.3: 8,000 people reached with messages through drama shows | # of people reached with drama messages | N/A | 8,000 | Photographs | Annual | Project staff and M&E | Annual | M& E Officer | VPE, Funding for services |
| Output 2.1.4:60,242 people reached with BCC educational sessions at sub-county/town council level | # of targeted populations attending the BCC educational sessions | N/A | 25,800 | Activity reports Attendance registers | Annual | Project staff and M&E | Annual | M& E Officer | VPE, Funding for services |
| Output 2.1.5: 60,262 of the targeted populations reached with IEC/BCC materials. | # of people accessing the IEC/BCC messages | N/A | 25,800 | Distribution records | Monthly | Project staff and M&E | Quarterly | M& E Officer | VPE, Funding for services |
| Outcome 3: A sustainable enabling environment that mitigates the underlying socio-cultural, gender based and other structural drivers of the HIV epidemic in Kasempa district by August 2016. | % of target population that views SGBV as NOT acceptable. | TBD | 30% | Baseline and Endline Secondary Data from UN and World Bank; | Annual | Project staff and M&E | Annual | M&E | VPE, Staff, survey team; stationary, Secondary data |
|  | % of men & women who are able to negotiate for safer sex with their sexual partners | TBD | 20% | Baseline and End line | Annual | Project staff and M&E | Annual | M&E | VPE, Staff, |
|  | % of young people engaged in transactional or cross-generational sex | TBD | 20% | Annual Project Reports | Annual | Project staff and M&E | Annual | M&E | VPE, Staff, stationary, Sec. data |
| Output 3.1.1: 60 Cultural, Elders, Political and Religious leaders develop by-laws to address structural and behavioral drivers of the HIV epidemic in their communities. | # of cultural and religious undergoing the training | N/A | 60 | Dialogue reports Attendance lists | Monthly | Project staff and M&E | Quarterly | M&E | VPE, Staff, stationary |
| Output 3.1.2:60,242 community members participate in dialogues to promote HCT, PMTCT, SMC and Condom Use | # of individuals attending community dialogues sessions | N/A | 25,800 | Activity reports Attendance lists | Monthly | Project staff and M&E | Quarterly | M&E Officer | VPE, stationary &Training |
| Outcome: 4: Well coordinated HIV prevention response in Kasempa district by August 2016 | # of government and non-government partners delivering strengthened combined HIV prevention strategies | N/A | 30 | Feedback on strengthened HIV prevention strategy interventions | Annual | Project staff and M&E | Annual | M& E Officer | Staff, stationary |
| Output 4.1.1: 12 Quarterly stakeholder stakeholders meetings held involving the District AIDS Committee, District Health Office, and District PLHIV Network leadership. | # of quarterly stakeholder meetings conducted | N/A | 12 | Staff activity log sheets, meeting minutes | Quarterly | Project staff and M&E | Quarterly | M&E Officer | Staff, stationary |
| Output 4.1.2: 30 bi-annual sub county AIDS coordination meetings held in each of the 5 sub counties | # of clients referred for other services and followed up | N/A | 30 | Referral forms | Monthly | Project staff and M&E | Quarterly | M&E Officer | VPE, stationary &Health personnel |
| Output 4.1.3: 3 documented advocacy success stories in place and HIV/AIDS commemorative and advocacy days held | # of success stories documented | N/A | 3 | Copies of documented stories Activity reports | monthly | Project staff and M&E | Quarterly | M&E Officer | Staff VHTs, VPEs and CORPs |
| Outcome 5: strengthened monitoring and evaluation systems at MYDF | # of M&E packs produced for data collectors to use | N/A | N/A | M&E packs distribution record form | Monthly | Project staff and M&E | Quarterly | M&E Officer | Staff, stationary |
| Output: 5.2.1. 12 quarterly M&E related support visits | # of M&E related support visits | N/A | 12 | M&E field monitoring reports, | Quarterly | M&E Officer | Quarterly | M&E Officer | Staff, stationary |
| Output: 5.2.4. Midterm Review (Evaluation) | Midterm review report | N/A | 1 | Evaluation report | Once; midway | M&E Officer | Once; midway | Project Coord. | Staff, stationary |
| Output: 5.2.5. Semesterly Board Field Visits-Monitoring visits | # of monitoring field visits made by the Board members | N/A | 12 | Reports | Semesterly | M&E Officer | Quarterly | M&E Officer | Stationary, fuel, funds. |

(b) Monitoring & Evaluation Narrative

- Data Collection

MYDF has competent and qualified staff who will track the project progress by collecting data from the following sources:

- Quantitative and qualitative data from the targeted populations: focus group discussions and in-depth interviews will be utilised to assess knowledge acquisition, attitudinal shift, behaviour change and replication of techniques.

- Qualitative data from key adult stakeholders assessing the development of a supportive environment for the MARPs to adopt positive behaviour change.

- Quantitative data from secondary sources (i.e. health clinic data, sub-county and district offices etc.) to correlate with self-reported data. This data will then be used in (1) tracking monthly outputs (as described in the M&E framework above), (2) measuring progress toward outcomes and (3) evaluating impact.

- Data Storage

All data collected by the Volunteer Peer Educators and staff will immediately be filed in both hard and soft form by the Monitoring and Evaluation Unit. All hard data will then be kept in files, well ordered and clearly labelled (per community) for easy referral. All soft/electronic data is entered into Excel and is then saved in the correct file (only once, with all previous versions being deleted) within a soft filing system.

- Data Analysis, Reporting, and Utilization

Once received, data will be cleaned and spot-checked. It will then be entered into an Excel and/or EpiInfo, according to the type of data.  Impact data from annual experience sharing and pre and post-tests will be analyzed by EpiInfo. Following analysis, qualitative and quantitative reports which summarize progress/challenges by placement community and overall programme will be written by the VPEs, the programme team and the M&E unit in line with MYDF’s Reporting Framework.

- Monitoring Process

MYDF possesses a comprehensive and robust participatory monitoring and evaluation system in place. The M&E unit is managed by the M&E Officer and is supported by the Programme Coordinator and the Management Committee. The following is the general procedure for M&E.

- VPEs record all field data for activities, events and lessons learnt in line with all required reporting frameworks, compiling data monthly. Training in these M&E procedures features prominently in VPE initial training.

- Through monthly support and supervision visits and quarterly M&E unit field visits, MYDF staff monitor and verify the field activities conducted by the VPEs.

- At each stage in the reporting framework, data is assessed to guide decision-making by all staff members ensuring effective utilization of the M&E data to inform programming and organizational decisions.

- Trends, progress and data are fed back regularly to community and district stakeholders as well as VPEs to ensure participatory collaboration in the use of data for planning.

- Quality Assurance

MYDF trains staff on quality assurance and staffs are expected play a central role in quality assurance by conducting data quality checks. This entails (a) staff verifying and investigating the validity of the data and case studies collected by the VPEs in the field through monthly field visits, (b) the project staff and M&E unit conduct spot-checks on all data collected and (c) inputting, reliably and completely, data into Excel. MYDF also carries out routine monitoring checks.

- Monitoring & Evaluation Capacity Building

Professional development and skill building of programme staff and M&E unit staff is a priority for MYDF. As such, an internal program for capacity building of relevant staff in M&E functions takes place on a monthly basis for each programme unit. These monthly Staff M&E Support Meetings have the objective of increasing the knowledge, skills and practice of staff who manage different parts of MYDF’s M&E systems and tools.

- Monitoring & Evaluation Budget

The total M&E costs over the three year project period is ZMK 30, 000 which accounts for 14% of the proposed budget.

- Monitoring External, Uncontrollable Factors

Key potential areas of risk and mitigating strategies are:

- Resistance by communities to MYDF’s MARP-led approach: it’ll engagement of community stakeholders throughout the programme cycle and monthly monitoring and advocacy meetings

- VPE disease/injury: VPEs trained in health & safety measures, incident prevention and emergency response procedures.

III C. CROSS CUTTING ISSUES

III. C 1. Coordination and District Participation

This project recognizes that existing structures in public, private, civil society and community which are essential for ensuring effective coordination, participation and delivery of services for people infected or affected by the HIV/AIDS epidemic in Kasempa district. This includes the local government, district AIDS coordination structures, CSO forums and networks, PHA forums and networks, and community-based organisations.

By facilitating partnerships among district departments, CSOs, PHA networks and CBOs, it is expected that duplication of activities will be minimized while referrals within the health and social support system will improve. Training district and sub-county leaders of government departments, CSOs, CBOs, PHA networks, PWD groups in HIV/AIDS action planning, resource allocation, fiduciary management, actual service provision and M&E is also expected to facilitate mobilization of communities to form groups/networks, prepare proposals and manage activities in their localities. Strengthening community management information system is expected to facilitate proper identification and targeting of vulnerable groups.

III.C.2. Gender

The prevalence of SGBV is high in Kasempa and the institutional and community response has been weak due mainly to cultural norms that promote male superiority and the submissiveness of females. Yet, the Modes of Transmission study has shown that SGBV is one of the key drivers and gender determinants of HIV/AIDS. Prevention of SGBV and responding to address the effect of SGBV is seen to contribute to reduction of HIV infections. The project will therefore strengthen capacities of medical, social and community institutions and technical staffs to prevent and respond to SGBV.

III.C.3. Community engagement

The project appreciates the complementarily of government programmes with those of civil society and local communities in order to achieve greater results. In the bid of eliminating any possibility of duplication of activities, the project design has been set to build synergy and engage with all stakeholders involved in HIV/AIDS in Kasempa district through periodic consultative meetings, project progress review meetings, presentation and incorporation project work plans and budgets into the district overall priorities, strategic plans, goals and objectives.

III.C.4. Meaningful and Greater Involvement of Persons Living with HIV (MIPA/GIPA)

The only active social infrastructure is of the PLHIV but there is absence of networks of youth clubs, post-test clubs, faith based clubs and women groups that provide psychosocial support to infected and affected persons. These are important because they represent a ready pool of volunteers to provide HIV and AIDS services at community levels such as HIV prevention, care and social support through Behavioral change communication (BCC), condom distribution, home based care (HBC), ART adherence, referrals, emotional rehabilitation, school attendance, child protection and socialization. The project will strengthen the social infrastructure of PLVHIV who are strategically positioned close to the targeted populations and empower them to implement and manage HIV/AIDS services.

III. C.5. Sustainability and Project Closeout plans

MYDF will deliberately integrate the project activities within the existing local government structures and other community groups and networks for sustainability. The project will be phased out taking into consideration the need to nurture and support the systems and structures that will have to be sustained after the project, and this is a core ingredient of the project.

MANAGEMENT SYSTEMS AND HUMAN RESOURCES

8.1 Governance and Management Structure (refer to the organizational chart)

MYDF is a registered nongovernmental organisation. See attached the organisational structure. The Secretariat is led by the Executive Director and composed of 11 full-time employees and three volunteers.

8.2 Project Management Staff for this Project

The key personnel to be supported by this project are noted below. (CVs and signed commitment letters were attached).

| Name | Position | % Effort |
| --- | --- | --- |
| Gerald Yungana | Executive Director | 100% |
| Reagan Chilumbu | Program Manager | 100% |
| Ruth Chilweza | Project Coordinator |  |
| James Mwabila | Field Officer | 100% |
| Mickel Kashale | Project Administrator | 100% |
| Carol Kalenga | Monitoring & Evaluation Officer | 100% |
| Trust Kyalifungwa | Finance & Administration Officer | 100% |
| Rodinah Musamvu | Volunteer Peer Educators | 20% |
| Glory Chibuye | Volunteer Peer Educators | 20% |

8.0 IMPLEMENTATION PLAN

| Work Plan | Year 1 | Year 2 | Year 3 | Expected outputs | Quantified targets | Responsible person |
| --- | --- | --- | --- | --- | --- | --- |
|  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |  |  |
|  | J | F | M | A | M | J | J | A | S | 0 | N | D | J | F | M | A | M | J | J | A | S | 0 | N | D | J | F | M | A | M | J | J | A | S | 0 | N | D |  |  |  |
| OBJECTIVE 1: To empower over 60,242 individuals and communities to effectively demand for quality HIV/AIDS services and to demand for inclusive delivery of these services in Kasempa district by August 2016. |
| Activity 1.1.1: Project Launch at the district targeting 30 key stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 30 key partners prepared to work with the project | One launch at the district level | MYDF Project team |
| Activity 1.1.2: Conduct 180 monthly HCT outreaches (1 outreach/month/sub-county x 3 years) for target beneficiaries (21628 females and 20639 males) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 42,267 people accessing HCT services | 108 monthly outreaches | MYDF |
| Activity 1.1.3: Conduct 60 quarterly PMTCT outreaches (1 outreach/quarter/sub county x 3 years) for 800 pregnant women & lactating mothers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 800 expectant & lactating mothers reached | 800 | MYDF Project Team |
| Activity 1.1.4: Conduct 60 quarterly SMC outreaches (1 outreach/quarter/sub county x 3 years) for 4500 males |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 4500 males circumcised | 4500 | MYDF& Project Team |
| OBJECTIVE 2: To increase adoption of safer sexual behaviors and practices among60,242 target populations and community members in Kasempa district by August 2016. |
| Activity 2.1.1: Recruit and Conduct training sessions for 30 VHTs, 16 CORPs and 43 PEs (23 males, 20 females) in HIV combination prevention approach and effective communication skills. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 70 VPEs recruited | 70 VPEs | MYDF Project team |
| Activity 2.1.2: Establish 20 condom outlets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 20 Outlets in every targeted parts | 20 | Project team |
| Activity 2.1.3: Procure 34 male dildos |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 20 male dildos procured | 20 male dildos | MYDF team |
| Activity 2.1.4: Procure 34 condom storage wooden boxes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 20 condom storage | 20 | MYDF team |
| Activity 2.1.5: Conduct condom demonstrations and distribution of 700,000 condoms (560,000 male and 140,000 female) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2,400,000 condoms distributed | 2,400,000 condoms | MYDF team |
| Activity 2.1.6: Conduct 6 bi-annual (2 per year) drama shows for 8,000 people (3,550 females and 4,450 males) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 8,000 people reached | 8,000 | MYDF team |
| Activity 2.1.7: Conduct 576 bi-annual BCC educational sessions targeting60,242 beneficiaries (25,899 males, 28,158 females) (2 sessions/month/sub county x 3 years) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 25,800 | 25,800 | MYDF team |
| Activity 2.1.8: Reproduce and distribute 61,0242 IEC/BCC Materials |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | # IEC materials reproduced and distributed | 3,000 posters, 9,000 charts, 2 banners, 9,000 fliers, 9,000 brochures, 10,000 calendars and 1000 T-shirt. | MYDF team |
| OBJECTIVE 3: To create a sustainable enabling environment that mitigates the underlying socio-cultural, gender based and other structural drivers of the HIV epidemic in Kasempa district by August 2016. |
| Activity 3.1.1: Conduct 90 community dialogue sessions (1 quarter/sub county* 3 years) for 60 target beneficiaries (15 elders, 20Political, 15 cultural and 10 Religious leaders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3600 people participating in the dialogue meetings | 3600 | MYDF team |
| Activity 3.1.2: Conduct 90 (1 dialogue/quarter/sub county x 3 years) community dialogues to engage60,242 people (28,158 females) to address sexual gender based violence, childhood/ forced marriages and other socio- cultural structural drivers of HIV in Kasempa. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 18,057 people participating in the dialogue meetings | 18,057 | MYDF team |
| Objective 4: To achieve a well coordinated HIV prevention response in Kasempa district by August 2016. |
| Activity 4.1.1: Organize 6 bi-annual & participate in 12 Quarterly stakeholder DAC review meetings at the district for 30 key stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 12 stakeholder review meetings | 12 stakeholder review meetings | MYDF team |
| Activity 4.1.2: Participate in 30 sub county AIDS coordination meetings (two meeting per Sub County per annum) in 3 years. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | # 30 DAC & SAC meetings involved in | 30 DAC& SAC meetings | MYDF team |
| Activity 4.1.3: Develop the MYDF advocacy agenda & Participate in HIV/AIDS Advocacy/ commemoration days |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Advocacy agenda in place and HIV/AIDS days commemorated | 6 days (world AIDS Day on December 1st and Philly Lutaaya Day on December 17th. | MYDF Team |
| OBJECTIVE 5: To strengthen the monitoring and evaluation systems for the effective project implementation |
| Activity 5.1.1: Conduct 12 Quarterly Review meetings and Support Supervision visits for project Volunteers, CORPs and Peer Educators |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 12 Quarterly Review meeting | 12 | MYDF Team |
| Activity 5.1.2: Submit Quarterly Reports to Donors These will be delivered to the Head Office to document project progress. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 12 quarterly reports submitted to GLOBAL HAND Head Office | 12 (quarterly) reports | MYDF M & E Officers |
| Activity 5.1.3: Conduct Midterm Review (Evaluation) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Project midterm review conducted | One project review | MYDF Team |
| Activity 5.1.4: Conduct 6 bi-annual Board Field Visits-Monitoring visits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 6 field visits | 6 | MYDF M & E Officers |
| Activity 5.1.5: Conduct 12 quarterly project review meetings for staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 12 project team review meetings | 12 | MYDF M & E Officers |
| Activity 5.1.6: Facilitate 12 quarterly capacity building for the project staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 12 capacity building activities | 12 | MYDF M & E Officers |
| Activity 5.1.7: Reproduce M&E Data collection tools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | M&E Data collection tools | 1 | M & E Officer |

- Cost Proposal - Financial Management and Budget

Kindly see the additional Excel document.

# Text boxes

BOARD MEMBERS

EXECUTIVE DIRECTOR.

PROGRAME OFFICER

ACOUNTANT OFFICER.

ADMINISTRATIVE OFFICER

PROJECT CORDINATOR

(LIVEHOOD)

PROJECT   CORDINATOR (EDUCATION)

PROJECT   CORDINATOR       (HEALTH)

SECRETARY/CSHIER

FIELD WORKER

FIELD WORKER

DRIVER

FIELD WORKER

GENERAL ASSEMBLY.