PROJECT PROPOSAL

Contact Information

Neo Minds Youth Organization

Telephone: + 255 659 386 023/+255 715 164 118

E-mail: nmyorg@gmail.com

Programs coordinator: Mr. Baraka Joel Lemsanya.

Submitted By: Neo Minds Youth Organization (NMYO)

Project Title: Project Proposal on Youth Social-economic Development Centers in Tanzania

Grand Requested: 66380$

Ngo Registration No: ooNGO/00007218

Location:  NMYO Head Offices, Arumeru district, Arusha Region-Tanzania.

Implementer Agency: Neo Minds Youth Organization (NMYO).

Account Name:  Neo Minds Youth Organization Account No:  0150200744400 CRDB BANK.

Duration:  5 years

TIME FRAME: Any time after the approval of this project

Executive summary

The areas of intervention of this project are located in Arumeru District, on the outskirts of Arusha Municipality in the suburban residential and characteristically slum areas. People living in these areas are in condition of extreme poverty and consequently they have no possibility to afford the costs of basic needs, such as shelter, education, healthcare and food.

The majority of the families have an average number of six children per household and they struggle to survive by doing odd jobs. Therefore, all the family incomes are basically oriented to first needs and in most cases they cannot afford the cost of school fees for the children. In the case of a family that can afford the cost of the school fees, most of them don’t have money to purchase school materials, as exercise books and texts. As a result most of these poor families choose very simple and poor but affordable schools for their children. Children from poor families attend schools that have no libraries or opportunities for research. Yet these very children are examined together with the rest of the better off children who have access to good schools with all the necessary facilities. The extreme consequence of this is that the children that are in need of a scholarship to continue their studies, are the ones without possibilities to obtain it. The opposite is true, that it is the well off children who after attending very good schools perform better and are eligible for free higher education at university level.

For the children from these poor families who succeed to be in school, continuing with the education is still a big challenge this is because many of them drop out (stop) due to other reasons such as family needs. For example many girls stop going to school in order to take care of the sick parent at home or boys to do some work to support the home. By the time such a child is free to go back to school it is no longer possible to continue with the regular schools. The only options are entrepreneurs and vocational skills training. However the, cost of entrepreneurs and vocational skills training, that could be considered as a middle solution between work and school, are still beyond the means of many poor families living in these slum areas.

Illiteracy have negative consequences on the whole family, for the reason that a parent that hasn’t received an education, is not able to get a good job and is not able to pay the school fees for his children. Unfortunately the same parent cares very little about the size of his family thereby creating a vicious circle of poor families transmitted from generation to generation.

Through increasing quality and access to affordable education for poor children, and skills training for poor youth and women, this project aims to give a concrete possibility of social and economic empowerment to the adults of tomorrow and to all their families. Therefore, in this project we request you to support us the amounting of 91600USD for entrepreneurs, vocational skills training and establishment of a reaction and business center, to run a literacy school, to create a library, to build a youth sport center, to run professional trainings, ICT training, training for local NGOs and CBOs, to run a didactic cinema, and to promote community development.

# Introduction

Origin of Neo Minds Youth Organization

Neo Minds Youth Organization is a non-governmental organization founded in 2013 by service minded and dedicated youth of Arusha district. Limited social and economic development prompted a team to start this organization to address unmet needs in the community. The organization has been registered under the Non-Governmental Organization Act, 2002 with the Registration number 00NGO00007218. We aim to impart skills and knowledge to young people through developing several projects which will help and support them to be productive members of the society. We believe in the power of education to help young people create a future where they can live their potential.

Goals

To improve the quality of life for oppressed, disadvantaged, and marginalized youth.

To provide support, build capacity, and integrate young people into mainstream society who have traditionally been suppressed in personal, social, economic and political domains.

Objectives

-To eradicate illiteracy among young people.

-To reduce poverty by improving economic status of young people through income generation activities.

-To improve health status of communities through health education, environmental cleanliness, and increasing access to primary health centers in remote villages.

-To organize youth into self help groups and develop their leadership qualities to facilitate making decisions at personal and social levels.

-To inculcate the habit of thrift (savings) and credit among target groups.

-To promote gender equality.

-To organize street open events to expose young people talents.

Location/ Area of Operation

Neo Minds Youth Organization office is Located at SEKEI, ARUSHA and is legally operating in the Tanzania mainland.

Target Population

Target communities served by Neo Minds Youth Organization are from the lowest strata of society. The NGO works for upliftment of young people limited by a low status in society in the areas of social, economic, domestic, personal and cultural development. The total number of people directly and indirectly benefiting from the services from Neo Minds Youth Organization is approximately 3,000 in 2014.

Major Activities

-Health care activities in rural villages include free health camps and awareness programs.

-Vocational training: Programs are organized for unemployed youth to build their skills and make them profitable.

-Training programs for groups of 10 young people include computer and music.

-Library for youth: Arusha is having only one regional library. We provide library services to young people during the week where they can build their skills in reading.

-Women’s development program: Organizing women into self-help groups, promotion of savings and credit activities, and small businesses development through micro-finance in Sekei, Arusha.

Current Projects in Neo Minds

The current project is to train young people in five colleges in Arusha about public debate format and at last have a competition among them and also organizing women into self-help groups, promotion of savings and credit activities, and small businesses development through micro-finance in Sekei, Arusha.

# Backgrounds and justification

Arumeru District is one of the 9 districts which form Arusha Region in northern Tanzania. The district lies between longitudes 36.5o to 37.5o east and latitudes 3.5o to 3.7o south of the Equator. Mount Meru which is the second highest mountain in the country with the height of 45931.8 meters above the sea level is situated in the northern part of the District. Arumeru District has an area of 2966 square Kilometers which is about 3.6 of the area of Arusha region of which total area is 82424 square kilometers. Administratively, the district is divided into 6 divisions, 37 Wards and 133 villages. It is composed of three major ethnic groups which are the more sedentary Wameru and Waarusha and the pastoralist Maasai.

This area is recurrently hit by food deficit mainly because of population pressure, erratic nature of rainfall, land shortage, backward agricultural technology (lack of modern agricultural implements and input) and so on. Regarding social services coverage this zone is backward. The primary enrollment ratio doesn't exceed 70% while that of secondary education is 15.6%. According to recent survey made by finance and economic development department nearly 60% of the population are illiterate in Iringa. The health coverage of this zone is 38% while only 19% of zonal population gets clean drinking water.

The district has numerous socioeconomic problems such as poverty, poor infrastructure, unemployment, poor social services and social ills. These make it to be incompatible with the booming population that is hungry for these services. Young population is becoming dominant population group in the town. This group is also the most affected group of society by the above stated socio –economic constraints. The young sect of society in Arumeru is alarmingly increasing from time to time because of three reasons 1) high rural to urban population 2) the strategic location of the town 3) the presence of some government institutions. Rural area of Arumeru district is generally characterized by high land shortage (in some places less than 0.3 ha per household) causing low productivity.

Because of his there is horrible poverty in rural Arumeru that forces the young to migrate to urban center especially Arusha town in search of better life, education, health and other services.

# Problem statements

The youngsters in Arumeru district have got economic and social problems. The economic problem is lack of employment opportunities. Even though youth population is dominant in the town, there are no enough jobs to absorb them and there is very high unemployment. As a result the youth do involve in illegal activities such as theft, gangsters, kidnapping and so on to sustain their lives. Common social problems are lack of recreation or entertainment centers, inadequate social facilities (health, education, and housing), etc. The lack of recreation center has led to engagement of youth in bad habits such as chewing chat (local stimulant plant) and drinking alcohol. In the study made by youth, sport and culture department of Arumeru district 75% of the youth indicated that the reason for problems caused by youth in the district is lack of entertainment centers for them. The same study also shows that 66.7% the youth spend their time chewing chat, as there is no place for recreation. In the study 75% of the youth indicated that establishment of youth center could alleviate the problems of the above-mentioned bad habits.

To observe the problems of youth one can easily go to the streets of Arumeru district and observe the army of youth wondering joblessly. In every streets of Arumeru - it is common to see them in a very large number crowding the streets without any work .If these are mobilized in organized manner; they can really bring about great change in their lives and in the society. Youth at present is being scorched by HIV/AIDS. Thus it is essential to act as soon as possible to reverse the deteriorating situation of the youth at least to maintain the sustenance of our generation. Their potentials could be used for the development of the nation if attention is paid to them. They could also contribute to attainment of our development agenda that we are hoping to attain. Recognizing this, we do present this proposal to the development partners to fund this project so that the youth can contribute to the betterment of their own life and of the community.

# Project Aim

To improve the living standards of people living in marginalized areas of Arusha/Arumeru district through entrepreneurs, educational, skills training and support.

# Specific Aims

The project will take place in Arumeru district and the project intervention will have the following specific aims;

1. Training in entrepreneurial skills

- Forming youth SACCOs,

- Micro credit soft loans

- Computer training

- Internet services

- Small home agricultural activities

- Manufacturing tourist local products for export

2. To run a youth center

3. To run a Nursery, primary school and secondary school

4. To run vocational skills trainings (metal fabrication, carpentry, tailoring, saloon, ICT)

5. To promote community development

6. To create a library

7. To build a youth sport center and to run sport activities

8. To run a cinema / a didactic cinema

9. To construct recreation and business center

- Cafeteria

- Shops

- Sport center

- Information center i.e. cultural heritage and tourist promotion  services and  marketing rural agricultural products though internet

- Film show center

10. Provision of credit to those engaged in small scale business

- Café service

- Shop trading

- Sport center

- Information center

- Film Show center

- Small agricultural activities and vocational training activities

11. To improve the capacity of the staff of local NGOs and CBOs.

# Project Objectives

The overall objective of this project is to create an enabling environment for the youth of Arumeru district in Arusha region of Tanzania so that they can be self - dependent, contribute to the development of the area and be an active participant in development effort of the nation.

Specific objectives are to inculcate entrepreneurial skills in the youth, to make youth self-employed, and initiate the youth to be engaged in sporting activities, small business (micro-credit revolving fund), vocational skills training, a didactic cinema, ICT enterprises and other similar innovative and creative projects.

# Project Activities

# Table 1:  Activities Breakdown

| S/NO | Activities | Unit | Quantity | Remark |
| --- | --- | --- | --- | --- |
| 1 | Training in entrepreneurial skills - Forming youth SACCOs - Micro credit soft loans - Computer training - Internet services - Small home agricultural activities - Cinema shooting and production - Professional tailoring, hairdresser, crafts, informatics, metal fabrication and carpentry | No of youngsters | 170 |  |
| 2 | Construction of recreation and business center - Cafeteria - Shops - Sport center / youth sport center - Information center i.e. cultural heritage and tourism promotion services, and marketing rural agricultural products though internet - Film show center - A library | Classes “ “ “ “ | 2 20 1 1 1 |  |
| 3 | Provision of credit to those engaged in small scale business - Café service - Shop trading - Sport center - Information center - Film Show center - Small agricultural activities | Youngsters “ “ “ “ | 30 80 20 20 20 |  |
| 4 | Provision of sporting materials - Football team - Volley ball team - Table tennis | No-of team “ “ | 4 4 5 |  |
| 5 | To improve the capacity of the staff of local NGOs, FBOs and CBOs | No. of NGOs, CBOs etc | 50 |  |
| 6 | To promote community development | No. of projects | 20 |  |
| 7 | Support HIV/AIDS affected families orphans | No. of HIV/AIDS supported AIDS orphans families | 40 |  |
| 8 | Employment of project personnel Employing of project coordinator | No | 1 |  |

# Activities of the project

- Training the youth on entrepreneurial skills.

- Establishing recreation and business center.

- Provision of credit services.

- Provision of sporting materials.

- Forming youth’s network of Savings and Credit Cooperative Societies (SACCOs)

- Civic education and leadership training

- Computer training

- To run a literacy school

- To run professional trainings (tailoring, hairdresser, crafts, informatics, cinema shooting and production)

- To promote community development through support to local community initiatives to improve the standards of living of the population.

- To run sport activities

- To build a youth sport center and to create a library

- To improve the capacity of the staff of local NGOs, CBOs, and FBOs

- To run vocational skills training (metal fabrication, ICT, carpentry, tailoring, saloon).

- To run a didactic cinema

- To empower local communities to search for and identify ways of addressing their developmental needs through educating and supporting young people to become effective agents of change.

- To promote gender equality through equally participation in all development activities.

- To support HIV/AIDS orphans affected families.

# Training the youth on entrepreneurial skill

Most of the youth in town are unskilled. Most don’t have enough knowledge on enterprise development, petty trading and related activities. Some have skills but their knowledge is traditional. Besides, they have no start up capital. Therefore, training on business development and going to envisaged business of their interest is the first step.

# Establishing a recreation and business center

As mentioned earlier the youth have nowhere to spend their time. Besides, as there is no job there is high unemployment. Therefore, a center that can be used as both recreation and business should be established. In the center there will be shops for young small-scale businessmen, cafeteria, sport center, information center and film showing center. In the shops & cafeteria those youngsters who took training and revolving credit shall undergo the venture of their own interest. The sport center shall provide indoor game services .The information center will give internet and information services. Film showing will launch in the small hall that is to be constructed together with the above centers. In these centers the remaining youth shall spend their time for recreation.

# Provision of revolving fund for the entrepreneurial youth

To be engaged in trading activities in the center (business & recreation) they need start up capital. To this end, they should be given revolving fund to those interested that will be collected back. The beneficiaries are those who are going to trade in the shops, involve in cafeteria service, in running sport, information center and film show. The repaid money will be given again to others who didn’t get the credit.

# Provision of sporting materials

In here different sport teams which were already formed will be given sporting materials. The sporting team’s types are football, netball, volley ball and table tennis.

# Needy Youth Support

Youth support activities  seeks to improve lives of poor young people through vocational skills for orphans and vulnerable youth (carpentry, computer maintenance, tailoring and hairdressing), educational support for 121 children, functional Adult literacy training, community development activities (micro credit; sustainable agriculture; food aid to orphans and elderly people; health and hygiene trainings), environmental protection (energy saving stoves, biogas production; rain water harvesting; use of compressed soil bricks), running a cinema showing didactic movies and cartoons to the children of the slum, supporting to the local community through the distribution of mosquito nets and medicaments, organizing sport and drama activities for the youth of the slum,  and income generation through movie shows/ sale to cover part of the costs of the organisation.

# Construction of a youth center

The project plans to construct a youth center for the youth and the poor families of people living in and around Arumeru district. This will enable NMYO to expand and improve on the educational programs already existing in NMYO. The center will constitute a meeting point for the youth people and a center of new activities and new opportunities. The center will comprise, a multipurpose hall, some classrooms, a library books storage room, two offices and toilets. The center will accommodate the literacy school for adults, a course of ICT, some recreational activities, one library and the didactic movies projection in which the target beneficiaries are 1500 persons. The youth center will be used to improve the management of local NGOs partners and thus increase their levels of sustainability. The main activities of the center are a literacy school for the children and professional trainings for youngsters and women, but it will host also some activities addressed to the whole community; a shop for selling local handcraft, trainings for local partner organization staff members, awareness meetings and free cinema. In the specific the planned activities are;

# Reference Library

One of the rooms will be fitted with shelves and stocked with reference books for infants, youth of primary and secondary school level plus general reference books and magazines. Other related assets would be a public address system, music system, a video and television system in door and out door games. The place would be organized into a resource and recreational centre where the youth can meet and recreate in a constructive and guided way where they have access to resources and information that enables them to be connected to wider society and to the world. Where awareness and sensitization programs can be run on HIV/AIDS, male / female relationships, drug abuse,  cultural heritage and tourism advertisement with reference from  achieves  including Arusha National Park. Etc.

The multipurpose hall would be furnished for use as a reading and study room or workshop and training purposes. While two rooms of the center will host a library and a study room, in which students of all levels will have the possibility to deepen the knowledge acquired at school. There will be also a general book section for leisure reading. This facility will give the possibility to the students attending low level schools, to be prepared for the final exams. There will be also a veranda space where a wider public will have the possibility to read in a comfortable and quite environment.

# ICT Training

The course of computer directed by NMYO animators will involve the young people of the community of Arumeru and the women who cannot be admitted to similar courses because of the age, of the cost and the level of education. The number of beneficiaries will target a particular part of the population, on average 72 youngsters and 50 women. The center will also offer the possibility of using computers facilities in order to train local NGOs staff and improve the quality of their administration, and acquire ICT skills for all the beneficiaries of the center.

# Vocational skills training

In the aim of improving the life quality of disadvantaged persons and to give a professional qualification to the young people, NMYO will improve the quality of the existing vocational skills training, and increase the number of beneficiaries through acquisition of more training materials and instructors. Because of the problems off insuring a constant supply of electricity (sometimes the distribution is limited to 3 – 12 hours per day) NMYO will purchase a three –phase generator. At the end of the professional training the graduates will receive a professional kit (box of tools, sewing machine) that will put them in the position to start quickly working on their own. The total number of beneficiaries is of 250 young people. Also, NMYO will organize vocational trainings for disadvantaged youth aged from 12 – 30 years, with the aim of offering vocational skills for job in the following skills areas; tailoring, hairdressing, video making / photo making in which the project will be benefiting 60 tailoring, 52 hairdressing, and 30 video-making / photo youths.

# Support HIV/AIDS affected families

The HIV affected persons will be supported through the subsidies of medical care for the affected and start up input for the head of family in order to set up income generating activities. Furthermore the beneficiaries of the program will be referred to medical centers in order to receive free medical care and antiretroviral. Among the families supported by NMYO, 40 of them, the most disadvantaged ones, will receive a further support through food distribution.

# Training for local NGOs

The project plans to carry out staff training of local NGOs, FBOs and CBOs through seminars of two / three days on the following topics; human resources management, accountability and transparency, civic education, women/ youth participation, HIV/AIDS prevention, midwives and traditional birth attendants training, family planning, sustainability, project coordination, administration, project formulation and design, monitoring and evaluation, and similar project relating to GBV training and sexuality education including cultural heritage and tourism poverty reduction projects since Tanzania has no cultural heritage policy. The aim is to improve the management capacity and the organization of the local organisations. The planned number of beneficiaries is 20 persons / seminar.

# Awareness meeting

Once every month the main room will host sensitization and awareness meetings under the facilitation of professional and experienced trainers. The meetings will be followed by a discussion among the participants. The main topics will be; gender based violence, HIV/AIDS prevention, children rights, general health, and life saving strategies, women empowerment, cultural heritage and tourism promotion. The planned number of beneficiaries is 72.

# Cinema

For the youth the multimedia activities constitute a leisure and fast instrument to learn new things. Through documentaries, this activity will reach a greater number of youth in order to facilitate learning in a leisure atmosphere.

Literacy school

This activity aims at to improve NGO literacy program of informal classes for the most disadvantaged youth of the district. The aim is to give a first education to the ones whose families cannot afford the cost of a pre-school and therefore who don’t have the possibility to be prepared to pass the admission test for primary school. As part of the program, the families of these children will attend a monthly meeting to check on the performance of the pupils and will benefit from other trainings such as counseling on family planning and foreign languages (French, Chinese, Arabs, Italian and Germany).

# Sports center

The sport center will be constructed. The aim is to offer leisure activities and a meeting point to the young people of the slum and at the same time of giving to the most performing among them the opportunity to qualify for joining a national team. These activities will be;

- Construction of the sport center ; we plan to construct a sport facility that will include showers, dressing rooms, bathrooms, once meeting room, a field for soccer, one for volleyball and one for basketball.

- Sport Activities; the main activity of the center will be the improvement of the already existing soccer trainings. With the opening of the new sport grounds we will have the possibility to organize new sports activities for the free time of the young people.

In Setting up Our Partnership

In setting up our partnership in this project  it was agreed that NMYO management will be trained on how to consolidate our reciprocal exchange of skills, knowledge and experience transfer  in this partnership application, on how to maintain the given school materials, books,  medical equipment, training on how to operate the supported equipments, training on how to institutionalize ethical review of health care research and ethical issues in international collaborative health care research including ethics committee participation in this partnership, improvement of health and excellent  service delivery to the patients, adolescent sexuality reproductive health and family planning education,  and the donor partner will execute this training and not only to the NMYO  center but also to the  hospital management related youth care issues. The project partner and the NMYO will arrange together to provide this training with budget support from NMYO sources of fund and its partnership.

NMYO Contribution

We managed to own a wide area which can be used as our library. We expect to be supported any kind of books number that you can afford it.

Project strategy

First the youth will be selected for training .The selection will be carried out in collaboration with district administration and office for coordinating civic societies and social affairs. Training will be given by NMYO. The recreation and business center is to be constructed by NMYO through fund obtained from donors. When the construction is completed the youngsters who have obtained credit from the project will carry out their business in the center. The credit will be given to 170 youngsters who will engage in business activities in the center. Before credit is given they will sign agreement with NMYO. When they receive the credit they will be engaged in their business and will pay back after 1 year. After 1 year they are expected to have their own start up capital from the profit. The repaid amount will be given for other groups of youngsters who didn’t get the credit that are out the center. This will be done by NMYO in collaboration of concerned offices of the town.

The youngsters who live in the district can use the cafeteria, sport center, and information centers and film center for recreation. Therefore, the center benefits the whole youth of the district. Sporting materials will be bought and given to football and netball team, volley ball team and tennis table team. NMYO shall be in collaboration with different line offices to monitor their progress.

## Table 3:  Phasing out strategy

| No | Activities | Unit | Qty | Target by Quarter |  |  |  | Responsible Body |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |  |
| 1 | Training the youth Selection of youth Training the youth Forming SACCOs membership groups | No No | 170 170 | 170 170 | - | - | - | The project coordinator, youth and sport desk ,Department and dep't for coordinating civic societies and social affairs |
| 2 | Construction of youth center Bidding process Construction Handing over Monitoring |  |  | x - - - x | - x x x x | - - - x x | - - - x x | The project coordinator , NMYO engineer and engineer of construction and design desk |
| 3 | Credit provision Organizing the youth Signing agreement with youth Providing credit Monitoring | No No No | 170 170 170 | x - - - | x - - - x | x - - - x | x - - - x | The project coordinator, and dep't for coordinating civic societies and social affairs |
| 4 | Provide sport materials Selecting and organizing teams Purchasing sporting materials Providing materials Monitoring | No of teams LS | 13 Ls | 13 - - - x | - x - - x | - x - - x | - x - - x | The project coordinator, youth and sport desk |

## Project Input

Financial input to implement this project a total of 17850$ is needed. This is expected to be obtained from the donors. The following is the budget breakdown.

# Organization and management

This project will be implemented by Neo Minds Youth Organization (NMYO). NMYO using its own staff and the staff to be employed shall carry out the activities. NMYO                                                                   shall also monitor the progress of the project on daily basis. Evaluation shall take places involving all stakeholders the collaborating offices are youth, sport and culture offices, micro and small-scale trade and industry offices, and office for coordinating civic societies and social affairs and city administration of Iringa. These will provide technical support and collaborate in implementing, monitoring and evaluation. The donors are expected to fund the project. Donors also have the responsibility of monitoring the progress and finally evaluate. Community of Arumeru district shall involve from planning to evaluation of the project.

# Sustainability

The sustainability of this project will be guaranteed because the project involves the participation and collaboration of all concerned line offices and community. The beneficiaries through training given to them shall handle their business properly. The start up capital given on credit basis will be profitable as the beneficiaries are engaged in trade of their interest. Using the profits they will undergo their business on their own capital. Their repayment shall be used to provide as credit for who are even outside the center. It revolves from one group of beneficiaries to other youngsters. By doing so the revolving fund is expected not only to benefit the first beneficiaries but also majority of youth who have zeal to be self – employed. The project in general is expected to reduce unemployment rate.

# Expected output

## Long-term output

The youth to great extent contributed to development of the area

## Short term output

- 170 Youngsters obtained training on entrepreneurial skill.

- 1 Recreation and business center established.

- 170 Youngsters obtained revolving credit.

- 114 Youngsters obtained sporting materials.

- 170 Youngsters obtained civic education, leadership skills, gender based violence and child abuse training

- 200 Youngsters obtained computer and internet training

- Exported local made products

- Reduced poverty, illiteracy and unemployment

- Promote youngsters rights

- Promoted cultural heritage and tourism activities

## Phasing out strategy

Phasing out of a given project can be undertaken through different ways. For this project, the phasing shall take place through individuals and activities. In the first case, those youth who benefited from the project especially through credit service for the first round shall be left to continue on their own capital when they pay back the credit. Then the credit will be given to another youngster and so on. In the second case, for the first year NMYO will strictly follow up and manage the project the progress. However for the following years much of these responsibilities shall be transferred to line offices and community.

## Conclusion

In this project we request you to grant 66380$ for the implementation of this project that is expected to be conducted in Arumeru district and later the project will spread to other remained districts of Arusha. You’re kindly requested to partnership with us for the implementation of this unique project to be conducted in Tanzania.

Table 2:  The budget breakdown

| NO | Activities | Unit | Amount in USD ($) | Remark |
| --- | --- | --- | --- | --- |
| 1 | Training in entrepreneurial skill - Forming youth SACCOs - Micro credit soft loans - Computer & internet training - Success story telling - Small home agricultural activities | 1 | 8500 |  |
| 2 | Construction of recreation and business center (Cafeteria,Shops,Sport center, a library, vocational training, Information center and Film show center) | 1 | 23600 |  |
| 3 | Provision of credit to those engaged in small scale business Café service - Shop trading - Sport center - Information center - Film Show center - Small agricultural activities - Vocational training projects | “ “ “ “ | 3500 2600 2800 2000 2400 2200 |  |
| 4 | Supporting orphans education programs |  | 3200 |  |
| 5 | School Min Bus | 1 | ??? |  |
| 6 | Digital Steel Camera and Moving camera | 2 | 1800 |  |
| 7 | Laptop | 2 | 1320 |  |
| 8 | English and Science literature books | 4000 | 4000 |  |
| 9 | Fax machine, scanner, photo colored printer | 3 | 1160 |  |
| 10 | Provision of sporting materials - Football team / women soccer team - Volley ball team | “ | 3300 |  |
| 11 | Monitoring and evaluation | “ | 2000 |  |
| 12 | Photocopy materials and publication | ‘’ | 2000 |  |
| 13 | Equipment - 10 Sewing machines - 3 Sets of construction work tools - 3 Sets of hairdressing tools - Carpentry tools | 10 3 3 |  |  |
|  | Grand Total Requested |  | 66380$ |  |

Baraka Joel Lemsanya

Programs Manager

Neo Minds Youth Organization