  - Timeframe of activities/WORK PLAN

|  | Timeframe (in months) |  |
| --- | --- | --- |
| ACTIVITIES | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | RESPONSIBILITY |
| Signing of MOU | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | DONOR/ ECHF |
| Planning Meeting | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |
| Advocacy Visit to Stakeholder. |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |
| Inventory of WASH facilities. |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |
| Identification of WASHCOMs |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |
| Production of IEC materials. |  |  | X | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |
| Formation of WASHCOMs. |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |
| Training of WASHCOMs and Artisans. |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |
| Drillin of boreholes |  |  |  | X | X | X | X | x | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ECHF Driling and Building experts. |
| Monitoring of the information provided by the WASHCOMs. |  |  |  |  | x | x | x | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |
| Monthly programmatic & financial report. | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |
| Monitoring & Evaluation. | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |
| Final Project Evaluation. |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |
| Dissemination of info to the general public. |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |
| Final Report. |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |
|  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Closing of Project papers. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ECHF |