RESEARCH ON DEVELOPMENT (ROD)

BOX 2051 Tamale N/R

anaale64@yahoo.com

Project

PROPOSAL

IMPROVING SKILLS OF WOMEN IN QUALITY AGRO-PROCESSING

233(0) 03720 22151

0277 161742

Summit to:

Northern Trull Network (NOTrUNET)

PROPOSAL FACT SHEET

1.  Name of Agency:  RESEARCH ON DEVELOPMENT (ROD)

Address: BOX 2051 Tamale N/R

Phone Number   233(0) 03720 22151

E-mail address:    rodghana@yahoo.com

Contact Person:    ALBERT AKANYA

2.  Name of Project: IMPROVING SKILLS OF WOMEN IN QUALITY AGRO-PROCESSING

3.  Amount being requested: $ 4,351.63

6.  List Project staff by positions and salaries, indicating those involved in this project.

| Name | Position | Allowance |
| --- | --- | --- |
| A Albert Akanya | Director | 25 |
| D Alimi Jamiu olaid | Coordinator | 15 |
| El- John Baba | Secretary | 10 |
| La Ladidi Imoro | Field office | 12 |

7.  Total Agency Budget for a year $ 13,000

8.  Total Project Budget $6,351.63

9.  how this Project will be evaluated.

R O D in collaboration with the Northern Trull Network (NOTrUNET) of Tamale N/R Ghana, Chiefs and opinion leaders of the community through increase sales revenues of the products and also interviews will be used to evaluate the project, based on performance indicators set.

Name of Agency:  RESEARCH ON DEVELOPMENT (ROD-GHANA)

Name of Project: IMPROVING SKILLS OF WOMEN IN QUALITY AGRO-PROCESSING

Brief History and Mission of the Agency

Research on Development (ROD) is non profit established under the laws of Ghana in 2004 and headquartered in Tamale   N/R, Ghana. The roots of this organization can be traced back to the work of ROD founder AKANYA AYANUREBA, whose experiences in research, creating a children’s Health Development program in Tamale in the 2001 and an education project in Tamale in the 2004 led him to create a program for community empowerment based on Agro processing, gender, child health, malaria, HIV/AIDS and education. The program they started, now known as the ROD Community Empowerment Program (CEP), has been implemented as of 2004 in more than 103 villages in northern region of Ghana. This was accomplished with support from donors including some district assembles, global fund, Tree Aid, ministry of health, national malaria control, ministry of agriculture and mafe Ghana.

The mission of ROD is to empower northern Ghana communities to bring about sustainable development and positive social transformation based on the respect of human rights.

To promote and enhancing Gender in women rights,   malaria ,HIV/AIDS and empowerment of women in agro processing skill in the communities  through provision of knowledge, advocacy information and training.

# ROD activity is in five broad areas of Agro processing skill Training, Women empowerment, A forestation, Education, human rights, Health and Agriculture.

Description of the Project for which funding is requested.

Women in the fahazini District play a vital role in the development of their society as they engage in subsistence farming as well as agro petty trade to substance their families and community members yet they luck the modern   skill of processing of their products this resultant to low patronage of their shea and groundnut oil products in the market.

Most of these women are illiterates and would need to be trained in order to produce quality product that will meet local and international market demands and also adding them new knowledge on shea butter especial soap making, body crème, shea hair lotions .

It is believed that when the women are given the necessary training they will expand their   processing.  They will also produce quality product that will meet the local and international market demands. Over the years there was little finance by the district assembly to expand their business. Yet because of poor quality processing, the processors still cannot expand their business Due to low quality of their products. In this light, the organization wishes to train them on quality processing to meet local and international demands.

This will in effect help to alleviate poverty among women in those communities in the district.   Members of these women’s group will also meet their financial obligation; thereby help in the    upkeep of the family.

Goals/Objectives of project

To improve the quality standard of the women agro processing trade in the community through quality training processing standard so as to meet domestic local market and the international export demand, to improved training on attractive and alternative packaging of their products.

Project purpose

To increase family income of the women, hence help alleviate poverty in the community as families can afford to enroll/retain their children in school, attain quality health status, meet the cost of household up-keep and continue to sustain the shea butter/ground nut oil business.

Activities

- Mobilization and assessments of the women processors

- Sensitization of the processors on good sanitation/hygiene practices

- Training of the steps of modern quality processing

- Training of the steps of modern quality processing

- Training of simple and attractive packaging of the products

- Advocacy for maintain the quality standard of the processing

- Monitor/evaluation of project activities

Strategies

Practical involvement of the women processors will be divided into small group in other to understands the steps process of the training, they will follow the steps by each group, this will  enable the trainer identify which group is performing poorly so that they can be repeated and corrected. However, so as the processors will be ably to understand the process of the processing of quality production for market demand.

Expected Output

- Training on the quality standard of processing shea butter and groundnut oil held.

- Training on attractive and alternative packaging completed.

- Capacity of women processors for managing the quality of the products established.

Expected out comes

    - Women in fahazini are processing quality standard of shea butter and groundnut oil for domestic and

international export market.

    - The products are package simple and attractive for the domestic market demand.

    - Reliability of consuming products without being harm is totally assure

Target beneficiary

The entire women of agro processes of shea butter and groundnut oil groups in community of fahazini will  be train on quality processing and simple attractive package.

Project location

The location of the project is fahazini of savelugu  District in the northern region

##### Results

There are  significant increase in  production  of  quality produce through the  quality knowledge  of processing training resulting an increase demand of produce in the market and change in attitude of maintenance of general sanitation and hygiene have been improve as much as expected.

Monitory and evaluation

The project will be monitor and access by Research on Development (ROD-GHANA) and assembly Man of the community

CONFLICT RESOLUTION/GROUP DYNAMICS

The organization will advocate on conflict resolution in the community where the project is to take place among women in the groups this will enable the organization and groups achieve common goals for the benefit of the project in the community.

IMPLEMENTATION PLAN

| Intervention area | Specific Objective | Activities | Implementation Period |
| --- | --- | --- | --- |
| Training of women in agro processing trade | Improve the quality standard of the women agro processing trade in the community through quality training processing standard so as to meet domestic local and international export market. | Mobilization and assessments of the women processors | September |
|  | To proved quality training on attractive and simple packaging of the processes. | Sensitization of the women processors good sanitation/hygiene practices | October |
|  |  | Training of the steps of modern quality processing | November |
|  |  | Training of simple and attraction packaging of the products | December |
|  |  | Advocacy for maintain the quality standard of the processing | January |
|  |  | The network will monitoring/evaluation of activities | February –March |

Monitoring and Evaluations

| Intervention area | Activities | Output indicator | Means of verification |
| --- | --- | --- | --- |
| Quality Training of women in agro processing | Mobilize and assessments of the women processors | Women processors are physical present for training | Interview |
|  | Sensitization of the processors on good sanitation/hygiene practices | assurance good sanitation/hygiene practices of production | Interview |
|  | Training of the steps of modern quality processing | Women processors have acquire good quality processing skill | Displays of products and the test of the products |
|  | Training of simple and attractive packaging of the products | Women processors have acquire good simple and attractive packaging skill for product | Displays of products |
|  | Advocacy for maintain the quality standard of the processing | Women processors are to maintain the quality standard of the processing | Interview Displays of products and the Test of the products |
|  | Monitor/evaluation of project activities | Progress of work done will be monitored and evaluated | Interview/ visual looking. |

ACTIVITY PLAN AND   BUDGET

| OBJECTIVE | ACTIVITY | ACTIVITY ITEM | QUAT | UNIT COST | TOTAL |
| --- | --- | --- | --- | --- | --- |
| Improve the quality standard of the women agro processing trade in the community through quality training processing standard so as to meet domestic local and international export market. | Mobilization and assessments of the women processors | 1.Fuel and lubricant s 2.Mobilizations Materials 3.Community entry | 9 gallon 4 2 | 4.49 70 60 | 40.41 280 120 |
| To proved quality training on attractive and simple packaging of the processes. | Sensitization of the women processors on Good sanitation/hygiene practices | 1. Materials 2.Fuel and lubricant s 3. refreshment | 4 racks 9 gallons 2 | 40 4.49 150 | 160 40.41 300 |
|  | Training of the steps of modern quality processing | 1.Raw Processing Materials 2.Processing tools 3.Fuel and lubricant s 4. refreshment 5.wood 6.water 7. mill 8.Training consultant fee | 6 4 15 gals 2 5 2 tack 3 1 | 80 75 4.49 150 60 85 20 1,700 | 480 300 67.35 300 300 170 60 1,700 |
|  | Training of simple and attractive packaging of the products | 1. package Materials 2.package tools 3.Fuel and lubricant s 4. refreshment | 1 3 9 2 | 720 20 4,49 150 | 720 60 40.41 300 |
|  | Advocacy for maintain the quality standard of the processing | 1.Fuel and lubricant s 2. refreshment | 6 2 | 4.49 70 | 26.94 140 |
|  | Monitoring /evaluation activities of the project | 1.stationary s 2.Fuel and lubricant s 3. refreshment 4.Printing and photocopy | 2 rams 9 gallons 2 6 4 | 7 4.49 30 35 30 | 14 40.41 60 210 120 |
| TOTAL BUDGET |  |  |  |  | 4,351.63 |

Total project budget   $6,351.63

Amount being requested: $ 4,351.63

Organization contributions for the project: $ 2,000