## Sheet1
BUDGET FOR CRESSI PROJECT
COMPONENT | ACTIVITY | INDICATORS | TARGET | RESPONSIBLE PERSON | 1ST YEAR | 2ND YEAR | 3RD YEAR | BUDGET
Farmer Institutional Development | Mobilization and Sensitization of vulnerable children about this component | Vulnerable children aware of the benefits of this component | All the vulnerable children show interest | Program officers, project officers and finance manager | х |  |  | 3500000
| Grouping Vulnerable children and assessing their interest | Number of groups formed within the villages | 55 GROUPS | Village Based facilitaors, Agricultural field facilitators and project officers | х | х | х | 3000000
| Enterprise Selection/Identification of Agricultural inputs to be given | Number of enterprises selected | Low cost but high productive enterprises | Project officers, Agricultural field facilitators and Village based facilitators | х | x | x | 3500000
| Provision of Agricultural inputs to Vulnerable children as per their interest | All VC provided with agricultural inputs and practicing modern agricultural practices | 275 OVCS | Program manager, project officers, finance manger, Agricultural Field facilitators | х | х | х | 165000000
| Creating and Sourcing markets for agricultural products produced | Ready market and linkages for the produced agricultural products | Markets for produced agric products easly accessed | Project offiers |  | x | x | 5500000
| SUB TOTAL | [6 empty] | 180500000
Project Management and Sustainability
| Conducting stakeholders meetings | Minutes and attendance lists | 20 meetings | ED, PM, FM, PO | x | x | x | 12600000
| Facilitation of Project Operations at all levels | Activities running without financial interfearance | All operations facilitated | Executive Director, Finance mager | x | x | x | 240000000
| Facilitation of Village Based Facilitators | Village Based Facilitators received allowences | 20 VBF facilitated | ED, PM, FM, PO | x | x | x | 20000000
| Stakeholders Monitoring and Evaluation of project activities | Monitoring tools, repotrs and attendance lists | Through out project implementation process | ED, PM, FM, PO | x | x | x | 24000000
| Participatory Monitoring and Evaluation | Monitoring tools, repotrs and attendance lists | 4 times | All stakeholders | x | x | x | 30000000
| Report writing and assessment of project officers | Reports written, assessment reports | After every three months | Program manager, project officers, finance manger, Agricultural Field facilitators |  |  |  | 8000000
| Annual and Semi Annual Review meetings | Review reports, minutes and attendance list | 4 meetings | All stakeholders |  |  |  | 8000000
| SUB TOTAL | [6 empty] | 342600000
Technology Promotion and Farmer Access to Information
| Contracting and Facilitation of Agricultural Field Facilitaors | Number of AFFs contracted and operating | 5 AFF | Executive Director, BOD, Program Manager | х | х | х | 90000000
| Trainings of Vulnerable children Groups on improved farming agricultural practices | Number of VC groups trained by AFFs | 55 GROUPS | AFFs and VBFs | х | х | х | 15000000
| 10% NSSF Contributions for Agricultural Field facilitators | Monthly contribution to NSSF for 5AFFs | 5AFFs | Executive Director, Program manager and Finance manager | x | x | x | 9000000
| Sub Total | [6 empty] | 114000000
Opening a Vocational Training School and Facilitating trainings
| Opening a vocational school |  |  |  |  | X | X | 350000000
| TOTAL PROJECT COST | [6 empty] | 987100000
| Constigency Fund |  | 5% of Total Project Fund |  |  |  |  | 49355000
GRAND TOTAL | [7 empty] | 1036455000