## PROJECT CONCEPT

| Name of Proposing Organisation: | GOOD SHEPHERD COMMUNITY DEVELOPMENT ASSOCIATION (GSCDA) |
| --- | --- |
| Name of Project: | #### Kamuli Pilot Environmental Protection through Promoting Tree Planting and Safe Forest Saving Stoves |
| Country: | Uganda |
| Site(s)/Location(s): | Kitayunjwa and Namasagali Sub-counties, Kamuli District |
| Number of Beneficiaries: | Namasagali and Kitayunjwa sub-counties in Kamuli District with a population of about 73,306 people with over 18,190 households and 133 administrative units/ LCs (villages). |
| Area details | https://kamuli.go.ug/ |
| Proposed Program Dates: | July, 2021 – July 2022. |
| Point of contact | Mugweri Yoweri Chairperson |
| E-Mail Address: | goodshepherdcomdevass@gmail.com yowerimugweri@gmail.com |
| Address: | P.O BOX 88 KAMULI, Buyobo Budhatemwa, Kamuli-Jinja Rd Kamuli District Uganda |
| Phone Number: | +256782908205 +256703643875 |

## Project Summary

The project being proposed aims to address livelihood needs for income generation, fuel wood, timber, fruit, fodder and other non-timber forest products  while halting and reversing the trend of the forest loss and related environmental degradation through promoting vegetable and fruit tree growing and agro-forestry systems. Despite their potential as a food security, poverty alleviation, environmental/energy conservation and sustainable livelihoods strategy trees and forests being a critical resource for people’s livelihoods, environmental conservation and national economic development, tree and forest resources have significantly diminished in recent years due to an increase in the number of people depending on them for survival as well as a lack of alternatives.

The long-term goal of the project is to contribute to the eradication of poverty, energy poverty, food insecurity and fostering a lasting high quality of life for the locals while safeguarding long-term environmental sustainability by growing fruit and multi-purpose trees and promoting agroforestry systems.

Our vision is: “planting trees for healthier populations and better environment”.

The medium-term development goal of the project is to enhance the ability to increase and sustain agricultural production for improved food security, nutrition and income generation while at the same time safeguarding the environment by adopting sustainable agricultural practices and appropriate technologies and at the same time ending energy poverty in our area through fostering increased fruit tree and tree planting production for enhanced food self-sufficiency and increased income generation for the school and enhancing the ability to conserve and protect the environment.

## Problem statement

Trees are the most important part of the ecosystem which helps in balancing the climate and the environment. A forest comprises of trees and plants helps to reverse the global warming which adversely maintain the health of the earth.

Global warming is the biggest problem facing planet earth and mankind nowadays which adversely affects our earth and results of the same are observed these days are: Increase in level of the sea, Temperature increase, Fog, Climate change, melting of glaciers.

The other effects of De-Forestation are: Soil erosion destruction, Water cycle, Loss of biodiversity, Climate of change.

Benefits of Trees and Forest on Earth:

- It helps in sustain all life and living organisms on earth.

- It helps in producing clean water.

- It helps in naturally filter air.

## Advantages of planting trees in reducing global warming

- An average size tree creates sufficient oxygen in one year to provide oxygen for a family of four.

- Planting trees can cut electricity costs up to 50 percent.

- Planting trees for the environment is good as they are renewable, biodegradable and recyclable.

- If we plant 900,000 million trees, the earth will get with 13 million more tons of oxygen.

- Once acre of trees can remove up to 2.6 tons of Carbon Dioxide each year.

- During photosynthesis, trees and other plants absorb carbon dioxide and give off oxygen.

- Trees keep in cheek the air and water pollution.

- Why planting trees is important is evident as they are the natural habitat of the animals and birds, as well as many endangered species.

- Planting trees means more wood and paper products which can be easily recycled.

- A newly planted whole forest can change tones of atmospheric carbon into wood and other fibrous tissue, thus reducing global warming.

## Why intervene for the two sub counties?

Namasagali and Kitayunjwa sub-counties are one of the sub-counties in Kamuli District. The sub-counties have 12 parishes with a population of about 73,306 people with over 18,190 households and 133 administrative units/ LCs (villages).

The sub-counties also have 29 government primary and 1 government secondary school and 88 private schools all of which do prepare food/ porridge for the learners. More than half of the households and all the learning institutions use fire wood and charcoal to prepare their food/porridge under the traditional unsafe stoves as they release open fire flames and harmful smoke to the housewives and the kitchen staffs at the institutions. In Namasagali and Kitayunjwa sub-counties, the children are manipulated by the charcoal and sugar cane dealers who employ them at cheaper rates that are unacceptable to the adults. These children have abandon schools for cheap labour where they face risks of being transported on the top of the charcoal trucks, fire burns, and alcohol and drug abuse.

Their economic activity in the sub-counties is based on deforestation / cutting of trees for charcoal for sell to the traders from different parts of the country. Kamuli district and in particular Namasagali sub-counties are well known as charcoal producing area. In addition, Kamuli District received the sugar factory at Kiroba village, which also causes deforestation because of growing of sugar cane. The youths also have abandoned agriculture sector leaving it to the women and elderly searching for jobs in town and cutting trees for charcoal causing environmental degradation in the area. Rain fall seasons have changed due to deforestation in the sub-counties and the whole district and region at large. The area experiences long drought which lead to a semi desert and food insecurity every year. This raises the poverty amongst the community rendering them unable to access the basic necessities of life. Having identified all this, GSCDA resolved to implement this project to address the above problems.

## Justification

Over the last few years, the forest cover in Kamuli district has significantly reduced. Accordingly, the local people reported that many parts of the district had extensive forest and tree cover but now most of it is gone. This has resulted in loss of biodiversity (including medicinal plants and wild animals) and severe land degradation due to soil erosion and loss of fertility. The local people note that many areas which used to be very fertile are now barren and the overall agricultural productivity in the area has declined dramatically which is pushing people deeper into poverty. Moreover, pressure on the remaining forests and trees is high as the proportion of people depending up on them for firewood and non-timber products is quite high.

Despite its potential contribution to the food security, nutrition and income for the rural population in Kamuli, fruit growing is a relatively low-key economic activity.

There is a need to sensitize, empower and assist the rural farmers to increase agricultural productivity and address potential environmental risks of associated to tree destruction and poor unsustainable small subsistence agricultural practices. This project will assist farmers to address some of the above-mentioned constraints and other emerging issues and needs so that people in the project area can derive maximum benefit from fruit growing and agroforestry practices as a strategy for improved food security, energy poverty eradication, poverty alleviation and sustainable livelihoods. It will encourage and support the locals to transform the current smallholder subsistence farming into economically viable agro-businesses.

The project will facilitate access to improved seeds; promote the adoption of modern agricultural technologies by  farmers; provide training in appropriate sustainable farming practices (including: soil and water conservation, integrated fertility management, composting, crop rotation, mulching, intercropping/use of cover crops, sylvopastoral systems and integrated pest management); facilitate the establishment of farmer producer-groups and foster competitive marketing of locally produced fruit products, including through training in harvest and post-harvest handling and quality control skills.

## Proposed execution of the project

GSCDA plans to build 90 Safe Forest Saving Stoves in rural communities of Namasagali and Kitayunjwa sub-counties in Kamuli District. This project will provide information on raising awareness on the need for conserving and preserving the biodiversity in the Namasagali and Kitayunjwa sub-counties. The proposal focuses on supporting the protection of the Namasagali and Kitayunjwa sub-counties in Kamuli District which includes:

- Tree planting at households, institutions and along the main community roads and river banks.

- Awareness raising workshops.

- Building 90 demonstration Safe forest saving stoves in rural communities of the two Sub Counties. Further suggestions pertain to create a community forest and extend the support to protection of other sub-counties in Kamuli district.

- To establish nursery beds for Acacia trees and fruits like oranges, mangoes, cocoa etc.

# ORGANIZATIONAL BACKGROUND.

## Legal and membership structure

Good Shepherd Community Development Association (GSCDA) established in 2014 GSCDA operates in Busoga region and is planning to expand its activities to seven districts in Rwenzori and Buganda Regions. It has a total of over 300 Women, Youth, PWDs, Elder farming groups with an average of 5-30 members per group. GSCDA has a membership of 205 farmer groups that constitutes to about 11,030 individual farmers of which ¾ are women.

## Mission

GSCDA’S Mission is to promote an empowered community socially, educationally, and economically through unity and hardworking and to give basic adult and youth education learning and empower the resource poor farming communities of both women and men through trainings, advocacy and access to better markets and its clear vision is a literate, productive and harmonious community of Youth, women and men meeting their basic needs and rights with ease, PWDs inclusive.

Our purpose is to empower the rural communities through training, advocating, and protection of the environment, human rights, agricultural development, health and other cross cutting issues for humanities.  Our target population is to help and empower the indigenous people of Men, women, youth, and elderly including the vulnerable or PWDs.

## Management

GSCDA has a General Assembly which is the top policy making organ and a Management Board which is the highest administration organ that oversees the smooth implementation of all programs. The secretariat comprises of a technical team that implements all the approved programs of the association which is headed by the programmes coordinator. The other staffs include the project coordinators, administrative secretary, Accountant and field officers.

## Staff

GSCDA has ten (10) staffs of which 5 are full time paid up that include the programmes coordinator, Accountant, 2 Field Officers and administrator.  The rest are volunteers who are facilitated as per their assignments/ tasks.

## PROJECT OBJECTIVES AND EXPECTED RESULTS

## Project Objectives

- To reduce wood consumption, air pollution and charcoal smoke and avoid harmful health through construction of 90 demonstration fuel saving stoves so as to allow recovery of forests and mangroves.

- To contribute towards afforestation, protect and reduce soil erosion by facilitating the planting of 900,000 trees in Namasagali and Kitayunjwa sub-counties.

- To promote the economic empowerment of women and youth groups by including them in the project activities through establishment of nursery beds and construction of Safe Forest Saving Stoves.

- To assist particularly from  poor and disadvantaged families, to engage in fruit and tree growing and increase vegetable crop production for improved food security and income generation for the school thus enabling the school to  meet the costs of other educational needs such as money for tests ,Lunch for both pupils and teachers, among others.

- To promote awareness of the value and importance of planting trees(including fruit tree and tree lots) for different purposes; how to raise and tend tree seedlings and ways of integrating trees into farming systems through the production and dissemination of public awareness materials.

- To enhance capacity of farming households in surrounding areas to apply appropriate technologies and sustainable farming practices (including: composting, soil and water conservation, integrated pest management, environmentally sustainable application of agrochemicals, etc.) through awareness and training workshops, information dissemination and extension services.

- To mobilize and assist the project beneficiaries to organize themselves into Farmers’ groups and a Community Association to manage and sustain the activities initiated under the project and take advantage of the economies of scale in purchase of farm inputs; processing, transportation and marketing of agricultural produce; increase their market share and facilitate better access to credit and other financial services.

- Facilitate access to improved seeds and seedlings including fruit tree seedlings.

- Facilitate access to agricultural inputs (including fertilizers, pesticides and farm tools);

- Promote the adoption of modern agricultural technologies.

- Organize workshops and other training activities (farm visits, study tours and dissemination of information and technical training materials) on appropriate sustainable farming practices, including: soil and water conservation, integrated fertility management, composting, sylvopastoral systems and integrated pest management);

- Offer on-farm extension support and advisory services, upon request;

- Train, equip and deploy local agricultural extension workers/ animators (change agents);

- Foster competitive marketing of locally produced agricultural products (including through training in harvest and post-harvest handling and quality control skills and technologies);

- Facilitate young farmers’ access to relevant information, including market prices and credit opportunities.

- Facilitate the establishment of young farmer producers and marketing groups.

# Expected Results

- Through sensitization about environmental conservation, the communities shall increase support and participation in the project.

- 75% of the population in Namasagali and Kitayunjwa sub-counties shall desist from deforestation.

- 90 demonstrations safe forest saving stoves shall be built at the sub-counties and at least 10,000 households shall each have one.

- The rate of air pollution from wood smoke and fire risks shall be reduced resulting into better health condition in the sub-county.

- There shall be increased participation in tree planning activities by the community members.

- There shall be positive green environmental change that is suitable for human and animal habitation in Namasagali and Kitayunjwa Sub-counties.

- Soil fertility shall be restored resulting into high production of crops and food security in the sub-counties.

- The project shall create employment opportunities to the communities specially the women and youth by establishing tree nursery beds and construction of forest saving stoves at subsidized rates within the Sub Counties and neighbouring areas.

- There shall be working environmental protection committees (EPC) that will also comprise of women and youth at village, parish and sub-county level.

## Project Sustainability

The youth and women groups shall be supported to continue with the project by establishing tree nursery beds for sale to communities at subsidized rates. They shall also continue constructing of safe forest saving stoves for communities after the end of the project period. GSCDA shall also ensure that this project is incorporated in the district’s work plan and budget. All these shall contribute to project’s sustainability.

# PROJECT BUDGET

### Project Funding Summary

| Funding source | Funding plan, ( Ug shs) |  | Total ( Ug shs) | Total(US$) |
| --- | --- | --- | --- | --- |
|  | Years 1 | Year 2 |  |  |
| A. Grant | 75,111,000 | 28,513,000 | 103,624,000 | 25,906 |
| B. Community | 5,342,000 | 2,289,000 | 7,632,000 | 1,908 |
| C.Proposing Organization | 25,920,000 | 18,200,000 | 44,120,000 | 11,030 |
| Total project cost | 106,373,000 | 49,002,000 | 155,375,000 | 38,844 |

### Community Contribution

| Sources of community contribution | Type( cash/ in kinds) | Projected | Value in Ug shs |
| --- | --- | --- | --- |
| Soil for construction of SFSS @ 180,000 X 9 X 2 | 3,240,000 | Projected | 3,240,000 |
| Water @ 10.000 X45 X 2 | 900,000 | Projected | 900,000 |
| Paspalm@20,000X45 X 2 | 1,800,000 | Projected | 1,800,000 |
| Banana stem @ 5000 X 45 X 2 | 450,000 | Projected | 450,000 |
| Pagers @ 10,000 X 18 X 2 | 360,000 | Projected | 360,000 |
| Hoes @ 12,000 X 18 X 2 | 432,000 | Projected | 432,000 |
| Jerry cans @ 45 X 5000 X 2 | 450,000 | Projected | 450,000 |
| Total 7,632,000 Projected |  |  | 7,632,000 |

### Proposing organization’s contributions

| Sources of community contribution | Type ( cash) | Committed | Value in Ug shs |
| --- | --- | --- | --- |
| Staff salary (5) | 36,000,000 | Committed | 36,000,000 |
| Rent | 6,000,000 | Committed | 6,000,000 |
| Power and water bills | 2,120,000 | Committed | 2,120,000 |
| Total 44,120,000 committed |  |  | 44,120,000 |

## Projected Expenditures

### Projected expenditures

| Expenditure categories | Year 1 Ug shs |  | Year 2 Ug shs | Total Ug shs |  |  |  | Us $ |  |  |  |  |  |  |  | % total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sensitization of sub county leaders 45 people |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mobilization | 60,000 |  |  | 60,000 |  |  |  |  | 15 |  |  |  |  |  |  |  |  |
| Stationary | 180,000 |  |  | 180,000 |  |  |  |  | 45 |  |  |  |  |  |  |  |  |
| Facilitators’ allowance | 252,000 |  |  | 252,000 |  |  |  |  | 63 |  |  |  |  |  |  |  |  |
| Refreshments | 168,000 |  |  | 168,000 |  |  |  |  | 42 |  |  |  |  |  |  |  |  |
| Participants transport refund for 45 people | 820,000 |  |  | 820,000 |  |  |  |  | 205 |  |  |  |  |  |  |  |  |
| Sub total | 1,480,000 |  |  | 1,480,000 |  |  |  |  | 370 |  |  |  |  |  |  |  |  |
| Sensitization of parish leaders about the project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mobilization | 60,000 |  |  | 60,000 |  |  |  |  |  | 15 |  |  |  |  |  |  |  |
| Stationary | 2,100,000 |  |  | 2,100,000 |  |  |  |  |  | 525 |  |  |  |  |  |  |  |
| Facilitators’ allowance 3pple x 9 x 200,000 | 5,400,000 |  |  | 5,400,000 |  |  |  |  |  | 1,350 |  |  |  |  |  |  |  |
| Transport refund for 630 x 10,000 | 6,300,000 |  |  | 6,300,000 |  |  |  |  |  | 1,575 |  |  |  |  |  |  |  |
| Meals for 630 people @ 5000 | 3,152,000 |  |  | 3,152,000 |  |  |  |  |  | 788 |  |  |  |  |  |  |  |
| Sub total | 17,012,000 |  |  | 17,012,000 |  |  |  |  |  | 4,253 |  |  |  |  |  |  |  |
| Project launching |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Public address system | 252,000 |  |  |  | 252,000 |  |  |  |  | 63 |  |  |  |  |  |  |  |
| Hire of tents and chairs | 1,000,000 |  |  |  | 1,000,000 |  |  |  |  | 250 |  |  |  |  |  |  |  |
| Refreshments 630 X 2 people | 1,260,000 |  |  |  | 1,260,000 |  |  |  |  | 315 |  |  |  |  |  |  |  |
| Music dance and drama | 500,000 |  |  |  | 500,000 |  |  |  |  | 125 |  |  |  |  |  |  |  |
| Mass media | 300,000 |  |  |  | 300,000 |  |  |  |  | 75 |  |  |  |  |  |  |  |
| Transport for staffs and stuff | 1,544,000 |  |  |  | 1,544,000 |  |  |  |  | 386 |  |  |  |  |  |  |  |
| Honouring | 500,000 |  |  |  | 500,000 |  |  |  |  | 125 |  |  |  |  |  |  |  |
| Sub total | 5,356,000 |  |  |  | 5,356,000 |  |  |  |  | 1,339 |  |  |  |  |  |  |  |
| Formation of environmental protection committees (EPCs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Nomination of EPCs at all levels | 340,000 |  |  |  |  | 340,000 |  |  |  |  | 85 |  |  |  |  |  |  |
| Training of MDD group on project theme | 608,000 |  |  |  |  | 608,000 |  |  |  |  | 152 |  |  |  |  |  |  |
| Posters @ 1,500 x 1,000 | 1,820,000 |  |  |  |  | 1,820,000 |  |  |  |  | 455 |  |  |  |  |  |  |
| Quarterly Radio talk show@ 727,500 | 2,910,000 |  | 2,910,000 |  |  | 5,820,000 |  |  |  |  | 1,455 |  |  |  |  |  |  |
| Sub total | 5,678,000 |  | 2,910,000 |  |  | 8,588,000 |  |  |  |  | 2,147 |  |  |  |  |  |  |
| Construction of Safe Forest Saving Stoves |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Mobilization | 220,000 |  |  |  | 220,000 |  |  |  |  | 55 |  |  |  |  |  |  |  |
| Facilitators allowances of 4 staff x 2 days x 125,000 per day | 1,000,000 |  |  |  | 1,000,000 |  |  |  |  | 250 |  |  |  |  |  |  |  |
| 2 trips of bricks @ 300,000 | 600,000 |  |  |  | 600,000 |  |  |  |  | 150 |  |  |  |  |  |  |  |
| Soil for construction of SFSS @ 80,000 X 9 | 900,000 |  |  |  | 900,000 |  |  |  |  | 225 |  |  |  |  |  |  |  |
| Pipes @ 35,000 X 45 | 1,576,000 |  |  |  | 1,576,000 |  |  |  |  | 394 |  |  |  |  |  |  |  |
| Water @ 6300 X 45 | 284,000 |  |  |  | 284,000 |  |  |  |  | 71 |  |  |  |  |  |  |  |
| Paspalm @ 20,000 X 45 | 900,000 |  |  |  | 900,000 |  |  |  |  | 225 |  |  |  |  |  |  |  |
| Banana stems @ 5000 X 45 | 225,000 |  |  |  | 225,000 |  |  |  |  | 56 |  |  |  |  |  |  |  |
| Pangs @ 10,000 X 18 | 180,000 |  |  |  | 180,000 |  |  |  |  | 45 |  |  |  |  |  |  |  |
| Hoes @ 12,000 X 18 | 216,000 |  |  |  | 216,000 |  |  |  |  | 54 |  |  |  |  |  |  |  |
| Jerry cans @ 45 X 6000 | 270,000 |  |  |  | 270,000 |  |  |  |  | 68 |  |  |  |  |  |  |  |
| Sub total | 6,371,000 |  |  |  | 6,371,000 |  |  |  |  | 1,593 |  |  |  |  |  |  |  |
| To contribute towards afforestation by planting 900,000 trees in two sub-counties |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 20kgs of Acacia seeds ( trees) @ 30,000 | 600,000 |  |  |  | 600,000 |  |  |  |  |  |  | 150 |  |  |  |  |  |
| 180kg of polythene bag 10,000= per @ | 1,800,000 |  |  |  | 1,800,000 |  |  |  |  |  |  | 450 |  |  |  |  |  |
| Imported soil for nursery bed 9 trips @ 100,000 | 900,000 |  |  |  | 900,000 |  |  |  |  |  |  | 225 |  |  |  |  |  |
| 9 trips Manure at 70,000 | 632,000 |  |  |  | 632,000 |  |  |  |  |  |  | 158 |  |  |  |  |  |
| 18 watering cans @ 25,000 per each | 452,000 |  |  |  | 452,000 |  |  |  |  |  |  | 113 |  |  |  |  |  |
| 18 wheel barrows @ 150,000 per each | 2,700,000 |  |  |  | 2,700,000 |  |  |  |  |  |  | 675 |  |  |  |  |  |
| 18 spades @ 30,000 per each | 540,000 |  |  |  | 540,000 |  |  |  |  |  |  | 135 |  |  |  |  |  |
| 9 Plastic water tanks of 220 litters at 120,000 per each. | 1,080,000 |  |  |  | 1,080,000 |  |  |  |  |  |  | 270 |  |  |  |  |  |
| 9 glass shed nets at 800,000 per each | 7,200,000 |  |  |  | 7,200,000 |  |  |  |  |  |  | 1,800 |  |  |  |  |  |
| 120 poles @ 10,000 | 1,200,000 |  |  |  | 1,200,000 |  |  |  |  |  |  | 300 |  |  |  |  |  |
| 350 rafters @ 6,000 | 2,100,000 |  |  |  | 2,100,000 |  |  |  |  |  |  | 525 |  |  |  |  |  |
| 18 Rake @ 15,000 | 272,000 |  |  |  | 272,000 |  |  |  |  |  |  | 68 |  |  |  |  |  |
| Pricking @ 20= per each | 1,800,000 |  |  |  | 1,800,000 |  |  |  |  |  |  | 450 |  |  |  |  |  |
| Potting @20 | 1,800,000 |  |  |  | 1,800,000 |  |  |  |  |  |  | 450 |  |  |  |  |  |
| Sorting | 600,000 |  |  |  | 600,000 |  |  |  |  |  |  | 150 |  |  |  |  |  |
| 9 nursery bed attendants @ 100,000 x 3m | 2,700,000 |  |  |  | 2,700,000 |  |  |  |  |  |  | 675 |  |  |  |  |  |
| Water | 500,000 |  |  |  | 500,000 |  |  |  |  |  |  | 125 |  |  |  |  |  |
| 9 pairs of gum boots | 180,000 |  |  |  | 180,000 |  |  |  |  |  |  | 45 |  |  |  |  |  |
| Sub total | 27,056,000 |  |  |  | 27,056,000 |  |  |  |  |  |  | 6,764 |  |  |  |  |  |
| To promote the economic empowerment of women and youth groups |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Trainings/workshops | 1,484,000 | 1,484,000 |  |  |  |  | 2,968,000 |  |  |  |  |  | 742 |  |  |  |  |
| Linkage of women and youth groups to development partners. | 360,000 |  |  |  |  |  | 360,000 |  |  |  |  |  | 90 |  |  |  |  |
| Disbursement of funds to women and youth groups ( 2 x 9 x 2,000,000) | 18,000,000 | 18,000,000 |  |  |  |  | 36,000,000 |  |  |  |  |  | 9000 |  |  |  |  |
| Sub-total | 19,844,000 | 19,484,000 |  |  |  |  | 39,328,000 |  |  |  |  |  | 9832 |  |  |  |  |
| Administration costs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Staff salary (5) | 18,000,000 | 18,000,000 |  |  |  |  | 36,000,000 |  |  |  |  |  | 9,000 |  |  |  |  |
| Rent | 3,000,000 | 3,000,000 |  |  |  |  | 6,000,000 |  |  |  |  |  | 1,500 |  |  |  |  |
| Power and water bills | 1,060,000 | 1,060,000 |  |  |  |  | 2,120,000 |  |  |  |  |  | 530 |  |  |  |  |
| Monitoring and evaluation | 1,516,000 | 1,516,000 |  |  |  |  | 3,032,000 |  |  |  |  |  | 758 |  |  |  |  |
| Audit fees |  | 3,032,000 |  |  |  |  | 3,032,000 |  |  |  |  |  | 758 |  |  |  |  |
| Sub-total | 23,576,000 | 26,608,000 |  |  |  |  | 50,184,000 |  |  |  |  |  | 12,546 |  |  |  |  |
| Grand Total | 106,373,000 | 49,002,000 |  |  |  |  | 155,375,000 |  |  |  |  |  | 38,844 |  |  |  |  |