## Proposed QMS Implementn Budget
KENYA COFFEE PRODUCERS ASSOCIATION
PROPOSED BUDGET FOR IMPLEMENTING QMS IN TENDELYANI SOCIETY
SOCIETY | NUMBER OF FARMERS | PROPOSED NO. OF LFs | PERMANENT STAFF | COMMITTEE MEMBERS | NUMBER OF WET MILLS
TENDELYANI | 899 | 22.475 | 9 | 9 | 1
EURO= Ksh 110
Details | Unit | Cost/unit (ksh) | No | Total (ksh)
TYPE OF COST
ADMINISTRATIVE COSTS
1 extension officer | month | 60000 | 12 | 720000
1 project Coordinator | month | 100000 | 12 | 1200000
Computer materials | PC/laptop | 80000 | 3 | 240000
Sub Total ksh |  |  |  | 2160000
TRAINING COSTS
Sensitisation seminars | wet mill | 15000 | 1 | 15000
Data collection by LFs | day | 250 | 112.375 | 28093.75
358 Lead farmers(LFs) training ( GAPS & Certification) | training day | 600 | 134.85 | 80910
358 LFs training on climate change | training day | 600 | 67.425 | 40455
Soil sampling+leaf analysis | sample | 1200 | 44.95 | 53940
Training for Quality Team ( GAPs, QMS & Certification) | training day | 2000 | 54 | 108000
Training for wet mill managers ( Coffee processing & Cerftification) | training day | 2000 | 3 | 6000
Review meetings at wet mills | review meeting | 20000 | 9 | 180000
10 field days | field day | 30000 | 10 | 300000
Training on coffee and tree nursery | training day | 2000 | 1 | 2000
Training for management committee | training day | 3000 | 27 | 81000
Training in word+excel for Coop | person | 5000 | 1 | 5000
Farmer training materials | farmer poster | 50 | 899 | 44950
2 motorbikes | bike | 150000 | 2 | 300000
Transport costs project manager- milleage | month | 100000 | 36 | 3600000
Transport costs 2 motorbike | month | 300 | 1728 | 518400
Sub Total ksh |  |  |  | 5363748.75
CERTIFICATION AND OTHER TRAINING COSTS
Certification costs | wet mill | 100000 | 2 | 200000
Self assessment costs | Day | 300 | 134.85 | 40455
NEMA audit and reports | wet mill | 60000 | 1 | 60000
Energy audit and reports | wet mill | 80000 | 1 | 80000
Computer materials | PC/printer | 50000 | 1 | 50000
Document & records Control system | wet mill | 80000 | 1 | 80000
Wet mill improvement to meet OHS Standards | wet mill | 200000 | 1 | 200000
Internal auditor training ( QMS & Certification) | training day | 15000 | 2 | 30000
Training on Occupational Health and safety | training day | 4000 | 18 | 72000
Training on First Aid, HIV ,fire safety etc | training day | 5000 | 9 | 45000
Sub Total ksh |  |  |  | 857455
COOPERATIVE EQUIPMENT COSTS
Tool kit Lead farmers & spray team | Lead farmer kit | 3000 | 201.475 | 604425
Moisture meters | moisture meter | 80000 | 1 | 80000
Coffee and tree nursery | wet mill | 100000 | 5 | 500000
Sub Total ksh |  |  |  | 1184425
CONSULTANCY COSTS | society | 1000000 | 1 | 1000000
Project Cost -Tendelyani |  |  |  | 8405628.75
TOTAL PROJECT COST IN EURO |  |  |  | 76414.8068

## imlementation plan
KCPA
KCPA COFFEE IMPROVEMENT PROJECT
QMS Implementation Timetable
Legend
KCPA & Trainers
KCPA Team & Coops/ Farmer Teams
Months | May-Aug 2013 | Sept-Dec 2013 | Jan-April 2014 | May-Aug 2014 | Sept-Dec 2014 | Jan-April 2015 | May-Aug 2015 | Sept-Dec 2015 | Jan-April 2016
Activities
Holding of sensitisation meetings for farmers
Elect Lead farmers
Due Diligence on elected PF’s farms
Establish members of the quality team( project management team) at Coop level
Data collection by Lead farmers
Coffee production training for KCPA Staff ( 1 week training at CRF)
Induction training for Lead farmers- Coffee chain, GAPs, Calendar of activities, record keeping, gender standards – 1 day workshop
Training of Lead farmers on GAPs (pruning, coffee nutrition crop protection, soil management, coffee picking and processing)- 2 day workshop
Soil analysis for Lead farmers
Selection of demonstration plots
Training on good coop management for Management Committee/ supervisory
Training of Lead farmers on climate change adaptation and mitigation- 2 day workshop
Risk and opportunity analysis - 2 day workshop
Training on coffee processing for factory managers/ factory workers
Training on coffee and tree nursery management
Training of Lead farmers on sustainable agricultural land management practices(SALMs)- 2 day workshop
Training of the quality management teams
Zonal training of farmers by Lead farmers
Quarterly trainings for Lead farmers
Quarterly reviews of project plan/ activities
Completion of quality plans for wet mills
Training of KCPA staff on certification Standards
Training Lead farmers on the use of GAPs to make farmers more resilient to climate change- 2 day workshop
Training Lead farmers and spray operators(team) on pesticide application and safe use.
Farmers field days ( 1 per wet mill)
Exposure visit to certified Coops by Lead farmers and quality teams
Computer application training at Coop and wet mills ( Staff and Management)
NEMA Audit for Wet Mills
Training on social and environmental standards – quality teams and staff-Occupational health and safety, fire fighting, first aid , CBA and Gender standards etc
Survey of wet mills / dry mill to assess status, capacity and constraints
Application for certification
Capacity building for Coops , Wet Mills , Dry mills- Computers, fire equipments, first aid kits, sample drying tables, moisture meters, cupping labs
Completion of the Quality Management System/Internal Control System
Self assessment before verification
Verifications
Data collection by Lead farmers

## BUDGET NOTES
KENYA COFFEE PRODUCERS ASSOCIATION
PROPOSED BUDGET FOR IMPLEMENTING QMS IN TENDELYANI SOCIETY
SOCIETY | NUMBER OF FARMERS | NUMBER OF WET MILLS
TENDELYANI | 899 | 1
EURO= Ksh 110
Details | Unit | NOTES
TYPE OF COST
ADMINISTRATIVE COSTS
1 extension officer | month | one officer at ksh 60,000*36 months*2
1 project Coordinator | month | one officer at ksh 100,000*36 months
Computer materials | PC/laptop | 3 comps @ksh 80,000
Sub Total ksh
TRAINING COSTS
Sensitisation seminars | wet mill | ksh 15,000 refreshments one per wet mill
Data collection by LFs | day | 358 Lfsworking 5 days@ksh 250
358 Lead farmers(LFs) training ( GAPS & Certification) | training day | two trainings per year for three years
358 LFs training on climate change | training day | 1 training per year for 3 years
Soil sampling+leaf analysis | sample | 358 samples*2 years
Training for Quality Team ( GAPs, QMS & Certification) | training day | 2 trainings per year*3 years
Training for wet mill managers ( Coffee processing & Cerftification) | training day | 1 training per year*3 years
Review meetings at wet mills | review meeting | 5 coop reviews* 3per year* 3 years
10 field days | field day | 2 reviews per coop per year*3 years
Training on coffee and tree nursery | training day | 1 training for wet mill managers
Training for management committee | training day | 1 training per year for 3 years
Training in word+excel for Coop | person | 1 training of cherry clerks in 17 wet mills
Farmer training materials | farmer poster | 1 training poster per farmer for all farmers
2 motorbikes | bike | cost of two bikes@ ksh 150,000
Transport costs project manager- milleage | month | transport cost per month*3 years
Transport costs 2 motorbike | month | fuel cost plus meinteinance* 24 days *2 bikes*36
Sub Total ksh
CERTIFICATION AND OTHER TRAINING COSTS
Certification costs | wet mill | ksh 100000 per wet mill*17* 2 years external audit cost
Self assessment costs | Day | 358 LF@300* 2 audits in 3 years
NEMA audit and reports | wet mill | Internal EIA*17 wet mills
Computer materials | PC/printer | 1 desk top*17 wet mills
Document & records Control system | wet mill | 1 Document software module
Wet mill improvement to meet OHS Standards | wet mill | ksh 200 per wet mill* 1year
Internal auditor training ( QMS & Certification) | training day | 17 auditors *2 trainings in 3 years
Training on Occupational Health and safety | training day | 2 trainings *45 staff
Training on First Aid, HIV ,fire safety etc | training day | 1 training 45 staff
Sub Total ksh
COOPERATIVE EQUIPMENT COSTS
Tool kit Lead farmers & spray team | Lead farmer kit | prining saw, shears,Gum boots, hat and dust coat
Moisture meters | moisture meter | 1 meter per wet mill
Coffee and tree nursery | wet mill | 1 nursery per coop@ ksh 100,000
Sub Total ksh
TOTAL BUDGET KSH
TOTAL EURO