Project concept note for funds from HELVETAS

Project title: Multimedia Library

Focal Area for which funding requested (Tick)

Sustainable and equitable socio-economic development

Conservation of the environment

Preservation and promotion of culture

Promotion of good governance

Others (Support to Youth and promote media industry)

Amount funding sought:

| Total funds requested from HELVETAS (UDS) | Co-financing from other sources (USD) | Total funds required for the Project (USD) |
| --- | --- | --- |
| 76,987 | 0 | 76,986.01 |

Grant period:  Year 2014   to Year 2016

Starting date: 1st Jan 2014

Applicant Details

Name of CSO:  Youth Media Centre

Mailing Address: P.O Box 311, Thimphu

Telephone: 340753     Fax: 323705     Email: ymcbhutan@gmail.com       Website: www.youthmediacenter.org

Head of CSO (Name and position):	Pemaa Dorji, Executive Director				 Project Contact (Name and position): Barun Gurung 								          Phone(Mobile): +975 17582052

Phone(Fixed): +975-2-340753

Fax: +975-2-323705

Email: gurung.varun506@gmail.com

Multimedia Library – Concept Note

Having just established its formal education system in 1950s, Bhutan is continuously striving to build a knowledge-based society and develop expertise in order to compete in the international market. In spite of such efforts, national issues such as poverty, unemployment, and economic crises are on the rise, and several potentially lucrative fields remain underdeveloped. The field of multimedia is one area that has become important for communication, education, health, research, social services, business, environment, media and entertainment, but is limited by a lack of skills, knowledge and professionalism.  This limitation exists mainly because of inaccessibility of resources, trainings, coaching, and workshops to serve as a platform to learn about multimedia. Seeing the multimedia industry as one of the most promising industries that could generate employment and revenues in Bhutan, the Youth Media Center (YMC) is proposing to establish a Multimedia Library (ML) to provide resources and educational programs for the general public. The core objective of launching the ML is to support people in creating multimedia products that can meet the international standards by enhancing their skills and knowledge through education.

The need of a ML is further highlighted by the results of a needs assessment survey of 28 Bhutanese youth. 93% of the respondents believe that Bhutan is still amateur in the field of multimedia, and 100% of them support launching a multimedia library to educate the nation in creating a vibrant media society.

The ML will not only contain traditional books, newspapers, magazines and electronic resources covering a wide range of subjects, but also conduct activities like video recordings (movies and documentaries), sound recordings (music and audios), photography and all multimedia related activities. The ML will also conduct trainings, workshops and coaching, know-how programmes, and inspiring lectures in order to support new and innovative ideas. In addition, the ML will create archives on domestic multimedia institutional information.

By using the ML’s materials and attending its educational programs, ML users will become able to produce multimedia products that meet international standards. The heightened quality of products will create more employment opportunities and revenue, thus alleviating the unemployment and poverty issues currently facing Bhutan without having adverse affects on pristine natural environment. In addition, the ML will contribute to building a more vibrant media society in Bhutan.

LOGICAL FRAMEWORK

| Project description |  | Objectively verifiable indicators of Achievement | Source and means of Verification | Assumption and Risk |
| --- | --- | --- | --- | --- |
| Overall Objective | To support people in creating multimedia products that meet international standards | Number of products consumed internationally | Reports by ML users on products they have made that have been consumed internationally, which they attribute to their ML use | It may take years for quality products to be produced |
| Immediate objectives | 1. To enhance the skills and knowledge of ML users 2. To provide resources for ML users to use to create multimedia products | Number of multimedia resources contained in the ML (books, DVDs, and other educational materials); Number of people attending ML programs | Inventory of resources kept in the ML; feedback forms of users attending ML programs | Users may use the resources available but may not enhance their skills and knowledge or not create multimedia products |
| Output 1 | Skilled and high caliber multimedia employees and youths who are meeting international standards for professional multimedia products | Quality of multimedia products produced by ML users | ML will inventory products made by ML users sold in the international market | Products may meet domestic but not international standards |
| Activity 1 | Advertising trainings, workshops, knowhow programmes and coaching | Through television and print media | Media observation and office documentation | General public along with the youths are watching TV and print media advertisements |
| Activity 2 | Hiring of professionals / consultants for the programmes to be conducted at the ML | No. of professionals/ consultants hired | Agreement letter | May not find qualified professionals / consultants for the programmes |
| Activity 3 | Selection and registration of trainees | Number of trainees selected and registered | Reports and registration documents |  |
| Activity 4 | Giving inspiring lectures & know-how programs for ML users | Attendance of registered trainees for the programs | Attendance register of trainees for lectures and programs | All are interested in knowing more about multimedia. |
| Activity 5 | Providing trainings, workshops and coaching for ML users | Training design and schedule | Training Reports and Training Certificate, visit by donor agencies |  |
| Activity 6 | Interim training report submission | Date (report submitted to Donor Agencies) | Date (report received by Donor Agencies) |  |
| Activity 7 | Awarding of certificates | No. of trainees receiving certificate | Training report |  |
| Activity 8 | Submission of final report | Date (report submitted to Donor Agencies) | Date (report submitted to Donor Agencies) | Completion of training |
| Activity 9 | Creating TV programmes for multimedia education | No. of programmes broadcast | Media observation | General public along with the youths are watching the programmes |
| Output 2 | Institutional strengthening and capacity enhancement of ML | Teaching & learning facilities for the trainees | Report and physical verification through visits |  |
| Activity 1 | Procurement of electronic equipment (desktops, servers, DVDs, etc.) and necessary furniture | No. of equipment (electronic gadgets) | Bills and receipts |  |
| Activity 2 | Procuring and collecting the library resource materials (printed books, digital books, audio and audiovisual tutorial books and programs) and archiving the Multimedia resources (Photographs, films and videos, music and sounds, software packages, instruction packages, learning aids, tutorials, etc.) | No. of library resource materials procured and collected | Bills and receipts |  |
| Activity 3 | Creating international institutional linkage (with multimedia libraries, film industries, music industries, photo industries, etc.) | Names of institutes with whom the ML has corresponded | Agreement letters | Willing to help NGO through kinds or minimum cost |
| Activity 4 | Domestic institutional linkage to help design training courses and provide authentic and credible certificates | Names of institutes with whom the ML corresponded | Agreement letters | Willing to help NGO through kinds or minimum cost |
| Activity 5 | Archiving of domestic multimedia institutional information and other electronic resources | Updating the latest information | Records of information | Multimedia industries cooperate with the Multimedia Library |