- ANNEX VI

- INTERIM NARRATIVE REPORT

- Assessment of implementation of Action activities    (CHILDHOPE-ZAMBIA)

  - Activities and results

Please list all the activities implemented during the reporting period under each of these results areas

  - Please list activities that were planned and that you were not able to implement, explaining the reasons for these. Note that these should also be reported under the appropriate result areas below.

Result 1:  strengthened National Coordination for Inclusive Education in Zambia

Result 2: Blind and low vision children access quality education as close to their homes as possible.

Activity 1

- Coordination Meetings

Coordination meetings were held in Mazabuka, Monze, Choma and Kalomo Districts with 25 participants overall. The teams were oriented to ZIEP ideologies. More prominent among them been;

The overall objective of this Zambia Inclusive Education Programme action has been to contribute to Zambia’s realisation of “Education for All” Millennium Development Goal by 2015 targeting the blind and low vision children. The purpose of this action is to increase accessibility of quality education for blind and low vision children through strengthening of the capacity of the service providers to provide inclusive education as well as advocating for a system change in the provision of education in order to accommodate the needs of children with special needs:

Role and participation in the action of the various actors and stakeholders

- Sightsavers Zambia Country Office will be responsible for the overall management of the programme. It will provide the technical expertise, and play a major role in advocacy and management of the contract with the EC. Sightsavers will provide coordination of the project which will include planning and monitoring, administration of the funding, compilation of financial and programme reports.

- Ministry of Education through the Teacher Education and Standards Directorate will work to implement a national data base for monitoring education outcomes for blind and low vision children; whilst at District Education office will work closely with the special needs unit to ensure quality services in the districts.

- CHILDHOPE ZAMBIA – will be the implementing partner for Southern Province. CHILDHOPE using its experience in implementing ECCDE programmes in Southern province; will sensitise communities, mobilise them for action and deliver inclusive education programmes at community schools in six districts in Southern province. CHILDHOPE will report to Sightsavers Zambia Office

- Zambia Federation of Disability Organisations (ZAFOD) will be engaged to help sensitise parents of children with disabilities in all districts of the programme. ZAFOD officials will serve as role models to encourage community acceptance to allow their blind and low vision children to be enrolled in school.  ZAFOD will coordinate its work with CHILDHOPE and ZOCS and report to Sightsavers.

- Zambia Open Community Schools Zambia Open Community Schools (ZOCS) will be responsible for contacts to community schools in the various districts; will collaborate with CHILDHOPE for in-service teacher training, and will support the training of PCSCs. ZOCS will also help in coordinating Copper belt work and reporting.

District Coordinating teams were formed as follows:

| SN | NAME |  | STATION | POSITION | PHONE # |
| --- | --- | --- | --- | --- | --- |
| Mazabuka District |  |  |  |  |  |
| 1 | Hanguwa Tim | DEBS Office |  | DEBS | 0977824823 |
| 2 | Mubita Preston | Mazabuka Dist Hospital |  | DMO Eye Specialist | 0964007184 |
| 3 | Bonaventure Chipimo | CHILDHOPE Mazabuka |  | Dist Coordinator | 0977808604 |
| 4 | Chris Ntalasha | Community Development |  | A/ Comm Dev. Officer | 0967718136 |
| 5 | Kennedy Kauka | Mazabuka dist Hospital |  | Snr Physiotherapist | 0977768524 |
| 6 | Sikabanga Siatwiinda | DEBS Office |  | DESO | 0977891198 |
| 7 | Mufwinda Peter | DEBS Office |  | ESO- ODL | 0977527081 |
| Monze District |  |  |  |  |  |
| 1 | Chilema Peggy |  | DEBS Office | DEBS | 0965232206 |
| 2 | Mizinga Elvis |  | DEBS Office | ESO Special | 0979147093 |
| 3 | Mkandawire Mdaniso |  | DMO | Eye Specialist |  |
| 4 | Sarenje Oris |  | DEBS | District Planning Officer |  |
| 5 | Chipo Namwako |  | Monze Town Basic | Physically Challenged Teacher |  |
| Choma District |  |  |  |  |  |
| 1 | Mbilikita Jennifer |  | DEBS Office | ESO Special | 0977820523 |
| 2 | Rita Hatontola Duunka |  | Choma Dist Hospital | Eye Specialist | 0977312242 |
| 3 | Hanyanga John |  | St Mulumba Special Sch | Head Teacher | 0977410833 |
| 4 | Mubita I Rita |  | DEBS Office | DRCC | 0977809566 |
| 5 | Nakasamu Victor |  | Community Dev | DCDO | 0955839839 |
| 6 | Lesa Christabel Chanda |  | Dastra | Teacher | 0977224828 |
| Kalomo District |  |  |  |  |  |
| 1 | Mbilikita Jennifer |  | DEBS Office | ESO Special | 0977820523 |
| 2 | Hamilemba S K |  | DEBS Office | DRCC |  |
| 3 | Chanda Chisunka |  | Kalomo Dist Hospital | Physiotherapist | 0967466021 |
| 4 | Joseph Mambwe Sakala |  | Kalomo DMO | Planner | 0977835932 |
| 5 | Mutashala Joseph |  | Community Dev. Office | DCDO | 0966130765 |
| 6 | Mwanza Alick |  | Kalomo High School | Teacher | 0978367652 |
| 7 | Alisinda J C K |  | Kalomo High School | Head Teacher | 0955797531 |

Activity 2

- Sensitization of School Heads and Community Leaders

The sensitisation meetings were held with 75 educationists as listed below;

The meetings were designed to bring out the following outcomes:

- Participants oriented to the broader understanding of the Philosophy and rationale of Inclusive Education.

- Participants acquainted with the three year 2011-2013 Zambia Inclusive Education Programme and specifically the outcomes under Basic Education (GRZ &SSI/ EC) ;

- Participants understand their roles and responsibilities in the ZIEP project.

- Enhanced partner capacity to develop comprehensive networks for 2011 to 2013.

The key themes they were sensitised with include,

- What? Why? And How the ZIEP Programme 2011-2013 (Highlights)

- Philosophy and Rationale of Inclusive Education

- Early Childhood and Inclusion

- What Gets in the Way of an Inclusive Approach to Early Childhood Programming?

- What Are We Working Toward? Way forward

| Kalomo District Sensitisation Meeting |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| SN |  | NAME | STATION | POSITION | PHONE # |
| 1 |  | Mukwiza Bridget | Kalomo Basic | Ass/ DRCC | 0977620612 |
| 2 |  | Munsaka Collins | Goodhope Basic | SIC | 0977631852 |
| 3 |  | Matantilo George | Simakakata | Head | 0977406173 |
| 4 |  | Simaaya Collen | Nalubumba | D/Head | 0976007156 |
| 5 |  | Malumo Malumo | Choonga Basic | Head | 0955924849 |
| 6 |  | Haambokoma Beatrice | Kalomo Central | Head | 0977890234 |
| 7 |  | Muchanga Lady | Kalomo Basic | Head | 0977670806 |
| 8 |  | Kaluwe Joseph | DATF | Chairperson | 0977468209 |
| 9 |  | Mrs Katukula Getrude | Greenacres | S/Teacher | 0978544929 |
| 10 |  | Banda J. F. | Kalomo High | Teacher | 0977543435 |
| 11 |  | Mwanza A. | Kalomo High | Special .Educ. Teacher | 0978367652 |
| 12 |  | Alisinda J.C.K. | Kalomo High | Head | 0965848215 |
| 13 |  | Hamilemba S.K. | DEB- Office | DEBS |  |
| 14 |  | Mbilikita Jennifer | DEB- Office | ESO- Special |  |
| 15 |  | Mutashala Joseph | Community Dev. | DCDO | 0966130765 |
| 16 |  | Mbanachele Rhoda | Bwacha Basic | Head | 0977895220 |
| 17 |  | Chanda Chisunka | Kalomo Dist. Hospital | Physiotherapist | 0977466021 |
| 18 |  | Sakala Ernest | DATF/NAC | DACA |  |
| 19 |  | Sakala M. Joseph | Kalomo DMO | A/planner | 0977835932 |
| 20 |  | Sibongani Jonsen | K.D.T.R.Centre | Office orderly |  |
| Mazabuka District Sensitisation Meeting |  |  |  |  |  |
| SN |  | NAME | STATION | POSITION | PHONE # |
| 1 |  | Chris Ntalasha | Community Development | A/ Comm Dev. Officer | 0967718136 |
| 2 |  | Zulu Tomius | Nanga Special school | Head teacher | 0977820602 |
| 3 |  | Mabuku Malumbe | Mazabuka Special school | Class teacher | 0979536877 |
| 4 |  | Charles Chaaba | Dindi ECCD centre | Chairperson | 0976327944 |
| 5 |  | Kennedy Kauka | Mazabuka dist Hospital | Snr Physiotherapist | 0977768524 |
| 6 |  | Ndaliiba Steward | Chikankata Basic School | Act. Head Teacher | 0977575789 |
| 7 |  | Ndeleki Gift | Chikankata Basic School | Class Teacher | 0977633346 |
| 8 |  | Hambuli India | Simwaba ECCD Centre | Chairperson | 0978719889 |
| 9 |  | Mukoma Petronella | Mubuyu ECCD centre | Class Teacher | 0977232017 |
| 10 |  | Munkombwe Susan | Mubuyu community School | Head Teacher | 0977383277 |
| 11 |  | Sikabanga Siatwiinda | DEBS Office | DESO | 0977891198 |
| 12 |  | Mufwinda Peter | DEBS Office | ESO- ODL | 0977527081 |
| 13 |  | Akushanga Lungowe | Simwaba basic School | Head Teacher | 0977228284 |
| 14 |  | Choongo Margaret | MOH | CHW | 0966914937 |
| 15 |  | Choonya Jethro | Malala Basic School | Head Teacher | 0979206267 |
| 16 |  | Nchimunya Mwiinga | Malala community | ECCD Caregiver | 0978125771 |
| 17 |  | Moomba Roy | Mamulonga Basic School | Head Teacher | 0977828199 |
| Monze District Sensitisation Meeting |  |  |  |  |  |
| SN |  | NAME | STATION | POSITION | PHONE # |
| 1 |  | Alfred Mazuba | Choongo Special School | Village Headman | 0976845203 |
| 2 |  | Mwembe Eglinah | Choongo Special School | HEAD teacher | 0977372701 |
| 3 |  | Solomon Mazuba | Choongo Special School | Class Teacher (Deaf & Dumb |  |
| 4 |  | Clara Sibalwa | Broadview School | Class Teacher | 0977518564 |
| 5 |  | Nchobezyi Cletus | Broadview School | Head Teacher | 0979679146 |
| 6 |  | Mwiinga Ignitius | Manyaana Community Sch | Class Teacher | 0964580044 |
| 7 |  | Chipuya Washington | Manyaana Community Sch | ECCD Caregiver | 0968457149 |
| 8 |  | Chikubabe Phoster | Monze town School | Head Teacher | 0976748165 |
| 9 |  | Malambo Macha | Monze town School | Class Teacher | 0977782185 |
| 10 |  | Donard Musika | St Vincent de Paul | Class Teacher | 0979919419 |
| 11 |  | Sr Lontia Siakalambwa | St Vincent de Paul | Head Teacher | 0977410126 |
| 12 |  | Mambo Mweemba | Manungu Basic School | Head Teacher | 0977410666 |
| 13 |  | Mukwakwa Ronald | Manungu Basic School | Class Teacher | 0968664150 |
| 14 |  | Mukambala K Esther | Monze Basic School | Head Teacher | 0966599936 |
| 15 |  | Hangulu Shadreck | Monze Basic School | Class Teacher | 09771`14181 |
| 16 |  | Khumalo Fredrick M | Lwengu School | Class Teacher | 0977897238 |
| 17 |  | Chilema Peggy | DEBS Office | DEBS | 0965232206 |
| 18 |  | Mizinga Elvis | DEBS Office | ESO Special | 0979147093 |
| 19 |  | Kaumba Edith | DEBS Office |  | 0977348652 |
| Choma District Sensitisation Meeting |  |  |  |  |  |
| SN | NAME |  | STATION | POSITION | PHONE # |
| 1 | Iness Luchen Akabondo |  | Mwapona Community Sch |  | 0977891814 |
| 2 | Mary Mwape Mulenga D |  | St Patricks Basic School |  | 0977333148 |
| 3 | Priscilla Muyovwe Mwaandu |  | Adastra |  | 0977861584 |
| 4 | Hanyanga John |  | St Mulumba Special School | Head Teacher | 0977410833 |
| 5 | Rita Hatontola Duunka |  | Choma General Hospital | Eye specialist | 0977312242 |
| 6 | Patience Namakau Buumba |  | Choma General Hospital |  | 0966375703 |
| 7 | Lesa Christabel Chanda |  | Adastra |  | 0977224828 |
| 8 | Amanda Hachigabalala H |  | St Patricks Basic School |  | 0977312480 |
| 9 | Kingsley Londe |  | Shampande Basic School |  | 0977618473 |
| 10 | Cecilia Nakazwe Banda |  | Airport Community School |  | 0967240880 |
| 11 | Maaka Derick |  | Salvation Army Comm. Sch |  | 0979974946 |
| 12 | Mashamba Beatrice |  | Mwapona Community Sch |  | 0977497370 |
| 13 | Nakasamu Victor |  | District Admin Office |  | 0955839839 |
| 14 | Sikanyiti Saint M |  | DEBS Office |  | 0979628010 |
| 15 | Siachiwena Albert |  | Shampande Basic School |  | 0977820609 |
| 16 | Sydney L Muleya |  | Airport community School |  | 0977661405 |
| 17 | Mubita I Rita |  | DEBS Office | DRCC | 0977809566 |
| 18 | Mubanga N M |  | DEBS Office |  | 0977456893 |
| 19 | Mbilikita Jennifer S |  | DEBS Office | ESO Special | 0977820523 |

During the sensitisation the following were perceived as issues;

- Poverty levels of the communities

- General ignorance on the importance of inclusion of children with disabilities and their Rights

- Lack of infrastructure to accommodate children with disabilities

- Low literacy levels in the communities (among mothers)

- Lack of learning and teaching materials for people with disability in general and for children with Visual Impairment in particular

- Community always think that children with disability are a burden to them and their education is very expensive

- Mostly communities have a phenomenon that children who differently-abled do not learn from an early stage of life

- Lack of community structures that can help the promotion of Inclusive education at all levels

- Weakening extended family systems that can no longer provide extended care

- Cultural barriers on the roles of each of the family members especially on issues of Gender and equity and Child Rights and disability

The strategies that emerged from the sessions in reaction to challenges above included:

- Orientation of Community School Teachers to Inclusive education and technicalities of identifying, assessing and handling children with disability

- Need to improve school infrastructure to accommodate CSEN

- Sensitization of local communities on the underlying principle and magnitude of Inclusive Education and the Rights of people with disability, through PTAs, Church meetings, Social Clubs, Electronic Media (Local Radio Stations like Sky FM, Radio Mazabuka, Chikuni Radio etc) using the disabled as ambassadors.

- Encouragement of Parental involvement in all the programs that concern children with disabilities

- Sensitizing pupils on the need to accommodate friends who are disabled in schools.

- Strengthening the District Coordination committees by providing the teams with at least but not limited to the following:

- Desktop Computer for data computation

- Internet services for communication

- Motorbike for mobility

- Braille printing equipment for production of Braille Learning materials

- Coordination monthly petty cash for running around

RESULTS FROM THE INTERVENTION SO FAR

These teams were provided with terms of reference mostly in the overall coordination and spearheading of the implementation of the inclusive education programme. These teams were able to identify the following children with the support from local teachers. Mazabuka identified 14 children, Kalomo 55. Choma are yet to send updates soonest. Monze will only be able to send info on children’s status after they have done community sensitisation and comprehensive work on identification of children with visual impairment.

| # | District | Girls | Boys | Total | Type of Disability |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Low Vision | Blind | Deaf/ Dumb | Physically Challenged |
| 1 | Mazabuka | 4 | 10 | 14 | 11 | 3 | 1 | 1 |
| 2 | Monze | - | - | - | - | - | - | - |
| 3 | Choma |  |  |  |  |  |  |  |
| 4 | Kalomo |  |  | 55 | 50 | 5 | - | - |
|  | Total |  |  | 69 | 61 | 8 | - | - |

Mazabuka did indicate the names of children and their disability as follows;

| # | Name of Child | Sex | Age | Address | Status |  |  | Type of Disability |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | S.O | D.O | V |  |
| 1 | Munkombwe Royness | F | 12 | Kabobola |  |  |  | Low Vision |
| 2 | Katowa Hillary | M | 14 | Kabobola |  |  |  | Low Vision |
| 3 | Ngandu Romani | M | 17 | Hillside |  |  |  | Low Vision |
| 4 | Daliso Banda | M | 13 | Apollo |  |  |  | Low Vision / Albino |
| 5 | Hamani Jane | F | 15 | Kaleya Station |  |  |  | Low Vision/ Physically Challenged |
| 6 | Innocent Makala | M | 16 | Kaleya Station |  |  |  | Low Vision |
| 7 | Eniya Mkandawire | F | 16 | Show Grounds |  |  |  | Low vision |
| 8 | Socka Nasilele | F | 12 | Nkabika |  |  |  | Low Vision |
| 9 | Mapenzi H | M | 6 | Nkalama |  |  |  | Low Vision |
| 10 | Omanti H | M | 15 | Munenga |  |  |  | Blind |
| 11 | Benford | M | 14 |  |  |  |  | Low Vision |
| 12 | Nchimunya | M | 28 |  |  |  |  | Low Vision |
| 13 | Chabota Muteba | M | 9 | Kabobola |  |  |  | Deaf/ Dumb/ Blind |
| 14 | Gift | M | 16 |  |  |  |  | Blind |

We hope to get the same details from the other 3 districts where CHILDHOPE-Zambia is operating.

The districts provided lists of materials they feel will be appropriate for the Visually Impaired children. The quantities will be influenced by the number of children that we will identify soonest.

| # | Name of Item |
| --- | --- |
| 1 | STYLUSES |
| 2 | PERKING BRAILLE MACHINES |
| 3 | WHITE CANE |
| 4 | TALKING WATCHES |
| 5 | HAND-FRAMES/ POCKET-FRAMES |
| 6 | BRAILLE PAPER |
| 7 | TRACERS |
| 8 | SOUND BALLS |
| 9 | PLAYING CARDS |
| 10 | JIGSAW PUZZLES |
| 11 | MUSIC INSTRUMENTS (GUITAR, DRUMS, ETC) |
| 12 | COMPUTERS (TALKING) |
| 13 | DOLPHINS |
| 14 | SUN GLASSES (DARK ONES) |
| 15 | POLY PAPER |
| 16 | BRAILLE WATCHES |
| 17 | BRAILLE MAPS |
| 18 | FOLDERS (PAPER AND HARDBOARD) |
| 19 | MATTRESSES |
| 20 | MATHEMATICS TERRIER NUMBERS |
| 21 | DOTTED PLASTIC EGG TRAY |
| 22 | MAGNIFYING GLASSES |

Activity 3

- Capacity building for classroom teachers

This Activity was implemented.

Two three (3) day Training Workshops for Community School Teachers were held in Mazabuka and Monze Districts for Inclusive Education interventions in Southern Province’s selected districts. These trainings took place at Namulonga Basic School in Mazabuka and St Vincent De Paul Community School in Monze District during 28th to 30th December 2011 and 4th to 6th January 2012 respectively. Twenty-six (26) teachers benefited from the support of Sightsavers and European Commission through CHILDHOPE-Zambia and the Ministry of Education.

Workshop Objectives and Methodology

Aim and specific objective of the training

- The training aimed to increase participants’ understanding of Inclusive Education and its role in mainstreaming disability.

- The specific objective is to assist participants to incorporate an inclusive education perspective into the design of education and activity implementation.

Anticipated outcomes of the Trainings:

- Participants oriented to the Broader understanding of the Philosophy and rationale of Inclusive Education;

- Participants acquainted with the Teaching and Learning Methods in readiness for creation of Child Friendly School environments and specifically the outcomes under Basic Education;

- Participants understand their roles and responsibilities in the identification and support for children with Visual impairments including other physical and mental challenges as one of ZIEP project outcomes.

- Enhanced Teacher competences in handling children, Class Management, and Planning

- Enhanced teacher competence in child assessments for low vision

- Enhanced partner capacity to develop comprehensive networks for 2011 to 2013.

Participant’s expectations

- To acquire new knowledge and skills in teaching and learning methodologies

- Learn more on Classroom Management

- To participate fully in the workshop activities

- To acquire more skills on how to handle children with Special Education Needs

- Acquire skills on how to identify children with Low Vision

- To receive a certificate of attendance

- To be financially empowered

The themes the participants discussed include;

OPENING SESSION- Welcome and Opening Remarks by DEBS, Participants, and Facilitators

Issue 1: CHILD FRIENDLY SCHOOL -Brainstorm and Discussion

Issue 2:  CARE AND SUPPORT FOR TEACHING AND LEARNING-Brainstorm and Discussion

Issue 3: CLASS   DISCIPLINE - Brief Lecturette, Brainstorm and Discussion

Issue 4: THE ATTENDANCE REGISTERS- Brief Lecturette and Discussion

Issue 5: APPROACHES/METHODS TO LEARNING-Brief Lecturette and Discussion

Issue 6: CLASS MANAGEMENT AND MANAGEMENT-Brainstorm, Group work, Presentation and Discussion

Issue 7: LESSON PREPARATION--Brainstorm, Group work, Presentation, Discussion and Brief Lecturette

Issue 8: THE SCHEMES OF WORK - Brainstorm, Group work, Presentation, Discussion and Brief Lecturette

Issue 9: LESSON PREPARATION (LESSON PLAN) - Brainstorm, Group work, Presentation, Discussion and Brief Lecturette

Issue 10: TEACHER’S ROLES - Brief Lecturette and Discussion

Issue 11: QUALITIES OF A GOOD TEACHER - Brief Lecturette and Discussion

Issue 12: SPECIAL EDUCATION - Brief Lecturette and Discussion

Issue 13: EDUCATION ACT - Brief Lecturette and Discussion

Issue 14: HOW TO ASSESS CHILDREN WITH LOW VISION- Brief Lecturette and Discussion

Closing Session: Closing remarks and workshop evaluation

The following were the beneficiaries

| Mazabuka District Holiday Competence Training |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| SN | NAME |  | STATION | POSITION |  | PHONE # |
| 1 | Petronella Mukoma |  | Mubuyu Community School | Class Teacher |  | 0977232017 |
| 2 | Elizabeth M Malumbe |  | Mazabuka Basic School | Class Teacher |  | 0979536877 |
| 3 | Betty Chirwa Jere |  | Namulonga Basic School | Deputy Head |  | 0977541540 |
| 4 | Sheila S Chile |  | DEBS Office | DRCC |  | 0977520595 |
| 5 | Namaundu Ireen |  | Shimungalu Community School | Class Teacher |  | 0979662993 |
| 6 | Rona M Yoyo |  | Ndeke Community School | Class Teacher |  | 0977171255 |
| 7 | Mazuba Neddy |  | Chabota Community School | Class Teacher |  | 097730864 |
| 8 | Mwalunyunje Justinah Chansa |  | Namulonga Basic School | Class Teacher |  | 0976832034 |
| 9 | Hamalala Chibinga Mary |  | Nanga Special School | Class Teacher |  | 0979994605 |
| 10 | Muganya John |  | Nziba Community School | Deputy Head |  | 0976374861 |
| 11 | Christina Zimba Nyendwa |  | Kaleya Community School | Class Teacher |  | 0979990771 |
| 12 | Liwanga Kakuwa Siyambu |  | Mazabuka Basic School | HOD |  | 0979758683 |
| 13 | Hachoongo Edgar |  | Mutumbi Community School | Class Teacher |  | 0977699599 |
| 14 | Hamweenda Cecilia |  | Luyobolola Community School | Class Teacher |  | 0973792759 |
| 15 | Moomba Roy |  | Namulonga Basic School | Head Teacher |  | 0977828199 |
| 16 | Tim Hanguwa |  | DEBS Office | DEBS |  | 0977824823 |
| Monze District Holiday Competence Training |  |  |  |  |  |  |
| SN | NAME | STATION |  |  | POSITION | PHONE # |
| 1 | Victor Linyangu | Lukamantano Community School |  |  | Class Teacher | 0979910201 |
| 2 | Alexandra Hambote | Lukamantano Community School |  |  | Class Teacher | 0976853937 |
| 3 | Precious Habulembe | Lukamantano Community School |  |  | Class Teacher |  |
| 4 | Chuuka Osden | Lukamantano Community School |  |  | Deputy Head | 0974661684 |
| 5 | Royd Hinyama | St Vincent De Paul Community School |  |  | Class Teacher | 0979420134 |
| 6 | Jameson Kahwata | St Vincent De Paul Community School |  |  | Class Teacher | 0977593481 |
| 7 | Luyando Mponda | St Vincent De Paul Community School |  |  | Class Teacher | 0977270380 |
| 8 | Kanene Francis | St Vincent De Paul Community School |  |  | Class Teacher | 0975273153 |
| 9 | Sr Lontia Siakalambwa | St Vincent De Paul Community School |  |  | Head Teacher | 0977410126 |
| 10 | Chilema Peggy | DEBS Office |  |  | DEBS | 0965232206 |

PARTICIPANT FEEDBACK AND EVALUATION

Participants gave feedback during daily reflections and in a final evaluation. The methodology of feedback and results of the final evaluation are presented below.

## Daily Reflection - Eyes and Ears

Elected participants gave daily reflections and reports to present workshop observations. An ear to report presented what was said, and an eye to report accounted what was visually seen, both during workshop sessions and during informal side discussions.

## Final Evaluation

Participants presented a Final evaluation at the end of the workshop. They did evaluate their expectations against the set anticipated outcomes to come with conclusive statements about the extent to which the workshop met participants’ needs and about the workshop’s quality.

Ninety percent of the participants believed strongly that the workshop achieved its objectives, and that the design and process of the workshop helped in achieving them. All participants greatly appreciated the workshop materials and believed that they were extremely useful in helping the workshop to accomplish its objectives. Participants appreciated the interactive and participatory nature of the workshop.

Results outputs

- Broader understanding of the Philosophy and rationale of Inclusive Education;

- Better Teaching and Learning Methods adapted in readiness for creation of Child Friendly School environments and specifically the outcomes under Basic Education;

- Understood roles and responsibilities in the identification and support for children with Visual impairments including other physical and mental challenges as one of ZIEP project outcomes.

- Better Teacher competences in handling children,

- Better Class Management, and Lesson Preparation

- Teacher competence in child assessments for low vision and administration of the assessment tool

- Networks for 2011 to 2013 more comprehensive.

Result 3:  A positive attitude and increased support for Inclusive Education developed

For Example

Activity 1:

Title of the activity: workshop for provincial policy makers at location W with X participants for Y days on Z dates

Topics/activities covered <please elaborate>:

Reason for modification for the planned activity <please elaborate on the problems -including delay, cancellation, postponement of activities- which have arisen and how they have been addressed> (if applicable):

Results of this activity <please quantify these results, where possible; refer to the various assumptions of the Logframe>:

  - What is your assessment of the results of the Action so far? Include observations on the performance and the achievement of outputs, outcomes and impact in relation to specific and overall objectives, and whether the Action has had any unforeseen positive or negative results (please quantify where possible; refer to Logframe Indicators).

- Please list potential risks that may have jeopardized the realisation of some activities and explain how they have been tackled. Refer to logframe indicators.

  - Please provide an updated action plan

- Name of the contact person for the Action: ……………………………………………

- Signature: ………………………………………

- Location: ………………………………………

- Date report due: ……………………..…………

Date report sent: ……………………………….