PROJECT TITLE		: 	 EXPANDING  HOME AND COMMUNITY 								BASED SUPPORT SERVICES IN PRIMARY 								PREVENTION 	OF CHILD ABUSE AND EARLY 							INTERVENTION INITIATIVES

PROJECT COVERAGE	: 	KAJIADO COUNTY, RIFT VALLEY PROVINCE.

TARGETING		:	VULNERABLE AND ORPHANED CHILDREN OF 0- 							6YEARS

CONTACT PERSON	: 	CHRISTOPHER MWANGANGI

TITLE			: 	PROJECT COORDINATOR

IMPLMENTING AGENCY:	KITENGELA ORPHAN CHILDREN

P. O. BOX 415-000-1000 - KAJIADO,

NAIROBI.

TEL/FAX:xxxx	CELL PHONE: 254724522111

EMAIL:kofcare2011@yahoo.com

FUNDING AGENCY	:

LEGAL STATUS		: 	REGISTRATION NUMBER . MKS/CD/1/R/S/G 2426

AMOUNT REQUESTED	:               US$   192,655

PERIOD/DURATION	:	24 MONTHS

SUBMITTED ON		: 	JAN 2013

1.0	APPLICANTS

Kitengela Orphan Children programme is a Community Based Organisation (CBO) whose mission is the Rehabilitation of Orphan Children who have fallen into deprivattion due to socio – economic factors, negative cultural beliefs and gender inequity. Kitengela Children  was started as a self – help group in 1998, and registered with  the Ministry of sports, gender, culture and social services Kajiado County Number MKS/CD/1/R/S/G 2426 as a CBO  on 16th September  2002. Kitengela  Children has her secretariat and a local office in Kitengela  town in Kajiado County. Kitengela Orphan Childrenenjoys her status with most of ther activities targeting the rural areas of Kajiado County. The founders are women who were married at the age of 15 because of poverty and they had to struggle by venturing into unchartered waters to feed and educate their children. It’s through this background that they decided with other women to form Kitengela Children programme, to enable them share their life experiences with women who have faced/facing similar problems and to encourage them through building their capacity as to reclaim their lost positions in the society.(for more information please see the attached organisational profile)

The three key principal programmes are,

- HIV/AIDS sensitization

- Environmental conservation.

- Gender empowerment (women/Youth programs).

- Income generating and entrepreneurship

- BACKGROUNDS

Kitengela Children programme having major concern with marginalized vulnerable and disadvantaged communities establishes development initiatives at the local grass root especially in Kajiado County, West Constituency at   Kitengela  town Division has Kitengela Orphan Children office and other women self-help groups as partner implementing agency, so as to realize the objectives with high impact.

2..1	ACHIEVEMENTS

Kitengela Children programme Women Self-Help Group appreciates achieving,

- An elected management committee

- A borehole

- Two(2) shallow wells for domestic use

- Contributed 75 acre land for health facility/OVC –orphans Rehabilitation center

- Identified environmental conservation sites

- Training of TOTs in HIV/AIDS awareness

PURPOSE OF THE SOLICITED FUNDS:

To support primary prevention of child abuse and early childhood intervention initiatives focusing on families with children aged 0 – 6 years.

PROJECT COVERAGE

The proposed project will be based at community level in Kitengela  town Division Kajiado County, RIFT VALLEY Province.

PROJECT GOAL

Kitengela Orphan Children aims to provide a community development initiative where orphaned children, especially in the marginalized communities are free from abuse, poverty, ignorance and discrimination and where they can enjoy equal opportunities just like the other children.

OBJECTIVES OF THE PROJECT

- To prevent child abuse and vulnerability of orphaned children.

- To prevent HIV/AIDS prevalence in children

- To promote equal learning opportunities for girl and boy child.

- To  establish a safety net to reduce stigmatisation

- To promote community based support to OVCs.

PROJECT ACTIVITIES

- Establish Shelter/Centres for  OVC’s Feeding Programmes

- Support  day care services at the feeding Centres

- Elect playing facilities at the feeding Centres

- Support  informal education to the OVCs at the centres

- Provision of Preventive health care

TARGET BENEFICIARIES

The fundamental conditions of human development cannot be without sustained investment in essential basic human needs especially food, clothing and shelter. Therefore, this project target 18,418 beneficiaries as indicated by the population County plan as per 2002.

Kitengela Orphan Children targets directly 250 Orphaned and Vulnerable Children children seeking to strengthen primary prevention of child abuse focusing on families with children of ages 0-6 years.

The potential of orphaned children due HIV/AIDS related causes will be enhanced through establishment of safety nets. Therefore, the objectives of reducing stigmatisation, discrimination and any other form of child abuse are to be achieved.

PROBLEM STATEMENT

The CRC (Children’s Right Commission) sets out a framework for protection that emphasizes the family and community as having the main responsibility for caring for children (Art. 5, 18). The role of the state is to support and enable families and communities to fulfil this role. However, it is an unfortunate fact that in many cases families and communities are not protective and nurturing.

In these cases, as for vulnerable orphaned children, the state then takes on a greater responsibility to fill the gap (Art. 20: ‘A child temporarily or permanently deprived of his or her family environment…shall be entitled to special protection and  protection and assistance provided by the State’).

The majority of articles in the CRC apply to the orphaned children because of their extreme vulnerability and particular vulnerability to the following: violence (Art. 19), disease (Art. 24), discrimination (Art. 2), sexual abuse and exploitation (Art. 34, 32), substance abuse (Art. 33), emotional deprivation (Art. 19, 31), exploitative and harmful child labour (Art. 32), denial of rights within the juvenile justice system (Art. 37, 40), arbitrary execution (Art. 6), torture (Art. 37), lack of access to education (Art. 28, 29) and healthcare (Art. 24) and lack of identity documents (Art. 7).

The traditional extended family has ‘’lost meaning’’ and majority of the orphaned children relatives are not willing to take up the responsibility of the orphaned children. The orphans are seen as an extra burden in most The U.N. Rules for the Protection of Juveniles state that children shall have the right to facilities and services that meet all the requirements of health and human dignity.195 The facility's physical environment should be designed with the aim of rehabilitation and with due respect for the need of children for privacy, sensory stimuli, opportunities for association with peers and participation in sports, physical exercise and leisure time activities.196 Every juvenile should be provided with sufficient bedding, which should be kept clean and in good order.197 Sanitary installations should be of a sufficient standard to enable every juvenile to comply with his or her physical needs in privacy and in a clean and decent manner.198 Children should have the right to use their own clothing, to the extent possible, and care should be taken to ensure that children have adequate clothing for the climate.199 Suitably prepared food should be provided at regular meal times and should meet standards of dietetics, hygiene, and health.

JUSTIFICATION

Extended families as a remedial measure

1.Families where they face discrimination and all forms of child abuse. In most cases they are isolated from other children in the families and they are denied all the existing opportunities to enjoy just like the other children.

The orphans suffer a second loss when they are divided among their relatives in the family to take care of them and this explains why majority of children opt to stay alone in the child-headed families.

2.Street  life as a remedial measure

Where are their families? Relatively few street children are actually orphans (although these numbers are increasing in some countries due to AIDS). The majority of street children are still in contact with their families and/or extended families. Many of them work on the streets in order to contribute to their family’s income. Those who run away often do so because of physical, psychological and/or sexual violence or abuse at home. Family breakdown is also common in the case of re-marriage and problems with step-parents.

The orphaned children tend to run to the streets trying to escape from the cruellity they face from the discriminative society where they become more vulnerable and engage in drug abuse (glue sniffing), begging, child prostitution and other forms of child delinquency behaviour.

Importantly, many projects try to reunify street children with their families. However, this is a complex and frustrating task that requires much specialised counselling to address the root causes why the child ran away in the first place. Unfortunately, in many cases, reunification with the family fails, or is not in the best interests of the child.

1.Children and elderly headed families

these families are as a result of children loosing both parents due to HIV/AIDS related causes leaving children without parents or families  headed by the elderly people mostly of age 60-80 years. These children suffer due to poor early childhood development and health related problems like malnutrition and majority die before five years of age.

This also denies some children opportunity to go to school especially the girl child since they have to remain at home to take care of their siblings and provide family labour.

The elder children also face all types of abuse as they work hard to make ends meet e.g. the girls face all forms of sexual abuse from the men who take advantage of their vulnerability and make false promises to them. The girls fall a trap thinking that they will get material support to cater for their families or ailing parents risking HIV/AIDS and unwanted pregnancies.

In reality, it is often civil society organizations (CSOs) rather than governments that take on the burden of caring for these children. Increased cooperation and collaboration is required amongst CSOs in order to exchange lessons learned and good practices. It is also needed between CSOs and the state to ensure the sustainability of programmes and to address underlying socio-economic and discriminatory policies that perpetuate the vulnerability of orphaned children.

This reality leaves no chance for the women of Kitengela Children programme to compromise the prevalence of OVCs hence; they are moved towards alternatives such as fostering, group homes and residential centres where the children are rarely alone even if they have no family contact. “Here we do not have any kind of blood relation with each other. But when we are with other friends, though we do not have any name for our relation, we are like a family. We are all actually members of our family.” [Children Diary, Save the Children Fund -UK Nepal, 2001]

ANTICIPATED RESULTS

At the end of the project, there would be over 6,400 households with over 10,418 people to benefit direct with,

- Over 350 orphaned children delivered from elements of poverty and intra-house poverty.

- 90% of abused children delivered from irresponsible house hold heads.

- 85% of population access economic opportunities and social services for the poor.

- Secure and caring environment for the proper growth and development of vulnerable children.

The Kitengela Orphan Children initiative will complement efforts by other development agencies to achieve the national goal of child abuse prevention at national level through primary prevention and early intervention initiatives.

4.0	PROJECT MANAGEMENT

Kitengela Orphan Children observes with confidence the operations, enhancing accountability and transparency at all levels of the programmes. The responsibility of the project management is run by Board members Kitengela Children programme Women management committee

DDO / DSDO

Kitengela Children Elected Committee Members

Project Coordinator

Preventive Health Care/HIV/AIDS

Food Security/environmental conservation

Gender Empowerment

Other Identified Groups

4.1	PROJECT IMPLEMENTATION

The key strategies are:

Project phase one: Kitengela Orphan Children initiative will focus on the major development challenges and cross cutting issues in the community to increase prevention of child abuse at house hold levels and other influential institutions.

Activities

- community mobilisation and sensitisation

- Feeding programmes

- Day care services

- Informal education

- Preventive health care services

Project phase two:

Children of compulsory school age have the right to education which should be "designed to prepare him or her for return to society." Therefore, in furtherance to her activities Kitengela Orphan Children initiative will involve a rehabilitation centre which will also be a counselling centre as the long term intervention. Children above compulsory school age (more than 6 years) who wish to continue their education will be permitted and encouraged to do so, and every effort will be made to provide them with access to appropriate educational programs.

Activities

- Formal education support

- Boarding facilities

- Counselling centre

- Paediatric services

- Transport facilities

- Food and Clothing

SUSTAINABILITY

Although education is not yet compulsory in Kenya, the Kenyan government has committed itself to providing tuition-free education at the primary level (standards 1-8) to all. In these cases Kitengela Children programme initiatives will continue through provision of basic education, health services and other aspects of life like food, shelter and clothing which the youthful population calls for.

The Kitengela Orphan Children Committee and influential leaders would continue protection and management always through practical demonstration initiatives advocating for the children rights. Orphaned families (children and women) capacity will be build to establish safety nets to reduce stigmatisation and to increase Income generating per house hold.

MONITORING AND EVALUATION

Kitengela Children programme through its management Committee members will independently conduct bi – monthly follow up(s) and evaluation exercise of each of the project activity and the entire process. This will be done with the help of experts in social audit and evaluation, who are expected to review the outputs to the project against the set goal, purpose, target group, objectives, strategy and activities.  The constant monitoring and bi - monthly evaluation will enable the organization to ascertain progress and effectiveness of the project strategies. This will in turn help in assessing the cost effectiveness and efficiency in terms of participation and facilitation with the view of learning lessons and constraints of the project.

PROJECT TIME FRAME

| PROJECT PHASE 1 | RESOURCES | EXPECTED OUTCOME | DURATION |
| --- | --- | --- | --- |
| community mobilization and feeding programme | Kitengela Orphan Children and community skilled/manual labour and Partner | - Identified 350 OVC in their families’ best interest. - Established feeding shelters - Identified care and informal education givers - cooks identified and cooking facilities available - Feeding facilities available - Available food stuff - Ready beddings and playing objects | 12 months |
| PROJECT PHASE 2 | RESOURCES | EXPECTED OUTCOME | DURATION |
| Counselling, boarding and education support centre for the OVC | Kitengela Orphan Children and Community | - Available boarding facilities. - available counselling services - available transport facilities - Available formal/vocational education support funds - Available paediatrician services | 12 MONTHS |

PROJECT IMPLEMENTING BUDGET

PROJECT PHASE 1(ONE)

| FOOD STUFF | AMOUNT: US$ |
| --- | --- |
| 150 bags of maize@ US$ 42 100 bags of beans@ US$ 76 20 bags of Rice@ 85 20 Bags of Ndengu@ 47 50 bags of Uji flour@ 110 200 cartons of milk powder@ 30 240 litres of cooking oil@ 1.50 10 bags of wheat flour@ 60 1,800 kilos of sugar@2 20 kilos of salt@ Fruits @ Vegetables@ beddings@ playing toys@ clothing@ TOTAL | 6,300 7,600 1,700 942 5,500 6,000 360 600 3,600 20 24,710 1,418 4,500 350 15,000 75,000 |

PROJECT PHASE 2(TWO)

BOARDING FACILITIES						  11,155

TRANSPORT VAN						   15,000

EDUCATION SUPPORT@ US$ 250			              88,000

5 VOLUNTEERS 						    3,500

SUB-TOTAL: US$						 105,830

GRAND TOTAL	 : US$	                                                             192,655

ORGANISATION PROFILE

HISTORICAL DEVELOPMENT

Kitengela Orphan Childrenis a Community Based Organisation (CBO) whose mission is the Rehabilitation of Women who have fallen into deprivattion due to socio – economic factors, negative cultural beliefs and gender inequity. Kitengela Children programme  was started as a self – help group in 1998, and registered with  the Ministry of sports, gender, culture and social services Kajiado County Number MKS/CD/1/R/S/G 2426 as a CBO  on 16th September  2002. Kitengela Children programme has her Secretariat in Naoirobi as the National offices and a local office  in Machakos Town  in Machakos County, Kajiado Town in Kajiado County. Kitengela Orphan Childrenenjoys her status with most of her activities targeting the rural areas. The founders are women who were married at the age of 15 because of poverty and they had to struggle by venturing into unchartered waters to feed and educate their children. It’s through this background that they decided with other women to form Kitengela Children programme, to enable them share their life experiences with women who have faced/facing similar problems and to encourage them through building their capacity as to reclaim their lost positions in the society.

In furtherence to her mission, Kitengela Children programme has through her activities realised that the difficulties faced by women at all levels and spheres of life can only be addressed when the thorny issues of gender inequalities are also addressed. Kitengela Children programme’s achievement have been realised in the training of women groups in enterpreneurship, HIV/AIDS sensitization, mainstreaming gender in civic education programme, and  environmental conservation. Our entry points have been the women groups and our targets are mainly women and men at a ratio 2 to 1.

There are historical factors that have led to women being lowly represented in Kenyan politics due to traditional attitudes and gender stereotypes in their roles. Traditions demands that men must lead while women and children are to follow an outdated tradition, which must be discarded at all costs. In regard to this Kitengela Orphan Children is in the fight for human right as it recognizes women’s rights as human rights therefore advocates for their rightful place in society by promoting and increasing their knowledge on their civic /civil rights, roles and responsibilities. Kitengela Orphan Children also promotes gender mainstreaming as an effective means for organizational development and change in leader ship and good governance.

OVERALL OBJECTIVES

Kitengela Orphan Childrenobjective is to create a conducive environment in which women and children can be empowered to overcome poverty, ignorance and discrimination.

###### SPECIFIC OBJECTIVES

- To advocate for the rights of women and children, for their rightful place in society by   promoting and increasing their knowledge on their civic/civil rights, roles and responsibilities.

- To build a multipurpose community center to be used as information center for women to access information, and encourage women to participate in discussions and decision-making process affecting them.

- To build the capacity of women groups as vehicles for good governance and management of socio-economic affairs by training and workshops.

- To network with other organizations that promotes gender equity and equality.

VISION

Kitengela Orphan Children envisions a society where women in general, especially the rural women and orphaned children, are free from abuse, poverty, ignorance and discrimination caused by gender biases and where they can have the capacity to support their families economically and socially and are aware of their civic rights as well as their responsibilities, obligations and free to advocate for their socio-economic, political representation and participation in public and development issues.

PHILOSOPHY

In order to add value to the quality of service delivery and stand out as reliable, stable and dependable service provider Kitengela Orphan Children believes in equity, justice, fairness, and eradication of ignorance and poverty, which are viewed as the main obstacles to sustainable development among the women and children.

GOALS

- To enhance and influence the gender skills in socio-economic governance, gender sensitivity in planning, budgeting and budget monitoring at County level of key Community Based Organizations (CBO) ’s, officials of County departmental heads and women and youths political and development representation.

- To give women in general especially the abused and orphaned children a chance to live normal life like any other person in Kenya. And to contribute to the reduction of poverty, ignorance, rebuilding the faith and will of abused women and children through promotion of women’s self help projects and giving them moral and material support where possible so as to reduce the dependency syndrome, which tends to subordinate them, leading to more abuse resulting to death.

LOCATION

Kitengela Orphan Children secretariat is located in Kitengela  Town with its branches at Kajiado and Naroko Counties.

TARGET GROUP

- Women who are victims of gender inequality

- Children orphaned by AIDS

- Abused women and those in difficulty circumstances

- Women living with HIV/AIDS

- Children living with HIV/AIDS

ORGANIZATION STRUCTURE

Kitengela Orphan Children is run by a Management Committee (whose titles are listed below) in collaboration with the Organization Members who ensures that Kitengela Orphan Children runs smoothly. The Committee works with  50 other members  (all of them women), and also works with services of secretariat staff, which includes the Administrative Officer, Programme Officers, Finance Officer, Secretary/information Officer, Office Assistant and  Student Volunteers on contract.

Kitengela Orphan Children works in collaboration with various Community Based Organizations in Kajiado West County – Naroko, Loitokitoko, Langata Rongai and Isanyia and other parts of Kajiado County.

The committee comprises of the following:-

- Chair person

- Asst. Chair person

- Treasurer

- Secretary

- 150 Members

STAFF STRENGTH AND PROGRAMME ACTIVITIES

Kitengela Orphan Children enjoys a local status, with most of its activities concentrated in Kitengela , Kajiado central and Isanyia Divisions in kajiado County, Naroko, Raisamiti,Loitokitoko  and Rongai Divisions in Kajiado County due to its limited human and financial resource capacity.

Kitengela Children programmeW/S/G’s activities include the following community based programmes:-

- Informal and formal training and education.

- Social counseling and empowerment.

- Peace building and reconciliation

- Gender mainstreaming

- Income generating and entrepreneurship

- HIV/AIDS sensitization.

- Environmental conservation

SERVICE DELIVERY SYSTEMS

To facilitate efficient service delivery Kitengela Orphan Children plans to organize its operations into two (2) systems paid services and voluntary services that is peace building in families, Counseling, guidance, and placement of orphaned children in both schools and family homes. Advocacy for representations of women in socio-economic management and political position. Consultancy services on development issues for community based organizations, and individual persons.

ACHIEVEMENTS

Kitengela Orphan Children appreciates achieving,

- An elected management committee

- Identified focal outreach area

- Contributed 75 acre land for health facility/OVC –orphans Rehabilitation center

- Identified environmental conservation sites

- Elected FOA management committee.

KITENGELA CHILDREN PROGRAMME W/S/G’ S DEVELOPMENT PARTNERS FOR THE NEXT 12 MONTHS

Kitengela Orphan Children has formed a good working relationship with:

- National AIDS Control Council (NACC)- HIV/AIDS/Sexual rights and it’s effect on socio-economic among women

- County Social Development Officer

- Constituency Development Fund –Training of TOTs Kshs.60,000

- American Self Help Fund –Environmental conservation(construction of gabions) Kshs.769,000

- Canadian Local Initiative Fund – Water and Sanitation Kshs. 2.9 M

- OPEC International Fund

- Japan Embassy (GGF) – Construction of PHCF –Kshs.6.4 M

- Communities, churches, Institutions and individuals.

CHALLENGES

- High levels of illiteracy hence there is need for formal adult education.

- Threatened food security efforts due to frequent and prolonged droughts

- Sudden collapsing of stimulated income-generating activities to provide alternative sources of income other than charcoal burning.

- Denying girls equal learning opportunities as the boys

- Cultural practices: witchcraft which is widely spread and deeply entrenched in some parts of the County and as a result, residents working in urban centers and outside the County fear going to their rural homes or even investing there.

- Under developed infrastructure: most of the road in the County are earth roads and are in very pathetic state and become impassable during the rainy season.

.

KITENGELA ORPHAN CHILDREN PROGRAMME INITIATIVE ACCOUNT.

MC/MS/ ACCOUNT BOOST INITIATIVE ACCOUNT

REPORT AND FINANCIAL STATEMENT SFOR THE YEAR ENDED 31ST DECEMBER 2012.

# CONTENTS 									        PAGE

GROUP INFORMATION 								1

MANAGEMENT COMMITTEES REPORT 						2

STATEMENT OF MANAGEMENT COMMITTEE’S RESPONSIBILITIES 		3

INDEPENDENT AUDITORS REPORT 						4

BALANCE SHEET 								5

INCOME AND EXPENDITURE ACCOUNT 						6

CASH FLOW STATEMENT 							7

NOTES TO THE ACCOUNTS 							8-9

SCHEDULE FOR RECEIPTS AND PAYMENTS					9

NDETAI & CO

CERTIFIED PUBLIC ACCOUNTANTS (K)

P. O. BOX 1165,

KAJIADO, KENYA.

KITENGELA ORPHAN CHILDREN INITIATIVE ACCOUNT.

MC/MS/ ACCOUNT BOOST INITIATIVE ACCOUNT

REPORT AND FINANCIAL STATEMENTS FOR THE YEAR ENDED 31ST DECEMBER 2012.

# GROUP INFORMATION

AUDITORS: 				NDETEI & CO

Certified Public Accountants

P. O. Box 65,

Kajiado, Kenya.

BANKERS: 				CO-OPERATIVE BANK

ACCOUNT NO. 0110079817900

Nacico Branch

FINANCIERS: 			MC/MS/ACCOUNT BOOST

FINANCIAL MANAGEMENT: 	KITENGELA ORPHAN CHILDREN

Committee Management.

KITENGELA ORPHAN CHILDREN INITIATIVE ACCOUNT.

MC/MS/ ACCOUNT BOOST INITIATIVE ACCOUNT

REPORT AND FINANCIAL STATEMENTS FOR THE YEAR ENDED 31ST DECEMBER 2012.

# MANAGEMENT COMMITTEE’S REPORT

The members of the management committee have the pleasure in presenting their report and audited financial statements for the year ended 31st December 2012.

# RESULTS

The results of the project’s operations are set out on Page 6.

MANAGEMENT COMMITTEE MEMBERS.

- Munanie Muli			– 	Chairperson.

- Alice Kanyaa		             -          Honorary Secretary

- Elizabeth Wanza           		– 	Honorary Treasurer.

# AUDITORS

NDETEI & CO Certified Public Accountants have signified their willingness to continue in office and hereby do so in accordance with the Grant Agreement.

By Order of the Management Committee.

Honorary Secretary.

Date:…………………………….

KITENGELA ORPHAN CHILDREN INITIATIVE ACCOUNT.

MC/MS/ ACCOUNT BOOST INITIATIVE ACCOUNT

REPORT AND FINANCIAL STATEMENTS FOR THE YEAR ENDED 31ST DECEMBER 2012.

STATEMENT OF MANAGEMENT COMMITTEE’S RESPONSIBILITIES.

The Grant Agreement between the National Aids Control Council Financial Management Agency and Kitengela Orphan Children requires the latter to prepare financial statements for each financial quarter, which give a true and fair view of the utilization of grant funds for the quarter. It also requires the Management Committee Members to ensure the organization keeps proper accounting records which disclose, with reasonable accuracy, the financial position of the project. They are also responsible for safeguarding the assets of the organization.

The management committee accepts responsibility for the annual financial statements, which have been prepared using appropriate accounting policies supported by reasonable and prudent judgments and estimates, in conformity with Generally Accepted Accounting principles and the requirements of the Grant Agreement. The Management Committee Members are of the opinion that the financial statements give a true and fair view of the further accepts responsibility for the maintenance of accounting records which may be relied upon in the preparation of the financial statements as well as adequate systems of internal financial control.

Nothing has come to the attention of the Management Committee to indicate that the organization will not remain will not remain a going concern for at least the next twelve months from the date of this statement.

CHAIRMAN:……………………………………………

HON.SECRETARY:…………………………………….

HON. TREASURER:…………………………………….

DATE:……………………………………………………

NDETEI & CO.

Certified Public Accountants (Kenya)		       P. O. Box 415-000-100							       Kajiado Kenya.

Phone: +25472452211

KITENGELA ORPHAN CHILDREN INITIATIVE ACCOUNT.

MC/MS/ ACCOUNT BOOST INITIATIVE ACCOUNT

REPORT AND FINANCIAL STATEMENTS FOR THE YEAR ENDED 31ST DECEMBER 2012.

INDEPENDENT AUDITORS REPORT TO THE MEMBERS OF KITENGELA ORPHAN CHILDREN AND THE MC/MS/ACCOUNT BOOST INITIATIVE ACCOUNT

We have audited the financial statements set out on pages 5 to 9 and have obtained all the information explanations considered necessary for our audit.

RESPECTIVE RESPONSIBILITIES OF THE MANAGEMENT COMMITTEE AND THE INDEPENDENT AUDITORS.

The financial statements are the responsibility of the Management Committee. Our responsibility is to express an independent opinion on the financial statements based on our edit.

BASIS OF OPINION

We conducted our audit in accordance with the International Standards on Auditing. These standards require that we are free of any material misstatements. An audit includes examining, on a test basis, evidence supporting the amounts and disclosures in the financial statements, assessing the accounting principles used and significant estimates made by the council, and evaluating the overall financial statements presentation.

OPINION

In our opinion, proper books of accounts have been kept and the financial statements which are in agreement therewith give a true and fair view of the state of affairs of the project as at 31st December 2012 and of the surplus for the year ended on that date and comply with the Generally Accepted Accounting Principles and with the grant Agreement.

The accounts have been prepared accurately, the funds have been expended properly in furtherance of the project objectives and value for money has generally been received. In our opinion, therefore, the accounts can be relied upon by the Controller & Auditor General MC/MS/Account Boost Initiative Account, the Financial Management Agency and other Stakeholders.

NDETEI & CO.

Certified Public Accountants (K)

Date: ……………………………

KITENGELA ORPHAN CHILDREN INITIATIVE ACCOUNT.

MC/MS/ ACCOUNT BOOST INITIATIVE ACCOUNT

REPORT AND FINANCIAL STATEMENTS FOR THE YEAR ENDED 31ST DECEMBER 2012.

BALANCE SHEET

31 DECEMBER 2012.

NOTE 		KSHS.

Current Assets

Cash in hand and bank 				2. 			250,000

250,000

Current Liabilities

Net Current Assets

Net Assets

Financed by General Fund

The accounts were approved by the management committee on and signed on this behalf by

Chairman: ………………………..

Secretary:…………………………

Treasurer:…………………………

KITENGELA ORPHAN CHILDREN INITIATIVE ACCOUNT.

MC/MS/ ACCOUNT BOOST INITIATIVE ACCOUNT

REPORT AND FINANCIAL STATEMENTS FOR THE YEAR ENDED 31ST DECEMBER 2012.

INCOME AND EXPENDITURE ACCOUNT

KSHS.		KSHS.

INCOME

Balance B/F 								1,500,000

Members contribution drive (154 members) Monthly subscriptions	   108,000

A/C Boost at 10% loaning on interest 				    900,000

Total Income grant from MC/MS/Account Boost					 																																			1,800,000

LESS EXPENDITURE

Rent offices / Account for Volunteer 					     75,000

Orphaned household support						3,721,796

Transport 								     25,000

Sitting allowance							     45,000

Printing / stationery							     30,000

Bank charges								       9,204

Repair and maintenance						     15,000

Consultancy and audit fee						     65,000

Funeral expenses to assist needy families 				     55,000

Miscellaneous expenses						     17,000

Total expenditure																			4,058,000

Net surplus / deficit                                                                              250,000

KITENGELA ORPHAN CHILDREN INITIATIVE ACCOUNT.

MC/MS/ACCOUNTBOOST INITIATIVE ACCOUNT

REPORT AND FINANCIAL STATEMENTS FOR THE YEAR ENDED 31ST DECEMBER 2012.

CASH FLOW STATEMENT 31 DECEMBER 2012

NOTE	 	KSHS.

Cash flow from operating activities

Cash generated from operating activities 			4. 		250,000

Net cash generated from operations 					250,000

Net cash inflow / outflow 							250,000

Increase (decrease) in cash and cash equivalents 				250,000

Movement cash and cash equivalent

Opening balance

Increase (decrease) in cash and cash equivalents

Balance as at 31st December 2012. 				5. 		250,000

KITENGELA ORPHAN CHILDREN INITIATIVE ACCOUNT.

MC/MS/ACCOUNTBOOST INITIATIVE ACCOUNT

REPORT AND FINANCIAL STATEMENT SFOR THE YEAR ENDED 31ST DECEMBER 2012.

NOTES OF THE ACCOUNTS

- PRINCIPAL ACCOUNTING POLICIES

  - Accounting convention

The accounts have been prepared under historical cost convention

- Cash and cash equivalents

For the purpose of cash flow statement, cash and cash equivalents comprises cash at bank and cash in hand.

- Grants

This is the amount that was contributed by group members.

- CASH AND CASH EQUIVALENTS

31 December 2012

KSHS.

Current Account 						205,000

Cash in Hand 						  45,000

250,000

- GENERAL FUND ACCOUNT

31 December 2012

KSHS.

Surplus / (Deficit) for the year 				250,000

Balance carried forward 				250,000

KITENGELA ORPHAN CHILDREN INITIATIVE ACCOUNT.

MC/MS/ACCOUNTBOOST INITIATIVE ACCOUNT

REPORT AND FINANCIAL STATEMENT SFOR THE YEAR ENDED 31ST DECEMBER 2012.

NOTES TO ACCOUNTS

- CASH GENERATED FROM OPERATIONS

Reconciliation of net surplus (deficit) to cash generated from operating activities.

31 December 2012

KSHS.

Surplus / (Deficit) for the year adjustments			250,000

Net cash generated from operating activities		250,000

SCHEDULE FOR RECEIPTS AND PAYMENTS

31December 2012

KSHS.		KSHS.

RECEIPTS

Income from MC/MS/Account Boost on loan interest 		4,308,000

4,308,000

PAYMENTS

Rent offices / Account for Volunteer 					     75,000

Orphaned household support						3,721,796

Transport 								     25,000

Sitting allowance							     45,000

Printing / stationery							     30,000

Bank charges								       9,204

Repair and maintenance						     15,000

Consultancy and audit fee						     65,000

Funeral expenses to assist needy families 				     55,000

Miscellaneous expenses						     17,000

Total Payments								4,058,000

Balance Carried Forward						               250,000