LOCAL IMPLEMENTING PARTNER NARRATIVE REPORT

| Organization Name: | OSILIGI CBO |
| --- | --- |
| Reference Number: | A/KCO/API-12 |
| Reporting period: | JULY-AUGUST 2012 |
| Region/Province: | RVP |
| County: | SAMBURU COUNTY |
| Person reporting and designation: | RAPHEAL LEKUNA COORDINATOR |
| Address: Telephone, E-mail: | Osiligi22@yahoo.com or rklekuna@yahoo.com 0727615033 |

- EXECUTIVE SUMMARY

Osiligi community care led coalition is a community based non-sectorian,non profit making and non political human development organization working with the local community and other partners in lorroki south to support; community development in the areas of OVC and CHBC services provision i.e. education for the sustainability of community self development initiatives, Environmental health i.e. Sanitation health, primary health care, TB, malaria and Trachoma infections control, reproductive health (HIV/ AIDS), STI STDS  among others.

OSILIGI VISION  STATEMENTS

OUR  VISION IS   TO  STRENGTHEN,ADVOCATE, NURTURE  AND PROMOTE  LOVE,CARE  AND SUPPORT FOR OVC’S  AND    CHBC  CLIENTS

MISSION

OUR IS TO CREATE  ACONDUCIVE  ATMOSPHERE THAT PROMOTES,TRANSFORMS,NURTURE THE WELL BEING  OF OVC/CHBC  CLIENTS(PLWHAs) AND OTHER VULNERABLE  GROUPS WITHIN THE  COMMUNITY

INTRODUCTION

OSILIGI organization has been operational for the last 6 years with partnership and support from various donors and funding groups amongst them are:-

- World vision IPA lorroki (WV)

- National AIDS control council 2002-2004

- National council of Kenya Women

- Child Fund Kenya Lorroki Child Care Programme

- The District children’s department,

- APHIA II RIFT VALLEY LED BY (WORLD VISION )

- Aphiaplusnal led by Pathfinder International and now;

OSILIGI  and APHIAPLUS IMARISHA consortium led by AMREF started a 3 month partnership implemented program on OVC’s and CHBC’s support programs and services in April, May, June, July and August 2012

The programmatic intervention areas of reproductive health are:-

- HIV/AIDS awareness creation towards the control and prevention of infections

- FP

- VCT sensitization

- HIV/AIDS stigma reduction,

- OVC social economic

- WASH

- Shelter and care

- Educational suport

- Economic and livelihoods empowerment.

- CHBC care and support services and as a new coalition partner;

Amref Aphiaplus Imarisha led coalition will be the leading partner for the next 5 years and will be expected to take the sighted community target systems to the next level of social health and economic development

SCAAP Mrs. Akiru CHBC client being provided with a blanket to shelter against the cold. Inset is one of the community health workers

2. PROGRESS AGAINST TARGETS

| Service Area | Activity | Indicator | Targets | Achievement |  |  |  | Percentage Achievement |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 4 |  |
| Health | Sanitary pads, water treatment Malaria prevention (nets | Activity photos | 400 200 400 | 100 50 100 |  |  |  | 25% 25% 25% |
| Education | Uniforms Fees Vocational training, Scholarstic materials ECD support | Receipts Receipts Photos | 423 100 20 150 312 | 154 - 15 50 201 |  |  |  | 0% 33% |
| Food & Nutrition | Unimix Cereals Proteins | Photos | 300 300 300 | 100 200 200 |  |  |  | 33% 67% 67% |
| Shelter & Care | Renovations Blankets issued Beddings Shelter Constr | Photos | 80 200 - - | - 100 - - |  |  |  | 0% 50% |
| Protection | Births registered Wills written Legal referrals Linkages for support | B certific | 300 - - - | - - - - |  |  |  | 0% |
| PSS | Family fun Day Home Visit CHW’s monthly meetings | Meals receipts Field Reports | 250 12 3 | 200 9 2 |  |  |  | 80% 75% 67% |
| Household Economic Strengthening | Trainings organic farming Restocking Loans issued | Photos Seed bags | 15 40 - - | 15 30 - - |  |  |  | 100% 75% |
| No. of OVC Served by primary Direct support (3 or more services | Uniforms ECD Levies Scholarstic Materials (630) | Photos Reports | 450 280 150 | 200 280 150 |  |  |  | 44% 100% 100% |
| No. of OVC served by supplementary direct support (1 or 2 services | Secondary school fees Vocational trainings | Reports Receipts | 100 - | 97 - |  |  |  | 97% |
| BCC Activities | HIV / AIDS awareness rallies Child’s rights Advocacy, VCT sensit.. | Videos | 3 6 6 | 3 6 6 |  |  |  | 100% 100% 100% |
| CHBC Activities | Nutritional supplementation | Photos | 45 | 27 |  |  |  | 60% |
|  | CHBC Kits | receipts | 15 | 0 |  |  |  | 0% |

- CHALLENGES AND RECOMMENDATIONS (Provide solution or recommendation for the challenges noted during the reporting period)

| Challenges | Recommendations |
| --- | --- |
| Low level of facilitation | Timely planning and release of funds and participatory project implementation by partners |
| Inadequate finances / funding of activities | Increase in the allocation of funds to facilitate in full implementation of project activities. |
| Belated release of resources | Timely and consistent release of resources |

## LESSONS LEARNT, HUMAN INTEREST STORIES AND SUCCESS STORIES

The organizational work has been going on in spite of  financial constraints becauses of proper linkage with other service providers among them, the government of Kenya

## PLANS FOR THE NEXT QUARTER/PERIOD

|  |  | ## Activity |  | ## Quarter Target |  | ## Timeframe |  | ## Responsible Person |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Education; - Uniform - Fees - ECD levies - Vocational support - Scholastic support |  | 240 150 280 20 350 |  | Nov,2012 – Jan, 2013 |  | Rapheal,samuel & osiligi board members |
| 2 |  | Health; - Sanitary towel - Water treatment - Mosquito nets sup - Med examination |  | 200 200 300 900 |  | Nov,2012 –Jan, 2013 |  | Raphael ,Solomon, Samuel ,health personnel, osiligi board members |
| 3 |  | Food & Nutrition; - Unimix for CHBC clients & OVC |  | 250 |  | Nov,2012 –Jan, 2013 |  | Rapheal,Solomon,&osiligi board members |
| 4 |  | Shelter & Care - Blanket provisions - Beddings - Clothes/Sheets |  | 300 200 |  | Feb-April 2013 |  | Raphael ,Solomon& the board members |
| 5 |  | Protection. Birth registration Referrals and linkages Will writing |  | 300 |  | Feb-April 2013 |  | Rapheal,registrars office, the CBO paralegals |
| 6 |  | Psychosocial - Family fun day - CHW’s meetings - Home visits - Spiritual Counseling - Emotional Counseling - Grieve and bereavement - Memory Book writing |  | 2 3 12 |  | Feb-April 2013 |  | Rapson,Samuel,rapheal & the CHWS |
| 7 | Economic Strengthening - Trainings - Linkages - Organic Farming support - Small business enterprises |  | 3 80 H/H 40 |  | Feb-April 2013 |  | Rapheal,Solomon,Samuel& Joyce |  |

- OVC SERVICES PROVIDED

|  | OVC Services Provided | Achievement |  |  |
| --- | --- | --- | --- | --- |
|  |  | M | F | Total |
| 1 | Health | 13 | 23 | 36 |
| 2 | Education & Vocational Training | 10 | 5 | 15 |
| 3 | Food & Nutrition | 57 | 34 | 91 |
| 4 | Shelter & Care | - | - | - |
| 5 | Protection & Legal Services | - | - | - |
| 6 | Psychosocial Support | 730 | 556 | 1286 |
| 7 | Household Economic Strengthening | 9 | 7 | 16 |
| 8 | Number of OVC Served by Primary Direct Support (3 or more Services) | 314 | 443 | 757 |
| 9 | Number of OVC Served by Supplementary Direct Support (1 or 2 Services) | 241 | 247 | 488 |
|  | Total Number of OVCs Served by the LIP |  |  |  |

- MANAGEMENT AND STAFFING

Osiligi has a strong management and staffs who oversee the implementation of  both OVC /CHBC care and support  the following  are they;

- RAPHEAL LEKUNA – COORDINATOR/MANAGER

- SOLOMON LETEROI—PROJECT  OFFICER

- SAMUEL  LEKARKAR – M&E OFFICER

- RAPSON LEKINO – MENTORSHIP OFFICER/DATA CLERK

- JOYCE NAITU  LENAKULA – PROJECT OFFICE ASSISTANT

- JOSEPH NDERITU_______ COMMUNITY DEVELOPMENT  OFFICER

- CONCLUSION

## OSILIGI highly appreciate the cooperation exhibited in the foregone quarter in the implementation of the project activities with partners and therefore; look forward for the same in the next program.

Report Prepared by

NAME: RAPHEAL LEKUNA

DESIGNATION: COORDINATOR/MANAGER