# PROJECT PROPOSAL DOCUMENT FOR LIVESTOCK REHABILITATION PROJECT PREPARED BY HOPE INITIATIVES ORGANISATION FOR FUNDING

Project Summary

## Name of Project	 Livestock Rehabilitation Project

Name of implementing

Organization	Hope Initiatives Organization

Contact Address	P.O. Box 139,Kitgum Uganda

Contact Person					Ms Lalam Jackline

Position						Founder/Chairperson

Type of Project	Livestock Rehabilitation Project

Location of Project				Kitgum District

Type of Project Beneficiaries	500

Duration of Project				1 (one) year

Legal Status – The Hope Initiatives Organization is a Voluntary, Community Based Organization. It is officially registered as a community based Organization in Kitgum district.

Community Contribution			$ 1,801   (UGX shs  4,790,000)

Amount of Fund requested			$ 74,720 (UGX shs 198,754,000)

Total Cost						$ 76,520 (UGX shs 203,544,000)

BACKGROUND AND PROBLEMS ANALYSIS

The war in North part of Uganda in the last decade brought untold suffering to the people and the in the North the people are still suffering since they are yet resettling in their homes and recovering from the past events of the war.

Their stories were not good to hear. Among the atrocities committed were houses, school, and other privates and public properties, the scared believes of the people burnt, destroyed, vandalized and looted. The human right of the people completely disregarded. People were killed, hand chopped off, stripped naked, force to eat their feaces and drink their urine, flock publicly and used as labor gang. Raping and force marriages were the order of the day.

Due to the above backdrop, Hope Initiatives thought of giving back hope to the community by doing the following:-

- The Organization agreed that, they would work in collaboration with the local community in the implementation of the project.

- Livestock (small ruminants), which were owned by participants, have been completely looted by the rebels during the war.

- There is no livestock available within the communities.

- Access to livestock is limited because of lack of funds.

The very essence Hope initiatives was formed is to intervene to alleviate the communities’ dire needs.

The project package also serves as a means of replacement of lost livestock. Since the farm families lack funds and alternative resources to purchase them, this will give back livestock to the participants who have lost everything in life.

PROJECT GOAL

The goal of the project is to improve the livestock level of 500 farm families in five (5) communities in Kitgum district.

### SPECIFIC OBJECTIVES

To help provide 500 farm families with livestock (cows, goats, sheep and pigs) to restart and ensure diversified production by January 2014

To reduce malnutrition and increase livestock cows, goats, sheep and pigs available for 500 farms families.

### PRESENT NEEDS

In order to support us reach our objectives, the organization organized a general meeting and listed the following:

- To purchase 15 male cows and 60 female cows for the project.

- To purchase 20 boars and 40 soars, for the establishment of a piggery at the project operational areas.

- To purchase 20 male goats and 40 female goats for the project.

- To purchase 20 male sheep and 40 female sheep at the project operational area.

- To construct a pigsty (pen) of 40ftx 20ft in size at the project site.

- To produce animal fed, water well and drugs for veterinary services.

- To achieve the above immediate objectives the organization needs inputs of initial capital to purchase them in order to start these activities.

IMPLEMENTATION STRATEGY

The under-mentioned strategies will be carried out to achieve the set objectives.

- Community mobilization and sensitization for further understanding of the project.

- Purchase and distribution of livestock (cows, goat, sheep and pigs).

- Protect the livestock (pigs, goats, and sheep) from being sold.

- Supervision, monitoring, reporting and Evaluation of project activities.

OPERATIONAL COMMUNITIES

| VILLAGES | NO OF FARM FAMILIES TARGETED |
| --- | --- |
| Opette Palabek Labongo donyo Manwoko Latiti | 100 100 100 100 100 |
| Total | 500 |

MONITORING AND EVALUATION

The project will be monitored by Hope Initiatives trained executives and jointly with the beneficiaries under the Project. Every activities carried out will be monitored to ascertain whether it is done correctly, at the given time frame and whether the desired effect(s) is achieved. A monitoring questionnaire will be prepared By the organization and used daily by the monitors.

Evaluation would be done from to time at the middle period of implementation and end of each activity.

INSTITUTIONAL CAPACITY

Hope initiatives has not yet done much and we hope for the best if funds allow. Since our target is to raise fund to restore hope to those whom their hope has gone.

PROJECT FEASIBILITY AND SUSTAINABILITY

The people in the operational communities are peasant farmers who have been involved in all their lives in livestock (cows, goats, sheep and pigs). The technology is not new, it part of the way of life of the people.

The people are familiar with the raising of cows, goats, sheep and pigs and the breeds that would be selected and bought are suited to the areas.

Also cows, goats, sheep and pigs are easy to raise involving little or no cost and use of locally available materials for food and housing which ensures continuity needs external support.

BUDGET LINE ITEM

DONOR AGENCY’S CONTRIBUTION

| No | Items | Quantity | Unit Cost | Total Cost |
| --- | --- | --- | --- | --- |
| 1 2 3 4 5 6 7 8 9 10 | Cows (female Cows (male) Goats (female) Goats (male) Sheep (female) Sheep (male) Soars Boars Animal Feed Water Well Drugs & Vaccines Transportation of cows, goats, sheep and pigs & other items to project site. | 60 50 40 20 40 20 40 20 120 bags 1 Lump sum Lump sum | 1,500,000 1,200,000 220,000 180,000 250,000 220,000 175,000 160,000 35,000 5,500,000 4,500,000 2,400,000 | 90,000,000 18,000,000 8,800,000 3,600,000 10,000,000 4,400,000 7,800,000 3,200,000 4,200,000 5,500,000 4,500,000 2,400,000 |
| 11 | Staff allowances | 8 |  | 10,000,000 |
| 12 | Administration Cost | 1 |  | 5,000,000 |
|  |  |  | Total | ugx 177,400,000 $ 66,692 |

DONOR AGENCY’S CONTRIBUTION PIG STY

(BUILDING)

| # NO | # ITEMS | # QUANTITY | UNIT COST IN UGX | TOTAL COST IN UGX |
| --- | --- | --- | --- | --- |
| 1 | Corrugated Iron Sheets | 12 bundles | 300,000 | 3,600,000 |
| 2 | Cement | 250 bags | 35,000 | 8,750,000 |
| 3 | Timber: 1” x 12” x12’ | 60 Boards | 14,000 | 840,000 |
| 4 | Timber: 2” x 12” x 12’ | 30 Pieces | 15,000 | 450,000 |
| 5 | Timber: 3” x 4” x 12’ | 10 Pieces | 13,000 | 130,000 |
| 6 | Timber: 2” x 4’ x 12’ | 50 pieces | 6,000 | 300,000 |
| 7 | Timber: 2 x 3 x 12 | 40 pieces | 2,700 | 108,000 |
| 8 | M.S. rods: ½” x 38’ | 55 length | 30,000 | 1,650,000 |
| 9 | M.S. rods: ¼” x 38’ | 10 length | 15,000 | 150,000 |
| 10 | Roofing nails | 40 packets | 5,000 | 200,000 |
| 11 | Head pans | 6 Head pans | 18,000 | 108,000 |
| 12 | Shovels | 5 Shovels | 45,000 | 225,000 |
| 13 | Wheel barrows | 3 wheel barrows | 100,000 | 300,000 |
| 14 | Binding wires | 1 roll | 90,000 | 90,000 |
| 15 | Double steel doors | 2 | 250,000 | 500,000 |
| 16 | Single steel doors | 1 | 175,000 | 175,000 |
| 17 | Window panes | 12 | 4,000 | 48,000 |
| 18 | Wire mesh | 4 roll | 75,000 | 300,000 |
| 19 | Wire nails (Assorted) | 150 packets | 5,000 | 750,000 |
| 20 | Tower bolts | 4 | 40,000 | 160,000 |
| 21 | Lockers | 3 | 30,000 | 90,000 |
| 22 | Paints (Assorted) | 22 gallons | 25,000 | 550,000 |
| 23 | paint brushes (Assorted) | 6 | 5,000 | 30,000 |
| # TOTAL |  |  |  | UGX19,354,000 $ 6,451.1 |

PIG STY BUILDING

LOCAL CONTRIBUTION

| No | Items | Quantity | Unit Cost | Total |
| --- | --- | --- | --- | --- |
| 1 2 3 4 | Land Sticks Food for work Skilled and Unskilled labor | Land 8 dozens lump sum | 2,700,000 40,000 850,000 1,200,000 | 2,700,000 40,000 850,000 1,200,000 |
|  |  |  | Total | UGX 4,790,000 $ 1,801 |

Project Budget Summary in UG Shillings and Dollars

| No | Items | Total cost in UGX | Donor Contribution In UGX | Local Contribution UGX |
| --- | --- | --- | --- | --- |
| 1 | Livestock Production | 145,800,000 | 145,800,000 |  |
| 2 | Animal Shelter | 19,354,000 | 19,354,000 |  |
| 3 | Animal Feed | 4,200,000 | 4,200,000 |  |
| 4 | Water Well | 5,500,000 | 5,500,000 |  |
| 5 | Drugs and Vaccine | 4,500,000 | 4,500,000 |  |
| 6 | Transportation of cows, goats, sheep, pigs and other items to project site | 2,400,000 | 2,400,000 |  |
| 7 | Local Contribution | 4,790,000 |  | 4,790,000 |
| 8 | Staff allowances | 10,000,000 | 10,000,000 |  |
| 9 | Administration Cost | 5,000,000 | 5,000,000 |  |
|  | TOTAL | UGX 203,544,000 $ 76,520 | UGX 198,754,000 $ 74,720 | UGX 4,790,000 $ 1,801 |