Proposal for Counseling and Training on the School Related Sexual and Gender Based Harassment Project

Bint-e-Hawa

(Daughter of Eve)

Break the Silence on Violence

Proposal written by:

Kamran Riaz

Director HRM

INSAF ORG

Ph: +92-91-5603037

Mob: +92-3219088071

Email: Kamran@insafngo.org

www.insafngo.org

31st March, 2014

Definition of Sexual and Gender-Based Violence/Harassment

Sexual and Gender-Based Harassment (SGBH) is harassment that is directed against a person based on gender. It constitutes a breach of the fundamental right of a person, liberty, security and dignity, equality between women and men, non-discrimination and physical and mental integrity. Gender-based Harassment reflects and reinforces inequalities between men and women.

Introduction

Pakistan stands sixth as the world's most populous country, with a GDI (Gender-related Development Index) ranking of 125th in the world out of 169 countries, and a GEM (Gender Empowerment Measure) rank of 99 out of 109 countries which is far blow average.

Pakistan has been the focus of fluctuating attention from donor organizations throughout its history. Two major disasters (the 2005 earthquake and the 2010 floods) have recently revived the interest of international donors and attracted new funding partners. However, additional issues have been raised too, especially in the aftermath of the recent floods, regarding the redirection of development funds towards emergency situations.

The role, responsibility and focus of donors on gender and violence issues when formulating development strategies, despite their apparent commitment, are unclear. Indeed, funding priorities do not point towards ending gender-based violence. The impact of these interventions is neither measured, nor very visible: there is neither any clear and consistent gender strategy among donors and international NGOs, nor a comprehensive data is available, which can be used as indicator or base when it comes to addressing issues like Sexual and Gender-Based Violence (SGBV), Sexual and Gender Based Harassment (SGBH) and Sexual Exploitation and Abuse (SEA) and that is the reason we cannot implement SGB strategies effectively. All the work that has been done was on the upper level or conducting seminars and having debates, but no one has ever tried to correct the problem at the grassroots level: working on the baseline. The websites of major donors, UN agencies and international NGOs do showcase programs and projects, but there was no indication of the use of impact indicators or indirect consultations and conversations. There is not any priority given to data collection from schools, colleges and universities and work on it, which stand as the baseline for implementing a gender-based strategy.

Pakistan has enacted a new law namely “the Protection against Harassment of Women at the Workplace Act, 2010” since last year. This is the first time that sexual harassment has been defined in Pakistan through a legislative instrument. Before this enactment, there was no clear definition of harassment, whether in public, private or workplaces. Section 509 of the Pakistan Penal Code 1860, explained “insulting the modesty” of a woman but there was no clear definition of “modesty." Moreover, there was no law to prohibit harassment at workplace.

In 2010, Government of Pakistan not only enacted a special law for preventing sexual harassment in the workplace but also amended section 509 of the Pakistan Penal Code. Now it clearly defines harassment and includes harassment at the workplace as well. It has further raised the maximum punishment for perpetrators from one to three years. Now under Section 509 of the Pakistan Penal Code, insulting the modesty of women or sexually harassing is a crime. The perpetrator of this crime may be punished with imprisonment, which may extend to three years or fine up to PKR 500,000 ($5000) or with both. However, this crime is still bail-able and compoundable (parties can settle the case between themselves even when matter is in the court, after permission of the court).

Islamic Republic of Pakistan signed the Conventions on the Right of the Child and on the Elimination of All forms of Violence and Discrimination against Women on 12 March 1996. Pakistan has commitment to universal education, gender equality and empowering of women. This is evident in the various domestic policies and laws endorsed by the previous government to preserve, protect and promote the rights of women and children. However, a review of the progress in universal primary education and initiatives undertaken in gender equality indicates that the targets achieved are not commensurate with input.

Project Background and Problem Statement

Despite all the legislation by the government, the condition of sexual harassment has been deteriorating in the absence of awareness. 100% female students that took part in our survey on SGBH do not know about those legislations at all thus making them ineffective because legislation is meaningless without making people aware that their legal rights do exist?

International researchers in the education sector have come to the conclusion that the missing link is the education of the girl child on harassment and violence (Source: Women in an Insecure World. DCAF Sep 2005). The argument has been made that access to schooling; successful performance and completion of education by girls will accelerate the rate of achieving universal primary education as well as most of the other national development goals. These goals cannot be achieved until children; boys and girls perceive educational institution as a safe and enabling environment.

Schools cannot be called prudent for children, especially girls until gender-based harassment is addressed. Most of the parents do not permit their female children to attend school as soon as they get puberty. The reason behind, it is the fact that they do not consider educational institutes safe enough. Currently, in Pakistan, interactions among students involve bullying, active or passive harassment and aggressive behavior largely by boys directed at girls. Such behavior is rarely punished.

Our law makers, law enforcers and school authorities are equally contributing to the cause by condoning sexual abuse and aggressive behavior. Lawmakers do the legislation but do not know how to interpret it to the concerned chunk of the society. Law enforcers make the process too lengthy, hectic and open that the aggrieved party becomes reluctant to report any incident and the school authorities never bother to make SGBH policies, therefore, schools have become breeding grounds for potentially damaging gendered practices, which remain with pupils into adult life. However, with appropriate intervention, effective advocacy and continuous reform programs, institutions can provide an enabling environment and a better learning place for the prevention of gender-based harassment, and it will stay for the rest of their lives with students. Educational institutions are breeding grounds for SGBH in all over the world. Reforms at this level would create a pounding effect on the overall situation of SGBH in the society, and reformed students would be better equipped to change the overall scenario.

The situation in Pakistan is worse than other under-developed countries, especially in the province of Khyber Pakhtun Khwa where orthodox Pathans are in majority. They do not permit their female children to get education in schools. But now the trend is changing. Now Pathans have realized the power of education but SGBH is still a big problem in the province. Before Pathans were unwilling to send their girls to school due to ignorance but now ignorance has been replaced by sexual harassment.

The Project: “Bint-e-Hawa (Daughter of Eve) Break the Silence on Violence

The idea of “Bint-e-Hawa (Daughter of Eve) Break the Silence on Violence was conceived after witnessing SGBH on and off the campus. This project is capable of providing the necessary intervention through provision of support services to victims of school-related gender-based harassment, creating platform where such cases can be reported, and through the establishment of a Gender Violence Survivor’s Support Network (GVSSN) in the targeted institutions to provide other support services to survivors. Bint-e-Hawa (Daughter of Eve) Break the Silence on Violence also sets up training programs for targeted communities to empower them with counseling skills to counsel survivors of school-related gender-based harassment. Bint-e-Hawa (Daughter of Eve) Break the Silence on Violence is a community-based counseling campaign which will be completed in four months duration. It will cater primarily to women and children survivors of SGBH. Bint-e-Hawa (Daughter of Eve) Break the Silence on Violence enjoys professional services of UNHCR and ATHA (Sweden) certified trainers, social coordinators and a very competent psychologist. It is expected that through training and support services to survivors, it  is possible to have a direct and positive effect on their well-being.

To address the problem of Sexual & Gender-Based Harassment (SGBH) we have selected educational institutions as baseline and collected comprehensive data on SGBH from six most populous schools, colleges and universities of district Peshawar:

- Forward High Schools for girls

- Forward College for Girls

- International College of Management Sciences (ICMS) School

- International College of Management Sciences (ICMS)

- Sarhad University of Information Technology Peshawar (Female Student

- IM Sciences University Hayatabad Peshawar (Female Student

Table-1

Composition of Sample Questionnaires Distributed and Questionnaires used

| Name of Institution | No. of Questionnaires Distributed | No. of Questionnaires Used |
| --- | --- | --- |
| Forward High Schools for girls | 75 | 53 |
| Forward College for Girls | 55 | 47 |
| International College of Management Sciences (ICMS) School | 60 | 55 |
| International College of Management Sciences (ICMS) | 65 | 57 |
| IM Sciences University Hayatabad Peshawar (Female Student | 80 | 80 |
| Sarhad University of Information Technology Peshawar (Female Student | 53 | 50 |
| Total | 388 | 342 (88%) |

Courtesy: Bright Future Organization Baseline Survey on SGBV 2013-14

Table-2

Students Response to 32 Questionnaire items

| S.No | Description | No. of Yes Responses | No. of “No.” responses |
| --- | --- | --- | --- |
| 1. | Do you know what sexual or gender based (SGB) harassment is? | 5 (10 %) | 45 (90%) |
| Have you ever faced any of the following in the campus: (Please check) |  |  |  |
| 2. | Unwanted text messages or calls | 19 (38%) | 31 (62%) |
| 3. | Pressurized to have a chat | 40 (80%) | 10 (20%) |
| 4. | Facial expression like winking or throwing kisses. | 48 (96%) | 2 (4%) |
| 5. | Followed by someone to home | 33 (66%) | 17 (34%) |
| 6. | Sexual comments, jokes or gestures | - 82%) | 9(18%) |
| 7. | Negative comments about being female | 50 (100%) | 0 (0%) |
| 8. | Having negative rumors spread around the school about you | 15 (30%) | 45 (70%) |
| 9. | Being teased with vulgar suggestive pictures from magazines | 8 (16%) | 42 (84%) |
| 10. | Being teased about being Islamic or Liberal | 29 (58%) | 21 (42%) |
| 11. | Being stared at in an offensive way | 50 (100%) | 0 (0%) |
| 12. | Being teased about your dressing | 43 (86%) | 7 (14%) |
| 13. | Being pressured to go out on dates | 42 (84%) | 8 (16%) |
| 14. | Being pressured to have friendship | 42 (84%) | 8 (16%) |
| 15. | Being assaulted physically/touched | 49 (98%) | 1(2%) |
| 16. | In what forms does SGB Harassment usually take place? Physical, Visual Verbal & non Verbal | 50 (100%) Yes in all forms | 0 (0%) |
| 17. | Do you think any of this behavior happens to girls in others schools? | 50 (100%) | 0 (0%) |
| 18. | Has any of your friends faced any or some or all of the above e mentioned harassment elsewhere. | 50 (100%) | 0 (0%) |
| 19. | How many incidents are in your notice regarding SGB Harassment on the campus? | 49 (98%) | 1 (2%) |
| 20. | How does SGB Harassment make you feel? | 32 (64%) | 18 (36%) |
| 21. | Do you think SGB Harassment is a problem in or out of your institute? | Out 50 (100%) | In 0 (0%) |
| 22. | Who do you think does most of the harassing in a school setting? | Boys 50 (100%) | Girls 0 (0%) |
| 23. | Who is most likely to be harassed? | Girls 48 (96%) | Boys 2 (4%) |
| 24. | Do victims usually report when sexually harassed? | 2 (4%) | 48 (96%) |
| 25. | What would you do if you were sexually / physically harassed? Report to authorities 00 Report to family 05 Report to teacher 01 Inform your friends 40 Nothing 04 |  |  |
| 26. | Are you aware of your rights not to be harassed? | 7 (14%) | 43 (86%) |
| 27. | Do you know school's policy regarding SGB Harassment? | 0 (0%) | 50 (100%) |
| 28. | Do you suggest a seminar/workshop on SGB Harassment awareness on the campus? | 47 (94%) | 3 (6%) |
| 29. | What sort of training do you suggest? Physical 02 Awareness 44 Both 04 |  |  |
| 30. | Do you think you are safe? | 22 (44%) | 28 (56%) |
| 31. | Do you think your school/college has good SGBH policy? | 43 (86%) | 7 (14%) |
| 32. | Do you think law authorities should amend laws regarding SGBH? | 50 (100%) | 0 (0%) |

Courtesy: Bright Future Organization Baseline Survey on SGBV 2013-14

Table-3

Students Responses to 32 Questionnaire items

|  | Description | Forward High Schools for girls |  | Forward College for Girls |  | International College of Management Sciences (ICMS) School |  | International College of Management Sciences (ICMS) |  | IM Sciences University Hayatabad Peshawar (Female Student |  | Sarhad University Of science And Tech Peshawar |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Responses (Nos. and % age) |  | Responses Nos. and % age) |  | Responses Nos. an d% age) |  | Responses Nos. and % age) |  | Responses Nos. and% age) |  | Responses Nos. and%age) |  |
| S.No. |  | Yes | No. | Yes | No. | Yes. | No. | Yes. | No. | Yes | No. | Yes. | No. |
| 1. | Do you know what sexual or gender based (SGB) harassment is? | 5 10% | 45 90% | 3 6% | 47 94% | 38 76% | 12 24% | 33 66% | 17 34% | 42 84% | 8 16% | 41 82% | 9 18% |
|  | Have you ever faced any of the following in the campus: (Please check) |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. | Unwanted text messages or calls | 19 38% | 31 62% | 15 30% | 35 70% | 44 88% | 6 12% | 44 88% | 6 12% | 22 44% | 28 56% | 19 38% | 31 62% |
| 3. | Pressurized to have a chat | 40 80% | 10 20% | 36 72% | 14 28% | 42 84% | 8 16% | 44 88% | 6 12% | 33 66% | 17 34% | 30 60% | 20 40% |
| 4. | Facial expression like winking or throwing kisses. | 48 96% | 2 4% | 45 90% | 5 10% | 46 92% | 4 8% | 48 96% | 2 4% | 39 78% | 11 22% | 30 60% | 20 40% |
| 5. | Followed by someone to home | 33 66% | 17 34% | 37 74% | 13 26% | 30 60% | 20 40% | 36 72% | 14 28% | 33 66% | 17 34% | 22 44% | 28 56% |
| 6. | Sexual comments, jokes or gestures | 41 82% | 9 18% | 43 86% | 7 14% | 46 92% | 4 8% | 48 96% | 2 4% | 41 82% | 9 18% | 42 84% | 8 16% |
| 7. | Negative comments about being female | 50 100 | 0 0% | 49 98% | 1 2% | 48 96% | 2 4% | 50 100 | 0 0% | 43 86% | 7 14% | 47 94% | 3 6% |
| 8. | Having negative rumors spread around the school about you | 15 30% | 45 70% | 3 6% | 43 94% | 17 34% | 33 66% | 13 26% | 37 74% | 11 22% | 39 78% | 18 36% | 32 64% |
| 9. | Being teased with vulgar suggestive pictures from magazines | 8 16% | 42 84% | 6 12% | 44 88% | 1 2% | 49 98% | 3 6% | 47 94% | 3 6% | 47 94% | 6 12% | 44 88% |
| 10. | Being teased about being Islamic or Liberal | 29 58% | 21 42% | 34 68% | 16 32% | 36 72% | 14 28% | 34 68% | 16 32% | 29 58% | 21 42% | 30 60% | 20 40% |
| 11. | Being stared at in an offensive way | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% |
| 12. | Being teased about your dressing | 43 86% | 7 14% | 39 78% | 11 22% | 43 86% | 7 14% | 41 82% | 9 18% | 25 50% | 25 50% | 37 74% | 13 26% |
| 13. | Being pressured to go out on dates | 42 84% | 8 16% | 45 90% | 5 10% | 32 64% | 18 36% | 41 82% | 9 18% | 18 36% | 32 64% | 30 60% | 20 40% |
| 14. | Being pressured to have friendship | 42 84% | 8 16% | 41 82% | 9 18% | 41 82% | 9 18% | 42 84% | 8 16% | 42 84% | 8 16% | 44 88% | 6 12% |
| 15. | Being assaulted physically/touched | 49 98% | 1 2% | 50 100 | 0 0% | 47 94% | 3 6% | 48 96% | 2 4% | 49 98% | 1 2% | 44 88% | 6 12% |
| 16. | In what forms does SGB Harassment usually take place? Physical, Visual Verbal & non Verbal (Yes all form) | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% |
| 17. | Do you think any of this behavior happens to girls in others schools? | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% |
| 18. | Has any of your friends faced any or some or all of the above e mentioned harassment elsewhere | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% |
| 19. | How many incidents are in your notice regarding SGB Harassment on the campus? | 49 98% | 1 2% | 48 96% | 2 4% | 38 76% | 12 24 | 34 68% | 16 32% | 22 44% | 28 56% | 15 30% | 35 70% |
| 20. | How does SGB Harassment make you feel? | 32 64% | 18 36% | 35 70% | 15 30% | 22 44% | 28 56% | 30 60% | 20 40% | 4 8% | 46 92% | 9 18% | 41 82% |
| 21 | Do you think SGB Harassment is a problem in or out of your institute? (out side) | 50 100 | 0 0% | 50 100 | 0 0% | 21 in 42% | 29 out | 18in 36% | 32out 64% | 10in 20% | 40 80% out | 18 in 36% | 32 64% out |
| 22. | Who do you think does most of the harassing in a school setting? (50 boys 100%) Girls 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% |
| 23. | Who is most likely to be harassed (Girls -48 and Boys- 2) | 48 96% | 2 4% | 50 100 | 0 0% | 49 98% | 1 2% | 50 100 | 0 0% | 50 100 | 0 0% | 48 96% | 2 4% |
| 24. | Do victims usually report when sexually harassed? | 2 4% | 48 96% | 5 10% | 45 90% | 3 6% | 47 94% | 4 8% | 46 92% | 6 12% | 44 88% | 1 2% | 49 98% |
| 25. | What would you do if you were sexually/physically harassed? Report to authorities Report to family Report to teacher Inform your friends Nothing | 00 05 01 40 04 |  | 02 05 04 35 04 |  | 05 03 07 30 05 |  | 02 04 09 30 05 |  | 03 06 06 30 05 |  | 01 05 10 25 09 |  |
| 26. | Are you aware of your rights not to be harassed? | 7 14% | 43 86% | 4 8% | 46 92% | 33 66% | 17 34% | 38 76% | 12 24% | 42 84% | 8 16% | 45 90% | 5 10% |
| 27. | Do you know school's policy regarding SGB Harassment? | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100% | 5 10% | 45 90% | 10 20% | 40 80% |
| 28. | Do you suggest a seminar/workshop on SGB Harassment awareness on the campus? | 47 94% | 3 6% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 47 94% | 3 6% | 50 100 | 0 0% |
| 29. | What sort of training do you suggest? Physical Awareness Both | 2 44 4 |  | 4 40 6 |  | 7 40 3 |  | 6 40 4 |  | 10 38 2 |  | 15 30 5 |  |
| 30. | Do you think you are safe? | 22 44% | 28 56% | 20 40% | 30 60% | 1 2% | 49 98% | 3 6% | 47 94% | 9 18% | 41 82% | 3 6% | 47 94% |
| 31. | Do you think your school/college has good SGBH policy? | 43 86% | 7 14% | 42 84% | 8 16% | 40 80% | 10 20% | 42 84% | 8 16% | 31 62% | 19 38% | 25 50% | 25 50% |
| 32. | Do you think law authorities should amend laws regarding SGBH? | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% | 50 100 | 0 0% |

Courtesy: Bright Future Organization Baseline Survey on SGBV 2013-14

It was found that there is a significant lack of Sexual and Gender-based Harassment (SGBH) awareness and girls are easy target to SGBH. They have been harassed (physically and mentally) on a regular basis and have no remedy to deal with the situation. It is a normal practice and they have been living with that. Besides that, there is neither school counseling system, focal person nor SGBH policy to meet with such mutiny and thus condoning SGBH. Educational institutions, therefore, can be breeding grounds for potentially damaging gendered practices which remain with pupils into adult life. However, with appropriate intervention, educational institutions can provide effective and enabling environment for the prevention of gender-based violence, which will definitely make an impact on the overall poor condition of our society in terms of SGBH. Our survey has shown that most of the harassment takes place from school to college-level female students, and they have severe need of training on SGBH.

The main objective of the proposed project is to provide quality counseling services to youth who is either victim of school-related gender-based SGBH or future prospects. There is a significant need for the provision of training and counseling to the victims as well as stakeholders of the target institutions in order to enable them to counsel the students themselves.

Psychosocial counseling, advocacy and training are core mandates of “Bint-e-Hawa (Daughter of Eve) Break the Silence on Violence (Daughter of Eve)”. Counseling is the process of helping people to realize the potentials in them to solve their problems. It is important for Bint-e-Hawa (Daughter of Eve) Break the Silence on Violence to seek the welfare of its clients and make females understand that they are heard, taken seriously and most importantly are believed, and they can stop what has been haunting them since childhood.

The main goal in this area is to create a confidential and safe platform for girl survivors to air their feelings and experiences with a counselor who are equipped with the knowledge and skills in helping them to cope with their situation, through group counseling and individual counseling. Through participation in supportive counseling and groups, survivors will realize they are not alone in their struggle against SGBH and are able to learn new strategies for taking control over their lives.

Target

To form Students, Teachers Committee (STC) and to increase opportunities that will create a forum for sharing ideas, experience and learning about SGBH among community members (students, parents, teachers and other stakeholders).

To provide services and referral systems for psychological counseling, medical support and services for victims and their parents.

To provide training in counseling to students, community volunteers, peer counselors and teachers and sensitize the school community on SGBH, what it is, the effects, and what should be done.

To acquire the services of a psychologist for the training and pursue school authorities to cater the services of a psychologist on a permanent basis to render his/her services to the survivors.

To create/increase awareness about the existence of SGBH in the proposed communities through a sensitization outreach as our initial step towards addressing the problems of SGBH. This will be done by partnering with the advocacy group of the project.

To sensitize students on their rights and responsibilities as children in the society, empower abused victims through counseling and developing long-term safety plans for them. Sensitize and train teachers and school attendants on the appropriate means of control to ensure discipline in schools. To encourage victims to break the silence, speak out and seek help when they are abused, or find their friend, neighbor being abused. We will also provide various training modules to school counselors. Bint-e-Hawa (Daughter of Eve) Break the Silence on Violence will help the targeted institution to develop their policy on SGBH through our experts.

To create a Gender Violence Survivor’s Support Network (GVSSN) shall be established which will include the concerned police station in the area, parents, focal person of the institution and SGBH activists from three different NGOs.

To collect reliable and actual data on SGBH and to maintain a comprehensive database of incidents for future training programs.

Targeted Population of the Project

Statistics (Population, Education, Target Institutions)

Khyber Pakhtun Khwa Education Statistics by the Government of Pakistan 2011/12

| Source: Annual Statistical Report 2012. Government of Khyber Pakhtun Khwa Province | Stage | Urban |  |  | Rural |  |  | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Boys | Girls | Total | Boys | Girls | Total | Boys | Girls | Total |
| Khyber Pakhtun Khwa | Pre-Prime | 160767 | 109030 | 269797 | 665623 | 448565 | 1114088 | 826390 | 557495 | 1383885 |
|  | Primary | 282958 | 193358 | 476316 | 1376248 | 907714 | 2283962 | 1659206 | 1101072 | 2760278 |
|  | Middle | 137313 | 85732 | 223045 | 451119 | 211302 | 662421 | 588432 | 297034 | 885466 |
|  | High | 73971 | 46134 | 120105 | 179569 | 72876 | 252445 | 253540 | 119010 | 372550 |
|  | High Sec | 48456 | 26557 | 75013 | 68505 | 19171 | 87676 | 116961 | 45728 | 162689 |
|  | Degree | 31558 | 7816 | 39374 | 19832 | 2139 | 21971 | 51390 | 9955 | 61345 |
|  | Total | 735023 | 468627 | 1203650 | 2760896 | 1661667 | 4422563 | 3495919 | 2130294 | 5626213 |

# of Government and Non Government Institutes, Students, Teaching

& Non Teaching Staff by Level in District Peshawar

| Level | # of Private Institutions | # of Government Institutions | Enrollment |  |  | Teaching Staff |  |  | Non-Teaching Staff |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Boys Girls Total |  |  | Boys Girls Total |  |  | Boys Girls Total |  |  |
| Primary | 247 | 1450 | 21266 92320 | 12964 43456 | 34230 135776 | 492 2270 | 1577 1662 | 2069 3932 | 287 630 | 242 312 | 529 942 |
| Middle | 388 | 1234 | 49531 14588 | 25172 12077 | 74703 10907 | 1412 782 | 2848 880 | 4260 1662 | 515 278 | 399 190 | 914 468 |
| High | 344 | 789 | 46729 34920 | 101784 22342 | 148513 57262 | 3196 1521 | 4677 1078 | 7873 2599 | 1345 234 | 634 188 | 1979 422 |
| Higher Secondary/Inter College | 67 | 32 | 11964 2376 | 24859 2230 | 36823 4606 | 834 310 | 1268 260 | 2102 570 | 530 99 | 178 75 | 708 174 |
| University | 18 | 12 | 12082 14032 | 11062 11062 | 23144 25094 | 2458 2100 | 2379 1856 | 4836 3956 | 364 421 | 276 400 | 640 821 |

Source: Annual Statistical Report 2012. Government of Khyber Pakhtun Khwa

Strength of Target Institutions

| # Name of Institution Girls Female Total Teachers |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1 | Forward High Schools for girls | 119 | 21 | 140 |  |
| 2 | Forward College for Girls | 148 | 24 | 172 |  |
| 3 | International College of Management Sciences (ICMS) School | 115 | 21 | 136 |  |
| 4 | International College of Management Sciences (ICMS) | 121 | 19 | 140 |  |
| 5 | IM Sciences University Hayatabad Peshawar (Female Student | 438 | 18 | 456 |  |
| 6 | Sarhad University of Information Technology Peshawar (Female Student | 254 | 22 | 276 |  |
|  | Total | 1195 | 125 |  | 1320 |

Courtesy: Bright Future Organization Baseline Survey on SGBV 2013-14

Implementation Plan

- Two expert trainers (male, female) and a female psychologist on SGBH will conduct trainings in all institutions.

- A total of 1320 female students and teachers in all institutions shall be trained.

- Group discussion between male and female students shall be encouraged to make male students realize about the seriousness of the issue and take them onboard to stop SGBH in and outside the campus.

- All the female teachers shall be trained in order to guide and provide help to students after the completion of the project.

- A total of 12 training sessions would be held. The details are as under:

| Name of Institute Trainings |  |  |
| --- | --- | --- |
|  | Forward High Schools for girls | 2 |
|  | Forward College for Girls | 2 |
|  | International College of Management Sciences (ICMS) School | 2 |
|  | International College of Management Sciences (ICMS) | 2 |
|  | IM Sciences University Hayatabad Peshawar (Female Student | 2 |
|  | Sarhad University of Information Technology Peshawar (Female Student | 2 |
|  | Total | 12 |

- Informative pamphlets, booklets and papers shall be distributed among students.

- A focal person (teacher) in all institutes shall be appointed who will handle all the cases related to SGBH, and a representative from students shall also be designated for on the spot handling of a problem. Both focal person and student’s representative shall be separately trained for effective performance.

- A Gender Violence Survivor’s Support Network (GVSSN) shall be established which will include concerned police station in the area, parents, focal person of the institution and SGBH activists from three different NGOs. These NGOs are responsible for meeting with all focal persons at the start of every month and collect data on SGBH and to maintain a comprehensive database of incidents for future training programs.

- All institutions shall be aided to constitute their own SGBH policy both in Urdu and English languages. Our Legal advisors will draw a sample policy and make changes as per requirement.

- Posters on SGBH (size 1.5’ X 2’) shall be displayed in all classes, hostels, cafeterias and important places to remind students about their rights.

- Pages on social media (Facebook, Twitter) shall be created and all the trained students shall be invited to join them and give their feed back to the page managers. Page manager shall be in contact with GVSSN and would instantly report to the network in case of any SGBH without disclosing the identity of the whistleblower.

- A talk show shall be held on local television channel (http//kay2.tv), in which competent experts, government officials, activists and educationalists shall participate.

- Project Completion Ceremony will take place in Peshawar. Teachers from other institutions, politicians, government officials, leading activists, INGOs, and print and electronic media shall be invited for an effective advertisement of the project. It will also make ground for further training programs in other institutions.

An evaluation strategy will be designed to capture quantitative and qualitative data for the counseling and future programs.

Quantitative Data:

- # of school Teachers who have received training

- # of females attended program

- # of teachers who have been reached through outreach and training

- # of survivors and victims counseled

- # of cases that referred by focal persons

- # of cases solved by the focal person

- # of cases that were referred to the authorities or parents

- A survey questionnaire after every training shall be handed over to the participants and ask about their fresh views on SGBV and that survey would indicate us about the effectiveness of the training and whether or not it requires any other ingredients to add to training.

Qualitative Data:

- Level of satisfaction with services by the institution authorities.

- Level of satisfaction with every training program, this will be performed after every training program.

- Knowledge of survivors of their human rights and legal options.

- Increase in self-confidence among survivors

- Demonstrated skills of services providers in providing client-based, respectful, services to survivors.

- Change in media response to cases of SGBV.

- Change in policy makers’ response to the issue of school-related gender-based violence.

- Because these kinds of services are new to Peshawar, ongoing feedback from survivors accessing these services will be crucial to ensure that the services are meeting the actual needs of the survivors in the most effective and efficient manner.

Monitoring and reporting

Regular monitoring of all training will be done by the Monitoring Team; output analysis shall be shared with the donor on a regular basis.

All procurements should be done through proper channel and by advertisement.

A teacher from each venue would generate a report regarding training and express his/her comments which shall be shared with the donor. Heads from all institutions shall be requested to generate a Performance Letter.

All the departments related to the project shall generate its monthly progress report and submit them to the monitoring section where all the outputs are maintained in soft and hard form and then it will be further submitted to the donor.

Project completion report will be developed by the Project Manager and submitted to the donor at the end of the project.

Donor’s Visibility

Considering the project overview, security measure should be taken continuously with the law and order department. We will continuously coordinate with the stakeholders and security agencies. Due to war against terror situation of KPK continuously avoiding such type of activities to show off any activities outside the premises. For avoiding hurdles, we will pre-plan security measures for effective implementation of project in areas. Donor's visibility will be as following:

• Signboards, display panels, banners and commemorative plaques;

• Clothing items such as tee-shirts and caps worn by project staff;

• All printing material shall carry the logo of the donor.

• Pena flex banners, media projection and other advertisement shall carry donor’s name.

A Catalyst for Further Development

Our team wants this project to be a role model for others. We believe that we owe some services to the society and especially to the most vulnerable part of our society. All the rates in Bills of Quantity are the minimum. We want to present this program as an example of dedication, social services and a duty towards our society. We will tag this project as a medal for our future programs.

Risk and Success Factors

Risk Factors

The project risk factor is the slow pace of mind change of women as they are new to this change to stand against SGBH and also the community change of attitude about women’s rights as human rights. This is because gender relations are power relations and some men may resist the change. Due to socialization process some women have also been marginalized for long that they take gender based harassment as a cultural practice and a part of our society.

Another risk factor is that some acts of violence do not have legal provisions and this is frustrating for someone after knowing that her rights are not covered by law. It should however be noted that changing attitudes is a conceptual process and preventing gender based violence requires a multi-sectoral approach by different partners, members of society and authorities. The non-existence of associations and SGBH committees is also a risk factor.

Success Factors

The project success factors include:

• Availability of quality trainers, psychologists, involvement of few active human rights NGOs, fully cooperation of authorities and enthusiasm of female students are all success factors that will over-shadow all risk factors.

• The existence of supportive policies and legal framework for promotion of gender equality and women’s rights.

• The project implementing organization partnerships with other service providers including police and NGOs for promotion of women’s rights and responding to SGBH partners is an added value for project implementation.

Expected Results and Project Sustainability

Expected Results

We expect the following results from this project, namely:

- Increased women’s awareness on their legal rights.

- Women take a more active role in preventing and responding to sexual and gender based harassment.

- Formation of a well equipped team (GVSSN) and data collection system.

- Women have a more positive image and self worth and ready to protect their rights.

- Women are more informed of SGBH service providers and ready to report SGBH cases and

- Seek other support services.

- Formation of grassroots community based SGBH action groups established.

Project Sustainability

Training of participants on their legal rights, sexual and gender based violence and training of trainers in an assured way for women to campaign against gender-based violence and report cases of gender based violence having known their rights. Increased knowledge on legal rights and service providers also opens long term beneﬁts to women in responding to gender based violence.

All the teachers in all 6 institutes shall be trained to guide students on SGBH cases, help students to know their rights and defend themselves in case of any discrimination against them. After the completion of project, a well trained staff of 10 teachers in each institution shall take care of the matters and that will provide great sustainability to the project.

The existence of GBH structure in form of committees and associations gives opportunity for the formation of women community-based initiatives to prevent and respond to Gender Based Violence.

The formation of team of focal persons will create future strong platform for continued sensitizations on gender based violence. The implementation of a plan of action to be developed after the training would get support from the local leadership since preventing and responding to gender based violence is one of their performance rates. Promotion of SGBH at the community level is also one of the components of social development. The project implementation therefore its well within the national development vision and has a high level of political support.

Uniqueness of Bint-e-Hawa (Daughter of Eve) Break the Silence on Violence (Daughter of Eve)

The overall purpose of this training program is to increase participant’s knowledge and understanding of the concept of sexual and gender-based harassment, sexuality, and rights. It will further take a look at the various forms of gender-based violence and the core principles for a code of conduct, reporting mechanisms and developing a Pragmatic response .Such an event was never happened here in Peshawar. Different NGOs and INGOs conducted seminars, workshops and awareness sessions in luxury hotels and the participants were elite members of the society which have nothing to do with the issues. Bint-e-Hawa (Daughter of Eve) Break the Silence on Violence (Daughter of Eve) is first of its kind campaign which will be held on the places which are worst effected. We had asked administrations of all the participant institutions to give us details of programs on the issue that were conducted in their institutions and it is sad to say that there were none.

Another uniqueness of Bint-e-Hawa (Daughter of Eve) Break the Silence on Violence (Daughter of Eve) is that we have conducted actual surveys of the institutions and there is no data that is based on hypothesis. We have gathered actual data from actual students and our efforts were acknowledged by the institutions.

Limitation of the project

Two schools and two colleges selected are for girls only while the two universities are co-education institutes so we will provide awareness and training to females only of the above mentioned institutions. That was due to the reason that 99% harassment that occurs is against female students. We will arrange an awareness session for boys in the upcoming months.

Government run institutions were reluctant to allow us to survey the institutions due to their conservatism. We were asked to submit full copies of the proposal, donor’s name, agenda, budget, motives and NCOs from the directorate of Education. We were advised to submit application to the planning division and then discuss the whole program with a team from the education directorate. We were also informed that it will take two months for the approval and wont be easy to get approval on such a burning issue which could offend students and their parents. We were not welcomed to start a program on SGBH.

On the other hand, private institutions welcomed us and praised our motivation and allowed us to go ahead. They took only few days to decide and informed us about their decision. They also wanted us to conduct more and more awareness programs, training and book fairs in their schools. Their attitude was positive as compare to government officials.

Members of the Project Implementing Consortium:

(Registration Certificates of all consortium members attached as Annex 2)

International Needy Society of A Right Forum (INSAF) is a national non-profit and non-governmental organization established in 2002 and registered in March 2011, under the Societies Act of 1860 (Registration No. 1183/5/6623). It works for education, human rights, livelihood, and peace and security. INSAF Org is a member of World Youth Organization (WYO) Sexual Harassment Watch (SHW), Save the Children Pakistan and Child Rights Movement (CRM) and GROW (Group of Right Organizations and Workers) since 2010. INSAF’s organizational

Organizational capacity is as under:

# of Employees:		21

# of Officials: 		10

Financial Standing		Sound

# of Offices			02

Areas of Expertise		Education, Human Rights

Bright Future Organization (BFO) is a national non-profit and non-governmental organization established in 2002 and registered in February 2012, under the Societies Act of 1860 (Registration No. 605/5/7047). BFO works with some of the most underprivileged communities in the Peshawar region and Khyber Pakhtunkhwa Province of Pakistan; Education, human rights, responding to emergencies, improving access to quality health, creating livelihood opportunities, distributing foods and goods related to day to day life and working closely with communities to promote self-reliance, feed the poor, help the needy, human rights, peace and security. BFO has been a proud member of World Youth Organization (WYO) Sexual Harassment Watch (SHW), Save the Children Pakistan and Child Rights Movement (CRM) since 2010 and believe in equal gender rights and free of violence society.

Organizational capacity is as under:

# of Employees:		12

# of Officials: 		10

Financial Standing		Sound

# of Offices			01

Areas of Expertise		Education, Human Rights

Women’s Illustrative Network (WIN) is a leading NGO that works for the empowerment of women in Pakistan. It was registered on 11th August 2005 under the Social Welfare Agencies Ordinance 1961 (XLVI of 1961). WIN is an active member of Sabaoon NGO, Save the Children Pakistan, GROW (Group of Right Organizations and Workers) and CRM. WIN has expertise in media projection and public awareness.

Organizational capacity is as under:

# of Employees:		13

# of Officials: 		11

Financial Standing		Sound

# of Offices			01

Areas of Expertise		Media, Education, Human Rights, Livelihood

Special Voluntary Help offered by:

Child Rights Movement (CRM) is a network of 35 registered NGOs who actively participate in Human Rights activities. CRM is a fellow of Save the Children Pakistan, Alif Ailan Program (British High Commission Islamabad) and has deep roots in the society. CRM will help us spreading the word regarding our program through its members which will help our cause on wider basis.

Contact Details:

Mr. Kamran Riaz

Director Admin and HRM

INTERNATIONAL NEEDY SOCIETY OF A RIGHT FORUM (INSAF)

TF 364, Deans Trade Center

Islamia Road

Peshawar Cantt: 25000

KPK, Pakistan

Ph: +92-91-5603037

Mob: +92-3219088071, +92-3329236269

Email: kamran@insafngo.org

www.insafngo.org

Bank Account Details:

Bright Future Organization

KASB Bank

Peshawar Cantt: Branch.

KPK. Pakistan

Account # 0005-136138-001

IBN # PK83 PLCO 0000 0051 3613 8001

WORKPLAN CHART

| # | Description | Week 1 2 |  | Week 3 4 |  | Week 5 6 |  | Week 7 8 |  | Week 9 10 |  | Week 11 12 |  | Week 13 14 |  | Week 15 16 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Planing, Hiring, Meetings With Officials, Briefing, Preperations, Printing Material | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Training At Forward High Schools For Girls , Formation Of STC |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Training At Forward College For Girls, Formation Of STC |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Project Performance Report To The Donor, Preparation For Next Training |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
| 5 | Training At International College Of Management Sciences (ICMS) School , Formation Of STC |  |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |
| 6 | Training At International College Of Management Sciences (ICMS) , Formation Of STC |  |  |  |  |  |  |  |  | X | X |  |  |  |  |  |  |
| 7 | Training At IM Sciences, Formation Of STC |  |  |  |  |  |  |  |  |  |  | X | X |  |  |  |  |
| 8 | Training At Sarhad University Of Info: & Technology , Formation Of STC |  |  |  |  |  |  |  |  |  |  |  |  | X | X |  |  |
| 9 | Project Completion Ceremony |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |
| 10 | Project Completion Report To Donor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |

BUDGET

| Donor Name |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Tile | Bint-e-Hawa (Daughter of Eve) Break the Silence on Violence (Daughter of Eve) |  |  |  |  |
| IP Name | Consortium |  |  |  |  |
| Operation Area | Khyber Pakhtunkhwa (KPK) |  |  |  |  |
| Budget | 2014 |  |  |  |  |
| Project during | 4 Months |  |  |  |  |
| Account | Item Description | Unit | Months | Unit cost/PKR | Total cost/PKR |
| 1. Over head Cost |  |  |  |  |  |
|  | Finance Officer | 1 | 4 | 40,000.00 | 160,000.00 |
|  | Office rent | 1 | 4 | 20,000.00 | 80,000.00 |
|  | Office utilities(Internet, Elect:,Phone) | 1 | 4 | 5,000.00 | 20,000.00 |
|  | Communication (mobile) | 1 | 4 | 5,000.00 | 20,000.00 |
|  | Office Supplies (paper, prints etc) | 1 | 4 | 2,500.00 | 10,000.00 |
|  | Total |  |  |  | 290,000.00 |
| 2.Project Costs |  |  |  |  |  |
|  | Project Manager | 1 | 4 | 50,000.00 | 200,000.00 |
|  | Female trainer | 1 | 4 | 50,000.00 | 200,000.00 |
|  | Male trainer | 1 | 4 | 50,000.00 | 200,000.00 |
|  | Psychologist | 1 | 4 | 50,000.00 | 200,000.00 |
|  | Project Staff travel | 1 | 4 | 35,000.00 | 140,000.00 |
|  | Fuel and Lubricants | 1 | 4 | 10,000.00 | 40,000.00 |
|  | Training session refreshments | 12 | 4 | 8,000.00 | 384,000.00 |
|  | Project Completion Ceremony | 1 | 1 | 100,000.00 | 100,000.00 |
|  | Bank charges | 1 | 1 | 10,000.00 | 10,000.00 |
|  | Donor visibility | 1 | 1 | 50,000.00 | 50,000.00 |
|  | Base line evaluation survey | 1 | 1 | 50,000.00 | 50,000.00 |
|  | Total |  |  |  | 1,574,000.00 |
| 3.Project Objective Capacity Building |  |  |  |  |  |
|  | Training Material Books and tools | 6500 | 1 | 50.00 | 325,000.00 |
|  | (for 6500 students,teachers etc) |  |  |  |  |
| 4. Project sustainabilty |  |  |  |  |  |
|  | Videos, pictures, Electronic & Print media |  | 1 | 125,000.00 | 125,000.00 |
|  | Total Project Cost |  |  |  | 2,314,000.00 |

ANNEX 1

SURVEY QUESTIONNAIRE

SEXUAL & GENDER BASED HARASSMENT

- Do you know what sexual or gender based (SGB) harassment is?

- Have you ever faced any of the following in the campus: (Please check)

- Unwanted text messages or calls

- Pressurized to have a chat

- Facial expression like winking or throwing kisses

- Followed by someone to home

- Sexual comments, jokes or gestures

- Negative comments about being female

- Having negative rumors spread around the school about you

- Being teased with vulgar suggestive pictures from magazines

- Being teased about being Islamic or Liberal

- Being stared at in an offensive way

- Being teased about your dressing

- Being pressured to go out on dates

- Being pressured to have friendship

- Being assaulted physically/touched

- In what forms does SGB Harassment usually take place?

Physical,

Visual

Verbal

Non-Verbal

All

- Do you think any of this behavior happens to girls in others schools?

- Has any of your friends faced any or some or all of the above

mentioned harassment elsewhere.

- How many incidents are in your notice regarding SGB Harassment on the campus?

- How does SGB Harassment make you feel?

- Do you think SGB Harassment is a problem in or out of your institute?

- Who do you think does most of the harassing in a school setting?

- Who is most likely to be harassed?

- Do victims usually report when sexually harassed?

- What would you do if you were sexually/physically harassed?

Report to authorities

Report to family

Report to teacher

Inform your friends

Nothing

- Are you aware of your rights not to be harassed?

- Do you know school's policy regarding SGB Harassment?

- Do you suggest a seminar/workshop on SGB Harassment awareness on the campus?

- What sort of training do you suggest?

Physical

Awareness

Both

- Do you think you are safe?

- Do you think your school/college has good SGBH policy?

- Do you think law authorities should amend laws regarding SGBH?