## Budget
SEVAC FOUNDATION-UGANDA | 2019/2021, BUDGET PROJECTION
| Year One (UgShs) | Year Two (UgShs) | Year Three (UgShs) | Year Four (UgShs) | Year Five (UgShs)
INCOMES
Donations and Grants | 90000000 | 320500000 | 300000000 | 4500000000 | 500000000
Fundraising Activities | 0 | 12000000 | 20000000 | 20000000 | 30000000
Organisation incomes | 0 | 3000000 | 10500000 | 2500000 | 2500000
| 90000000 | 335500000 | 330500000 | 4522500000 | 532500000
EXPENDITURES
Personnel
Net Payments | 10800000 | 40260000 | 39660000 | 542700000 | 63900000
NSSF Charges | 2700000 | 10065000 | 9915000 | 135675000 | 15975000
Withhold Tax | 756000 | 2818200 | 2776200 | 37989000 | 4473000
Medical Insurance | 540000 | 2013000 | 1983000 | 27135000 | 3195000
| 14796000 | 55156200 | 54334200 | 743499000 | 87543000
Travels
Local Travel Fares | 1200000 | 0 | 0 | 0 | 0
Subsistence allowances on foriegn missions | 0 | 1400000 | 2600000 | 2900000 | 2900000
Local travel allowances | 1200000 | 1863500 | 2950000 | 2950000 | 2950000
| 2400000 | 3263500 | 5550000 | 5850000 | 5850000
Equiment and Capital Assets
Computers | 3800000 | 0 | 8400000 | 10600000 | 0
Vehicles | 0 | 25000000 | 35000000 | 0 | 45000000
Funiture and Fittings | 1200000 | 1400000 | 0 | 8500000 | 1200000
Assorted Communication equipements | 1000000 | 0 | 1100000 | 2000000 | 0
| 6000000 | 26400000 | 44500000 | 21100000 | 46200000
Core Programs/Sevices costs
Trainings/Local Capacity building | 20300000 | 31000000 | 29400000 | 44682000 | 44682000
Social Mobilisations and Coordinations | 17800000 | 17900000 | 18000000 | 22000000 | 22000000
Supplies and Deliveries | 0 | 7057500 | 7052400 | 8057500 | 9050000
| 38100000 | 55957500 | 54452400 | 74739500 | 75732000
Operational Costs
Office Rent | 3500000 | 7200000 | 13200000 | 13700000 | 13800000
Internet subscription and Online systems | 3200000 | 5600000 | 12800000 | 12800000 | 14900000
Telephone Charges | 120200 | 3500000 | 3500000 | 3500000 | 3500000
Office Utilities | 147000 | 850000 | 1400000 | 1400000 | 1400000
Staionery | 560000 | 1280000 | 1580000 | 1580000 | 1580000
Vehicle Rentals | 3600000 | 0 | 0 | 0 | 0
Vehicle Fuel and Manatenance | 1400000 | 3500000 | 13500000 | 18800000 | 20437500
| 12527200 | 21930000 | 45980000 | 51780000 | 55617500
Other Expenses
Bank Charges | 270000 | 1006500 | 1322000 | 22612500 | 2662500
Audit Charges | 900000 | 3355000 | 3305000 | 45225000 | 5325000
| 1170000 | 4361500 | 4627000 | 67837500 | 7987500
Net Income/Loss | 74993200 | 167068700 | 209443600 | 964806000 | 278930000
| 15006800 | 168431300 | 121056400 | 3557694000 | 253570000

## Work Plan
| SEVAC FOUNDATION-UGANDA | 2019-2021,WORKPLAN
Link to Logframe | Outocme & Output Statement |  | Core Indicators | Year One |  |  |  | Year Two |  |  |  | Year Three |  |  |  | Year Four |  |  |  | Year Five
|  | Targets |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
THEME 1 | STRENGTHEN PARTNERNSHIPS AND COLLABORATIONS
Outcome 1:1 | Strengthened cordination and collaborations with development partners
Output 1.1.1 | Build new partnerships locally and globally | 20 partners identified | # of donors, # of foundations and partnerships reached | bar: Year Two Q1 to Year Five Q4
Outcome 1:2 | The organisation able to receive funding at the right time
Output 1.2.1 | Projects supported and Implemented as planned in the workplan without delay | 10 projects | # of projects supported | bar: Year One Q3 to Year Five Q4
Outcome 1:3 | Ongoing participation in both Local and International NGO activities
Output 1.3.1 | Strengthen cordination and collaborations with local and International development actors |  | # of local forum identified | bar: Year Two Q1 to Year Five Q4
Output 1.3.2 | Participate in the Working thematic Groups | 3 Active group | # of groups | bar: Year Two Q1 to Year Five Q4
THEME 2 | PURSUE FUNDING OPPORTUNITIES
Outcome 2:1 | Enough funds availabe for the implementation of health projects
Outcome2:1.1 | Strengthening local coordination systems and dissemination of the national policy and plans
Output 2.2.1 | Particpation in national/local coordination system on implementation of development programs | 30 forum sessions | # of sessions | bar: Year One Q2 to Year Five Q4
Output 2.2.2 | Advocate for inclusing implementatiom of National Health programs at the various levels | bar: Year One Q2 to Year Five Q4
THEME 3 | VISIBILITY AND ACCESSIBILITY
Outcome 3:1 | Support health programs in the community for better service delivery
Output 3.1.1 | Develop and establish our online tracking tool for our monthly activities in communities | 10 help centres | # of centres | bar: Year One Q4 to Year Five Q4
Output 3.1.2 | Formation and Strengthening of local health networks among selected at risk communities | 50 networks | # of networks | bar: Year One Q4 to Year Five Q4
Output 3.1.3 | Organise local symposuims and awareness session on pressing health issues among the community Members | 3 Annual Sessions | # of sessions | bar: Year Two Q1 to Year Two Q4; Year Three Q4 to Year Four Q4; Year Five Q4
Outcome 3:2 | Increase participation in institutions of learning
Output 3.2.1 | Start on the presentations of research fundings of health projects at conferences and Universities | 10 presentations | # of presentations made | bar: Year Two Q1 to Year Five Q4
THEME 4 | EVALUATE ONGOING PROGRAMS
Outcome 4:1 | Support the ongoing initiatives in selected disadvantaged communities
Output 4.1.1 | Support training of beneficiaries on health related bussiness | 1,000 beneficiaries (700 male & 300 females) | # of people trained (M/F) | bar: Year Two Q1 to Year Five Q4
Output 4.1.2 | Support the piloting and start-up of health projects | 50 start-ups | # of start-up health projects | bar: Year Two Q1 to Year Five Q4