FEDA

Femmes et Education des Adultes

Women and Adult literacy

Education, A tool for transformation

- Project Title:

Women literacy centres in Kazimia and neighbouring villages/ South-Kivu/DRC

- Brief Overview of Country

Population:  59 million

Adult literacy rate:  67%

Female literacy rate:  54%

Below poverty line:  not avail.

Life expectancy:  46yrs

Religion: Catholic 50%; Protestant 20%, Kimbanguist 10%; Muslim 10%

Other 10%

The Democratic Republic of Congo (DRC) is the size of Western Europe bordering nine countries in central Africa. It is a country of extraordinary mineral wealth yet due to decades of misrule and two civil wars most of the population live in abject poverty. As many as five million people are thought to have died unnecessarily since the start of the civil wars in the late 1990s.

Education is not freely provided, leading to many families giving priority to sending boys to school. Congolese culture encourages women to stay at home and look after the family, thus severely inhibiting their access to education and development opportunities.

- Identified need for the project

FEDA conducted a needs assessment in 2007 involving community members, women, local schools and community leaders. Findings showed low levels of literacy for women and the need to restore women’s hope in literacy. The establishment of a women’s literacy centre will ensure that the cycle of female illiteracy is broken and that women have the opportunity to participate in social and economic community development.

FEDA admits literacy as a tool for empowerment, enabling women to take part in decision-making and literacy linked to key issues in people’s lives such as income generation, family health and conflict resolution.

- Project aim and Objectives

To promote female literacy and empower women to access development services to reduce poverty, tackle HIV/AIDS and women’s rights violations, and build peace

The specific objectives are:

- To increase the literacy skills of 300 rural women and girls (15-45 yrs)

- To establish women’s literacy and resource centres in three villages

- To train 20 Literacy Facilitators (4 from each village) on the integration of vocational training, life skills and conflict resolution into adult literacy provision

- To develop a set of literacy materials suitable for the target group

This community approach to literacy will focus on the realities of people’s lives and will include vocational trainings, life skills education, conflict resolution, reproductive health, HIV and AIDS, and women’s rights.

Literacy facilitation will be in Swahili as the mother tongue and targets the following 5 villages (Kazimia, Kabogo, Kavumbwe, Nguma and Kikonde)

- Project activities, timescale and targets

| Timescale | Activity | Participants |
| --- | --- | --- |
| Months 1 & 2 | Consultation with local community members and traditional leaders to select suitable venues | 25 participants per village (incl. 5 leaders & 20 community members, with respect to gender balance) |
|  | Selection of Literacy Facilitators from the local community | 20 Facilitators (4 per village, at least 2 women per village) |
| Month 3 | 3 week training of Facilitators by FEDA trainers at Kazimia village | 20 Facilitators (4 per village) |
| Months 4 & 5 | Literacy classes meeting 3 times per week in each village | Average 60 learners per village |
|  | Establishment of adult literacy resource centres | All villages |
| Month 6 | Literacy classes meeting 3 times per week in each village | 300 Learners ( All villages) |
|  | Running adult literacy resource centres | All villages |
|  | Mid-term evaluation | Project team & Facilitators and village literacy committees |
| Months 7 & 8 | Literacy classes meeting 3 times per week in each village | 300 Learners |
|  | Running adult literacy resource centres | All villages |
| Month 9 | Literacy classes meeting 2 times per week in each village | 300 learners |
|  | Running adult literacy resource centres | All villages |
|  | Vocational trainings (tailoring, farming & husbandry, soap making, food production, conservation) | Average 60 learners per village |
| Month 10-12 | Literacy classes meeting 2 times per week in each village | 300 Learners |
|  | Running adult literacy resource centres | All villages |
|  | Vocational trainings | Average 60 learners per village |
|  | End of the year evaluation | Project team & Facilitators and village literacy committees |
|  | Appreciation ceremonies for Facilitators | Learners & facilitators |
|  | Reporting | Project team |

- Project Expected Outcomes

- Increased value placed on girl’s education and adult literacy

- Increased self-confidence and empowerment of women to bring about change in their lives, represent themselves, work collectively and participate in civic affairs

- Increased understanding of family and reproductive health, and HIV and AIDS

- Reduction in risky sexual behaviour among young people and empowerment of women to make informed decisions about their reproductive health

- Better management of family and local community conflicts

- Increased understanding of the status and important roles of women in the family and community, and the need to create opportunities for neo-literate women to step out of the household and involve themselves in vocational trades and business entrepreneurship

- Project outreach/target groups

- 300 women and girls (15 to 45 years) who did not have the opportunity to complete school

- 20 Literacy Facilitators from the local community, at least 50% women

- Indirectly, around 1,000 family members of literacy learners / Facilitators (through increased household income, improved family health, better conflict management and increased commitment to sending children to school)

- Organisational capacity

Established as a CBO/NGO September 2007 on World Literacy Day, FEDA exists to heighten social awareness, increase school enrolment of girls, self-confidence and personality development, to promote gender equity, women’s empowerment and the status of women in the family and community, to enable educational equality and to help build peace.

Since its creation, FEDA conduct literacy classes in Buma, Kibanga and Nguma. FEDA currently has 240 learners enrolled in three centres. They target young girls who dropped-out of their studies, household women and the wider female community.

FEDA has experience in the following areas: literacy, foreign languages apprenticeship, vocational trainings, Support of girls in schools, peace education and conflict resolution, women’s rights, reproductive health education and life skills education.

Members of FEDA form part of the annual general meeting for elections, appraisal of reports and provision of more perspectives. Five elected members form the Board of Directors, elected for three years for decision and administration and the coordination of staff and volunteers.

The work of FEDA is supported by X-Y (Netherlands), Feed the Minds ( UK), Self-funding and a range of contributors locally

- Monitoring and evaluation of the project

Weekly coordination meetings and periodic evaluations will take place for each activity under the responsibility of the Project Coordinator. FEDA will collect success stories, and organise focus group discussions, interviews with participants, field reports and project management sittings. The results will be reported at each stage of the project implementation and placed in libraries and public education settings. At the end of the programme duration, an evaluation involving all stakeholders and beneficiaries will be carried out to identify success, setbacks and plans for future work.

- Sustainability

This project is the result of a community initiative which already has the support of the target group. It is expected that learners will make a small financial contribution to the cost of their exercise books and pens to ensure their commitment and project sustainability. FEDA will also work with local leaders to ensure that the project becomes the property of the village and village leaders mobilise resources in their communities for the project sustainability.

- Project Budget

This budget is made in in Euro.

| Expenditure items | Requested Funds | FEDA contribution | TOTAL |
| --- | --- | --- | --- |
| EQUIPMENT AND MATERIALS FOR THE PROJECT |  |  |  |
| 1 laptop | 350 | 0 | 350 |
| 1 printer | 50 | 0 | 50 |
| 1 photocopy machine | 300 | 0 | 300 |
| 1 binding machine | 50 | 0 | 50 |
| Blackboards | 100 | 0 | 100 |
| Books for literacy resource centres in 3 villages @ 200 EUR/ per village | 400 | 0 | 400 |
| Total capital costs | 1,250 | 0 | 1,250 |
| PROJECT OPERATIONAL COSTS |  |  |  |
| A.Project staff cost |  |  |  |
| Allowance of the project coordinator | 500 | 500 | 0 |
| Allowance for 20 facilitators @ 100 EUR each | 2,000 | 0 | 2000 |
| Allowance for 3 vocational trainers @ EUR 150 each | 400 | 0 | 400 |
| Sub-Total | 2,900 | 500 | 3,400 |
| B) Consultation with community members & traditional leaders in 3 villages |  |  |  |
| Displacement for facilitators | 150 | 0 | 150 |
| Refreshments for participants | 180 | 0 | 180 |
| Travel for FEDA staff | 0 | 100 | 100 |
| Sub-Total | 330 | 100 | 260 |
| C) Training of literacy facilitators |  |  |  |
| Displacement participants | 100 | 0 | 100 |
| Feeding the participants | 1200 | 0 | 1200 |
| Lodging participants | 450 | 0 | 450 |
| Allowance for facilitators | 200 | 0 | 200 |
| Sub-Total | 1,950 | 0 | 1,950 |
| D) Literacy classes |  |  |  |
| Education materials for facilitation (books, pens, flip-charts, chalks…) | 600 | 0 | 600 |
| Exercise books & pens for learners | 350 | 0 | 350 |
| Sub-Total | 950 | 0 | 950 |

| E) Materials for the vocational trainings elements | 1,200 | 300 | 1,500 |
| --- | --- | --- | --- |
| F) Communications | 200 | 200 | 400 |
| G) Appreciation ceremonies for facilitators & learners | 300 | 100 | 400 |
| H) Reporting | 0 | 400 | 400 |
| I) Monitoring & evaluations | 600 | 0 | 600 |
| Total operational cost | 8430 | 1600 | 10030 |
| TOTAL BUDGET | 9680 | 1600 | 11280 |