## Proposed QMS Implementn Budget
KENYA COFFEE PRODUCERS ASSOCIATION
PROPOSED BUDGET FOR IMPLEMENTING QMS IN 5 SOCIETIES
SOCIETY | NUMBER OF FARMERS | PERMANENT STAFF | COMMITTEE MEMBERS | NUMBER OF WET MILLS
TENDELYANI | 899 | 9 | 9 | 1
KIRIANI | 1100 | 15 | 10 | 3
KAMACHARIA | 7365 | 21 | 10 | 4
AGUTHI | 1964 | 32 | 8 | 4
KAGAARI S | 3010 | 20 | 8 | 5
TOTAL | 14338 | 97 | 45 | 17
EURO= Ksh 110
SOCIETY | Budget -Ksh | Budget -Euro
TENDELYANI | 8405628.75 | 76414.8068
KIRIANI | 9255275 | 84138.8636
KAMACHARIA | 13965781.25 | 126961.6477
AGUTHI | 9568355 | 86985.0455
KAGAARI S | 11760112.5 | 106910.1136
Combined costs for all Five | 33719100 | 306537.2727

## imlementation plan
KCPA
KCPA COFFEE IMPROVEMENT PROJECT
QMS Implementation Timetable
Legend
KCPA & Trainers
KCPA Team & Coops/ Farmer Teams
Months | May-Aug 2013 | Sept-Dec 2013 | Jan-April 2014 | May-Aug 2014 | Sept-Dec 2014 | Jan-April 2015 | May-Aug 2015 | Sept-Dec 2015 | Jan-April 2016
Activities
Holding of sensitisation meetings for farmers
Elect Lead farmers
Due Diligence on elected PF’s farms
Establish members of the quality team( project management team) at Coop level
Data collection by Lead farmers
Coffee production training for KCPA Staff ( 1 week training at CRF)
Induction training for Lead farmers- Coffee chain, GAPs, Calendar of activities, record keeping, gender standards – 1 day workshop
Training of Lead farmers on GAPs (pruning, coffee nutrition crop protection, soil management, coffee picking and processing)- 2 day workshop
Soil analysis for Lead farmers
Selection of demonstration plots
Training on good coop management for Management Committee/ supervisory
Training of Lead farmers on climate change adaptation and mitigation- 2 day workshop
Risk and opportunity analysis - 2 day workshop
Training on coffee processing for factory managers/ factory workers
Training on coffee and tree nursery management
Training of Lead farmers on sustainable agricultural land management practices(SALMs)- 2 day workshop
Training of the quality management teams
Zonal training of farmers by Lead farmers
Quarterly trainings for Lead farmers
Quarterly reviews of project plan/ activities
Completion of quality plans for wet mills
Training of KCPA staff on certification Standards
Training Lead farmers on the use of GAPs to make farmers more resilient to climate change- 2 day workshop
Training Lead farmers and spray operators(team) on pesticide application and safe use.
Farmers field days ( 1 per wet mill)
Exposure visit to certified Coops by Lead farmers and quality teams
Computer application training at Coop and wet mills ( Staff and Management)
NEMA Audit for Wet Mills
Training on social and environmental standards – quality teams and staff-Occupational health and safety, fire fighting, first aid , CBA and Gender standards etc
Survey of wet mills / dry mill to assess status, capacity and constraints
Application for certification
Capacity building for Coops , Wet Mills , Dry mills- Computers, fire equipments, first aid kits, sample drying tables, moisture meters, cupping labs
Completion of the Quality Management System/Internal Control System
Self assessment before verification
Verifications
Data collection by Lead farmers